## owssvr
Activity Name | Activity Number | Office | Keywords | Activity Type | Predecessors | Successors | WBS Code | WBS | Duration | Brief Description | When is this activity needed | When is this activity NOT needed | Start Date | End Date | Critical Path | Other Notes | PDP Reference | Corrections and Recommendations | Step Count | Roles | Logic Features | Primary Constraint | Complete | Evaluation | HISTORICAL ACTIVITY (Y or N) | Roles4 | ID | Item Type | Path
PAR Checkpoint 1a - Introduce Project to Agencies | 01712 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | Consultant Kick-Off Meeting, Develop Project Framework Agreement (PFA), PE Funding Authorization | PAR Checkpoint 1b - Decide if PAR process will continue | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 40d | PAR Checkpoint 1a - Introduce Project to Agencies [Early Coordination/Need & Purpose] | Major widening and new location projects | All non-major widening and non-new location projects [Unless PTIP results suggest otherwise] | After schedule has been approved and staff asignments made; if consultant work, following NTP | GDOT letter submitted to LFA & USACE recapping discussion | [10 empty] | N |  | 1 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 1b - Decide if PAR process will continue | 01719 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Finish Milestone | PAR Checkpoint 1a - Introduce Project to Agencies | Define Project Concept (scoping or pre-concept), Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Create & Submit Environmental Study Area Layout, Data Acquisition for Scoping or Concept (with steps), Define Project Concept, PAR Checkpoint 2a - Evaluation for Alternatives carried forward | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 0d | PAR Checkpoint 1b - Decide if PAR process will continue | Major widening and new location projects | All non-major widening and non-new location projects [Unless PTIP results suggest otherwise] | GDOT letter submitted to LFA & USACE recapping discussion | LFA & USACE response | [10 empty] | N |  | 2 | Item | employeecenter/SAM/Lists/SAM
Define Project Concept | 00300 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Consultant Kick-Off Meeting, Develop Project Framework Agreement (PFA), FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps), Finalize Scoping and Outreach Materials, Finalize Screen 1 Report, Finalize Screen 2 Report, Finalize Screen 3 Report, Notice to Proceed (NTP) for Consultant Contract, PE Funding Authorization, PAR Checkpoint 2c - Submit range of alternatives, PAR Checkpoint 1b - Decide if PAR process will continue | Concept Meeting, Initial Concept Meeting, Local/Consultant Finalize Concept Report, Obtain Geotechnical Borings, PM Request VE Study, PM Reviews Concept Report, PM Submit Concept Report, Receive Environmental Study Area Layout / Start Environmental Studies, Receive Layout for UST/HW Phase I, Request Public Information Open House (PIOH), Request Soil Survey/Ex Pvmt Eval, Review Local/Consultant Draft Concept for Concept Meeting, Start Database Preparation | 5.1 | Local and Consultant Design for Concept | 120d | Define Project Concept-00300 This was the start milestone for concept development from the old Artemis schedule. It has been replaced with activity 19311- Roadway Design Concept Activities LOE (in house design). | In 2019 GENESIS Template |  |  |  |  | In 2019 GENESIS Template---- Roadway Design previously wanted this activity deleted |  |  |  | Roadway Design Engineer |  |  |  |  | N |  | 3 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY Practical Alternative Report Development (with steps) | 02000 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | 1st Concept Layout Revisions for PAR | Site Meeting with Resource Agencies for PAR | 5.4 | PAR Activities (old -- for reference only) | 85d | HISTORICAL OLD PAR ACTIVITY; Road Design develops PAR. | When more than one project location should be considered. | When there are not multiple location alternatives for a project. | after 1st Concept Layout Revisions for PAR are complete | when Practical Alternative Report Development is complete. |  |  |  |  | 4 | Roadway Design Engineer |  |  |  |  | Y | Roadway Design Engineer | 4 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 2a - Evaluation for Alternatives carried forward | 01732 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | PAR Checkpoint 1b - Decide if PAR process will continue | PAR Checkpoint 2b - Agency evaluation of alternatives carried forward, PAR Checkpoint 2c - Submit range of alternatives | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 40d | PAR Checkpoint 2a - Evaluation for Alternatives carried forward [Pre-Application/Alternatives] | Major widening and new location projects [unless outcome of 01719 is not to prceed to CP2] | All non-major widening and non-new location projects and those major widening and new location projects that do not advance past CP1 | Once alternative development has begun | GDOT information on alternatives being considered for advancement submitted to LFA & USACE | [10 empty] | N |  | 5 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 3d - Agency agreement on preliminary LEDPA/Prefered Alternative | 01799 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Finish Milestone | PAR Checkpoint 3b - Agency Review of PAR Report, PAR Checkpoint 3c - Hold Interagency PAR Meeting, PAR Checkpoint 3a - Prepare PAR Report | Preliminary Roadway Plans (consultant design), Receive Environmental Resource Boundaries (consultant design), Start Preliminary Roadway Plans, Receive Environmental Resource Boundaries (in-house design), Concept Report Review and Comments, Start Database Preparation, Conduct Avoidance and Minimization Measures Meeting (A3M), Concept Report Review and Comments, Receive Environmental Resource Boundaries (consultant design) for scoping phase | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 0d | PAR Checkpoint 3d - Submit least damaging alternative to design | Projects requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Projects NOT requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Interagency PAR meetng | USACE response | OES does not "submit" an alternative to design | [9 empty] | N |  | 6 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Review Existing Power Facilities for ITS | 01450 | TRAFFIC OPS | ITS;#27 | Task Dependent | Initial Concept Meeting | PM Submit Concept Report | 12.5 | ITS Development | 60d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN CURRENT GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 7 | Item | employeecenter/SAM/Lists/SAM
Concept Development Summary | 00200 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | WBS Summary |  |  | 1BB_CONCEPT | Concept Phase | 673d | [10 empty] | Project Manager |  |  |  |  | N | Project Manager | 8 | Item | employeecenter/SAM/Lists/SAM
Develop Project Framework Agreement (PFA) | 00110 | PROGRAM DELIVERY | Local;#9;#PM;#18 | Task Dependent | PE Funding Authorization | Define Project Concept, PAR Checkpoint 1a - Introduce Project to Agencies | 1.1 | Local Government Agreements | 60d | agreement between locals and GDOT; a document that has the % participation in funding, associated costs of each phase. | For local projects with federal funds | PFA is not needed for some local projects like scoping project with no reimbursable funds | Once PE is authorized, PFA is drafted and sent through CATS | It is an open agreement - no end date so if project starts and stops, PM does not need a new one unless there are STIP changes |  | only binding for Prelim; blank copy is sent to locals of local let approval form is separate, if local $ and just scoping phase, there is a MOA for oversight activities in lieu of PFA(does not cover ROW or CST) If more $ is needed, the PFA can be amended. |  |  |  | n/a |  |  |  |  | N | n/a | 9 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 3a - Prepare PAR Report | 01762 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | PAR Checkpoint 2c - Submit range of alternatives, Environmental Resource Identification Complete, Environmental Resource Identification Complete | PAR Checkpoint 3b - Agency Review of PAR Report, PAR Checkpoint 3d - Submit least damaging alternative to design | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 60d | PAR Checkpoint 3a - Prepare PAR Report | Projects requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Projects NOT requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Development of alternatives and impact comparison | Completion of PAR Report | [10 empty] | N |  | 10 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY Pre-Concept Meeting for PAR | 01800 | ROADWAY DESIGN | PAR;#10;#Roadway;#22 | Task Dependent | Initial Concept Meeting, Initial PAR Layout | 1st Concept Layout Revisions for PAR | 5.4 | PAR Activities (old -- for reference only) | 1d | HISTORICAL OLD PAR ACTIVITY Road Design meets with GDOT SMEs to discuss alternatives. | When more than one project location should be considered. | When there are not multiple location alternatives for a project. | after Initial PAR Layout | when Pre-Concept Meeting for PAR layout is complete. | [5 empty] | n/a |  |  |  |  | Y | Roadway Design Engineer | 11 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 3c - Hold Interagency PAR Meeting | 01782 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | PAR Checkpoint 3b - Agency Review of PAR Report | PAR Checkpoint 3d - Submit least damaging alternative to design | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 10d | PAR Checkpoint 3c - Hold Interagency PAR Meeting | Projects requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Projects NOT requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | End of PAR Report review period | Interagency PAR meetng | [10 empty] | N |  | 12 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 3b - Agency Review of PAR Report | 01772 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | PAR Checkpoint 3a - Prepare PAR Report | PAR Checkpoint 3c - Hold Interagency PAR Meeting, PAR Checkpoint 3d - Submit least damaging alternative to design | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 30d | PAR Checkpoint 3b - Agency Review of PAR Report | Projects requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Projects NOT requiring a Regional General Permit 35 or an Individual Permit under Section 404 of the Clean Water Act | Submittal of PAR Report to Agencies | End of review period - 30 business days | Agreed upon review period is 30 business days (6 weeks, approximately 45 calendar days) | [9 empty] | N |  | 13 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY 1st Concept Layout Revisions for PAR | 01900 | ROADWAY DESIGN | PAR;#10;#Roadway;#22 | Task Dependent | Pre-Concept Meeting for PAR | Concept Meeting, Develop Concept Layout of Preferred Alternate (with steps), Practical Alternative Report Development (with steps) | 5.4 | PAR Activities (old -- for reference only) | 5d | HISTORICAL OLD PAR ACTIVITY; Road Design uses meeting to develop first Concept layout revisions. | When more than one project location should be considered. | When there are not multiple location alternatives for a project. | after Pre-Concept Meeting for PAR | when 1st Concept Layout Revisions for PAR layout is complete. | [5 empty] | Roadway Design Engineer |  |  |  |  | Y | Roadway Design Engineer | 14 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 2b - Agency evaluation of alternatives carried forward | 01742 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Task Dependent | PAR Checkpoint 2a - Evaluation for Alternatives carried forward | PAR Checkpoint 2c - Submit range of alternatives | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 40d | PAR Checkpoint 2b - Agency evaluation of alternatives carried forward | Major widening and new location projects [unless outcome of 01719 is not to prceed to CP2] | All non-major widening and non-new location projects and those major widening and new location projects that do not advance past CP1 | GDOT information on alternatives being considered for advancement submitted to LFA & USACE | Following interagency meeting, GDOT letter submitted to LFA & USACE recapping discussion | [10 empty] | N |  | 15 | Item | employeecenter/SAM/Lists/SAM
Define Project Concept (scoping or pre-concept) | 01300 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | PAR Checkpoint 1b - Decide if PAR process will continue, Consultant Kick-Off Meeting, PAR Checkpoint 2c - Submit range of alternatives | Initial Concept Meeting, Request Public Information Open House (PIOH), Receive Environmental Study Area Layout / Start Environmental Studies, Review Local/Consultant Draft Concept for Concept Meeting, Desktop Surveys (no review by OES), Local/Consultant Finalize Concept Report, Partial Environmental Surveys (OES does not anticipate receiving docs that can be accepted), PM Reviews Concept Report, PM Submit Concept Report, Receive Layout for UST/HW Phase I, Concept Meeting | 5.1 | Local and Consultant Design for Concept (Scoping Pre-Concept or Concept) | 120d | [15 empty] | N |  | 16 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Initial PAR Layout | 01712old | ROADWAY DESIGN | PAR;#10;#Roadway;#22 | Task Dependent | Conduct Ecology Survey (with steps), Data Acquisition for Concept (with steps), Define Project Concept, Initial Concept Meeting, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design), Receive Environmental Study Area Layout / Start Environmental Studies | Pre-Concept Meeting for PAR | 5.4 | PAR Activities (old -- for reference only) | 5d | HISTORICAL OLD PAR ACTIVITY Road Design comes up with practical alternatives report | When more than one project location should be considered. These activities are needed when it has been determined that an Individual Section 404 Permit is required. | When there are not multiple location alternatives for a project. These activities are not needed when an Individual Section 404 is NOT required. | when it is determined that multiple locations should be considered for a project.;Concept development is under way and environmental resources have been identified. | when initial PAR layout is complete. The PAR has been completed and submitted to appropriate resource agencies. |  | The PAR activities, 01713 - 02300, should be combined into one PAR activity 02000. These activities consist of developing alternatives to avoid or minimize impacts to jurisdictional waters of the US for projects that require an Individual Section 404 permit. |  |  |  | n/a |  |  |  |  | Y | Roadway Design Engineer | 17 | Item | employeecenter/SAM/Lists/SAM
PAR Checkpoint 2c - Submit range of alternatives | 01749 | ENVIRONMENTAL SERVICES | PAR;#10;#Roadway;#22 | Finish Milestone | PAR Checkpoint 2a - Evaluation for Alternatives carried forward, PAR Checkpoint 2b - Agency evaluation of alternatives carried forward | Data Acquisition for Scoping or Concept (with steps), PAR Checkpoint 3a - Prepare PAR Report, Data Acquisition for Concept (with steps), Define Project Concept,Define Project Concept (scoping or pre-concept) | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 0d | PAR Checkpoint 2c - Submit range of alternatives | Major widening and new location projects [unless outcome of 01719 is not to prceed to CP2] | All non-major widening and non-new location projects and those major widening and new location projects that do not advance past CP1 | GDOT letter submitted to LFA & USACE recapping discussion | LFA & USACE response | [10 empty] | N |  | 18 | Item | employeecenter/SAM/Lists/SAM
Project Summary | 00000 | PROGRAM DELIVERY | General;#26;#PM;#18 | WBS Summary |  |  | 2020_PLUTO_v20.2 | 2020_PLUTO_Template 3-25-20 | 2755d | This is a summary activity that represents the overall duration of the project. | This activity is included with all project schedules in P6. | N/A | The earliest start date for any activity within the schedule. | The latest finish date for any activity within the schedule. | No | It is a summary activity only and cannot be updated with actuals. | N/A | N/A |  | n/a | N/A |  |  |  | N | n/a | 19 | Item | employeecenter/SAM/Lists/SAM
PE Funding Authorization | 00100 | PROGRAMMING | General;#26 | Start Milestone | OPC Schedule Approved by the Chief Engineer, Project Justification (request and receive) | Develop Project Framework Agreement (PFA), Consultant Acquisition (request through notification), Data Acquisition for Scoping or Concept (with steps), Define Project Concept, Design-Build Approval by Chief Engineer, Develop Revised Concept Report, Notice to Proceed (NTP) for Consultant Contract, Interchange Modification Report (IMR), Prepare Design-Build RFP, Request and Receive Traffic Data Volumes, PAR Checkpoint 1a - Introduce Project to Agencies | 1.0.5 | Project Initialization | 0d | Preparing Georgia Department of Transportation Federal -AID S.T.I.P. WORK AUTHORIZATION/FEDERAL-AID PROJECT AGREEMENT documentation | It is needed by all projects | It is needed by all projects. | When the Office of Financial Management receives the 1625 from the project PM | When the Office of Financial Management completes the PE Funding Authorization document. |  | *Process generally takes from 1 day to 3 months to complete. The time can be extended if FHWA has a question on STIP, TIP, funding, etc.; *If a project is state funded, it has authorized PE funding when the 1625 system documentation is official * If a project is PODI (has full FHWA oversight), it will skip Engineering Services review. *Documents listing steps for authorizations are available in ProjectWise in the SAM Programming folder. OFM sends PE Funding Authorizations in bulk to Kim Nesbitt in OPD. | [8 empty] | N |  | 20 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL OLD PAR ACTIVITY Project Justification (request and receive) | 00500 | PROGRAM DELIVERY | PAR;#10;#PM;#18 | Task Dependent | PM Request Initial Schedule | Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Define Project Concept, Initial Concept Meeting, Interchange Modification Report (IMR), PE Funding Authorization, Request and Receive Traffic Data Volumes | 1 | Project Initialization | 10d | (NOT IN GENESIS TEMPLATE?) This activity represents when the project justification statement should be requested, prepared and received.): An Interstate Justification Report (IJR) is a report that provides supporting data for a new interchange along an interstate; Both the IJR and IMR conduct an operation and safety analysis to verify that the proposed change does not have a significant adverse impact on the safety and operation of the interstate facility or the local street network. | All projects managed out of OPD and IPD. An IJR can be initiated by GDOT or the local government when a need to modify the interchange is identified. A precursor to an IJR by a local government would be an Interstate Feasibility Report (IFR) to determine first if the new interchange is feasible. If the interchange is determined to be feasible, the local government can move forward with developing the IJR. When GDOT proposes a new interchange, the Office of Planning assumes responsibility for preparing the IJR, incorporating concept and capacity/weave analysis prepared by the Division of Preconstruction.&nbsp; The Office of Planning reviews and comments on all IFRs, IMRs and IJRs. | Maintenance projects, Bridge Maintenance projects, funding only schedules. If there’s no justification or feasibility for the interchange. Both the IMR and IJR must meet FHWA’s Policy of Access to the Interstate System (May 22, 2017). | When the project manager requests the project justification statement. The review of an IMR and IJR starts when a local government submits the document to the GDOT Office of Planning. The request will included all documents and data used to conduct/justify the request. GDOT has 30 days to review the materials and proved comments back to the local government or submit the IMR/IJR to FHWA for review. If additional information is needed, the Office of Planning will send the document back to the local government for changes and revisions. The review period begins again when a revised document is resubmitted to GDOT Planning. There is no timeline on FHWA’s review and FHWA can request additional documentation and revisions. | When the project manager receives the project justification statement. The end date for GDOT is when FHWA either denies the request or makes a determination that the IMR/IJR meets safety, operational, and engineering acceptability for the proposed project. Based on FHWA’s policy, if a project is delayed, Proposals may be reevaluated if the project has not progressed to construction within 3 years of receiving an affirmative determination of engineering and operational acceptability (23 CFR 625.2(a); see also 23 CFR 771.129. | Yes. Concept Development. | Owner will be Planning, Bridge Office, or Traffic Operations. See PDP Chapter 5.3 Planning sends the Office of Roadway Design all IJR/IMRs to review/comment. If they have any comments or questions, they are sent back to the local government to address along with Planning’s comments ; The type of project (IFR,IJR, or IMR) submitted for review does not generally impact the Office of Planning’s 30 day review period. The length of time from 1st submission to approval/denial by FHWA depends on the response time from the local government after GDOT and/or FHWA conduct their review and if there are any questions or updates requested throughout the process. |  | Internal performance is graded by Planning meeting the 30 day response time and the level of additional information later requested by FHWA. |  | n/a |  |  |  | 1E+13 | Y | n/a | 21 | Item | employeecenter/SAM/Lists/SAM
Initial Concept Meeting | 00750 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Data Acquisition for Concept (with steps), Define Project Concept | Concept Meeting, Create & Submit Environmental Study Area Layout, Develop Alternatives, Pre-Concept Meeting for PAR, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Review Existing Power Facilities for ITS, Start Database Preparation | 5 | Concept Development | 1d | [10 empty] | n/a |  |  |  |  | N | n/a | 22 | Item | employeecenter/SAM/Lists/SAM
PAR Summary | 01700 | ENVIRONMENTAL SERVICES | PAR;#10 | WBS Summary |  |  | PAR | Practical Alternatives Report (PAR) -- Pilot Testing | 1315d | PAR Summary developing alternatives to avoid or minimize impacts to jurisdictional waters of the US for projects that require an Individual Section 404 permit. | These activities are needed when it has been determined that an Individual Section 404 Permit is required. | These activities are not needed when an Individual Section 404 is NOT required. | Concept development is under way. Environmental Resource identification may be underway & complete for major widenings. | USACE has provided concurrence that Department's preferred alternative meets the preliminary LEDPA. | [10 empty] | N |  | 23 | Item | employeecenter/SAM/Lists/SAM
Concept Meeting | 02600 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Define Project Concept, Pre-CTM Public Information Open House Held (for EIS), 2nd Concept Layout Revisions for PAR, Respond to PIOH Comments, Receive Environmental Resource Boundaries (consultant design) | Local/Consultant Finalize Concept Report, Start Database Preparation, PM Reviews Concept Report, Request Public Information Open House (PIOH), Finalize Concept Report, PM Submit Concept Report | 5 | Concept Activities for all projects | 1d | Concept Meeting | [9 empty] | n/a |  |  |  |  | N | n/a | 24 | Item | employeecenter/SAM/Lists/SAM
PM Reviews Concept Report | 02722 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Define Project Concept, Concept Meeting, Local/Consultant Finalize Concept Report, Submit Concept Report to PM | Concept Report Review and Comments, Respond to Concept Report Comments, PM Submit Concept Report, Management Concept Approval Complete | 5 | Concept Activities for all projects | 10d | PM Reviews Concept Report | [14 empty] | N |  | 25 | Item | employeecenter/SAM/Lists/SAM
Concept Report Review and Comments | 02900 | DESIGN POLICY & SUPPORT | Concept;#20 | Task Dependent | PM Reviews Concept Report, Receive Environmental Resource Boundaries (consultant design), PM Submit Concept Report, Receive Environmental Resource Boundaries (in-house design), , Respond to Concept Report Comments, PAR Checkpoint 3d - Submit least damaging alternative to design | Management Concept Approval Complete | 5 | Concept Development | 47d | Concept report review and comments. Concept report is routed to us and we review and coordinate reviews of the report with various office heads, district engineers, and SME’s. Coordinate with PM/project team to make corrections to the report, review any corrections made and route the report to senior management (Director of Engineering & Chief Engineer – and sometimes FHWA) for approval. If not approved, coordinate with project team to address issues and re-route the report for approval. Activity begins when the report is received by DP&S and ends when the hardcopy report is forwarded for approval. | – required for all projects requiring a concept report under the PDP | not required for projects not under the PDP, or when the PDP does not require a concept report | starts upon receipt of concept report for approval, or first business day after. Preceded by 02800 – PM submit concept report | End date is when concept report is routed to Director of Engineering and Chief Engineer (and sometimes FHWA) for approval |  | Obtaining approval of engineering reports requires a good deal of timely review and response by office heads, project team members, and coordination with participating reviewers. |  | reducing the scheduled time for concept approval results in a lower percentage of reports being approved on time. |  | n/a |  |  |  |  | N | n/a | 26 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY Site Meeting with Resource Agencies for PAR | 02100 | ENVIRONMENTAL SERVICES | PAR;#10 | Task Dependent | Practical Alternative Report Development (with steps) | PAR Revisions | 5.4 | PAR Activities (old -- for reference only) | 2d | This activity is when the Environmental Office determines a need and sets up a meeting with a resource agency. | This activity is needed when environmental needs to meet with resource agencies like the Core of Engineers . This should be a Environmental activity. | This activity is only needed when the environmental office determines the need to meet with a resource agency. | This activity is when the Environmental Office determines a need and sets up a meeting with a resource agency. | when resource agency meeting(s) are complete |  | This activity should be owned by the Enviornmental Office. |  |  |  | Roadway Design Engineer |  |  |  |  | Y |  | 27 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Resource Boundaries (consultant design) | 02439 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Finish Milestone | Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps) non-seasonal, Conduct History Survey (with steps), PAR Checkpoint 3d - Submit least damaging alternative to design | Concept Report Review and Comments, Initial PAR Layout, Management Concept Approval Complete, PM Submit Concept Report, Preliminary Plans Complete, Preliminary Roadway Plans (consultant design), Review Local/Consultant Draft Concept for Concept Meeting | 5.1 | Local and Consultant Design for Concept | 0d | Receive Environmental Resource Boundaries (consultant design) | [14 empty] | N |  | 28 | Item | employeecenter/SAM/Lists/SAM
PM Submit Concept Report | 02800 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Define Project Concept, Receive Environmental Resource Boundaries (in-house design), Submit Draft to PM for Concept Team Meeting, Receive Environmental Resource Boundaries (consultant design), PM Reviews Concept Report, Concept Meeting, Respond to Concept Report Comments | Concept Report Review and Comments | 5 | Concept Development | 0d | PM Submit Concept Report | [9 empty] | n/a |  |  |  |  | N | n/a | 29 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY 2nd Concept Layout Revisions for PAR | 02300 | ENVIRONMENTAL SERVICES | PAR;#10 | Task Dependent | Develop Revised Concept Report, PAR Revisions | Concept Meeting, Develop Concept Layout of Preferred Alternate (with steps), Review Local/Consultant Draft Concept for Concept Meeting | 5.4 | PAR Activities (old -- for reference only) | 5d | Road Design uses meeting to develop 2nd Concept layout revisions. | when revisions are neede to PAR | When no updates are needed to PAR | after PAR revisions are complete. | when 2nd Concept Layout Revisions for PAR layout are complete. |  | This activity doesn't happen often |  |  |  | Roadway Design Engineer |  |  |  |  | Y | Roadway Design Engineer | 30 | Item | employeecenter/SAM/Lists/SAM
Local/Consultant Finalize Concept Report | 02460 | ROADWAY DESIGN | Concept;#20 | Task Dependent | Define Project Concept, Concept Meeting | PM Reviews Concept Report | 5.1 | Local and Consultant Design for Concept | 20d | Local/Consultant Finalize Concept Report | [14 empty] | N |  | 31 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY PAR Revisions | 02200 | ENVIRONMENTAL SERVICES | PAR;#10 | Task Dependent | Site Meeting with Resource Agencies for PAR | 2nd Concept Layout Revisions for PAR | 5.4 | PAR Activities (old -- for reference only) | 60d | PAR revisions are made based on meeting comments. | when there are Site Meeting with Resource Agencies for PAR | when there are not Site Meetings with Resource Agencies for PAR | after Site Meeting with Resource Agencies for PAR | when PAR revisions are completed. |  | This activity doesn't happen often. |  |  |  | Roadway Design Engineer |  |  |  |  | Y | Roadway Design Engineer | 32 | Item | employeecenter/SAM/Lists/SAM
Management Concept Approval Complete | 03000 | DESIGN POLICY & SUPPORT | Concept;#20 | Finish Milestone | Define Project Concept, Pre-CTM Public Information Open House Held (for EIS), 2nd Concept Layout Revisions for PAR, Respond to PIOH Comments, Receive Environmental Resource Boundaries (consultant design) | Request Public Information Open House (PIOH), Preliminary Roadway Plans (consultant design), Conduct Agency Consultation for Ecology (with steps), Start Database Preparation, Conduct Noise Analysis (with steps), Start Preliminary Roadway Plans, Concept Approval to PFPR Inspection, Conduct Air Quality Analysis (with steps), Conduct Section 106 Consultation – History (with steps), PM Submit L & D Report | 5 | Concept Activities for all projects | 0d | Management concept approval complete – this is the milestone date when the report is approved by the Chief Engineer. Approved document is placed on ProjectWise & ArchiveStore for access, and approval announcement sent by email according to the | – required for all projects requiring a concept report under the PDP | not required for projects not under the PDP, or when the PDP does not require a concept report | Date concept approved by chief; preceded by activity 02900 | Date concept approved by chief |  | While the complexity and size of the project can affect approval time, the primary factors are the quality of the report and the response times of the project team to making corrections to the report. Innovative project designs can also cause longer review times. PoDI projects where FHWA wishes to review and approve the concept reports will also require additional time.Typically, most of the issues related to project complexity should be addressed prior to the concept submission. | [7 empty] | Activity 03000 is one of the Department’s metrics reported to the public quarterly. My e-performance document includes both the metric and the average time for reports to be approved, as well as the quantity of reports managed by my team. | N |  | 33 | Item | employeecenter/SAM/Lists/SAM
Local/Consultant Finalize Concept Report | 03460 | ROADWAY DESIGN | Concept;#20 | Task Dependent | Concept Meeting, Define Project Concept (scoping or pre-concept) | PM Reviews Concept Report | 5.1 | Local and Consultant Design for Concept (Scoping Pre-Concept or Concept) | 20d | Local/Consultant Finalize Concept Report | [14 empty] | N |  | 34 | Item | employeecenter/SAM/Lists/SAM
Revised Concept Summary | 04000 | ROADWAY DESIGN | Concept;#20 | WBS Summary |  |  | 2.1 | Revised Concept (only needed if intended to be critical path) | 77d | Revised Concept Summary | [9 empty] | n/a |  |  |  |  | N | n/a | 35 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Draft Concept for Concept Meeting | 02450 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | 2nd Concept Layout Revisions for PAR, Define Project Concept, Pre-CTM Public Information Open House Held (for EIS), Receive Environmental Resource Boundaries (consultant design), Respond to PIOH Comments | Concept Meeting, Start Database Preparation | 5.1 | Local and Consultant Design for Concept | 5d | Review Local/Consultant Draft Concept for Concept Meeting | [9 empty] | n/a |  |  |  |  | N | n/a | 36 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Draft Concept for Concept Meeting | 03450 | ROADWAY DESIGN | Concept;#20 | Task Dependent | Define Project Concept (scoping or pre-concept), Receive Environmental Resource Boundaries (consultant design) for scoping phase | Concept Meeting | 5.1 | Local and Consultant Design for Concept (Scoping Pre-Concept or Concept) | 5d | Review Local/Consultant Draft Concept for Concept Meeting | [14 empty] | N |  | 37 | Item | employeecenter/SAM/Lists/SAM
PM Request VE Study | 07950 | PROGRAM DELIVERY | VE;#46;#PM;#18 | Start Milestone | Data Acquisition for Concept (with steps), Define Project Concept | VE Study Request (OES) | 6 | VE Study (if needed) | 0d | PM Request VE (Value Engineering) Study | [14 empty] | N |  | 38 | Item | employeecenter/SAM/Lists/SAM
Revised Concept Report Review and Comments (with steps) | 04300 | DESIGN POLICY & SUPPORT | Concept;#20 | Task Dependent | PM Submit Revised Concept Report | Management Revised Concept Approval Complete | 2.1 | Revised ConceptRevised Concept (only needed if intended to be critical path) | 47d | Revised concept review and comments – this activity is almost identical to activity 02900 above. | required whenever a revised concept report is required by the PDP | not required whenever a concept report is not required by the PDP, or when no changes requiring a revised concept report occur during design phase | starts upon receipt of revised concept report for approval, or first business day after. Preceded by activity 04200 – PM submit revised concept report | End date is when revised concept report is routed to Director of Engineering and Chief Engineer (and sometimes FHWA) for approval |  |  |  |  | 6 | n/a |  |  |  |  | N | n/a | 39 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Resource Boundaries (consultant design) for scoping phase | 03439 | ROADWAY DESIGN | Concept;#20 | Finish Milestone | Partial Environmental Surveys (OES does not anticipate receiving docs that can be accepted), Environmental Resource Identification Complete, Desktop Surveys (no review by OES), Conduct Ecology Survey (with steps) non-seasonal, PAR Checkpoint 3d - Submit least damaging alternative to design, Conduct History Survey (with steps), Conduct Archeology Survey (with steps) | PM Submit Concept Report, Management Concept Approval Complete, Concept Report Review and Comments, Review Local/Consultant Draft Concept for Concept Meeting | 5.1 | Local and Consultant Design for Concept (Scoping Pre-Concept or Concept) | 0d | Receive Environmental Resource Boundaries (consultant design) for scoping phase | [14 empty] | N |  | 40 | Item | employeecenter/SAM/Lists/SAM
PM Submit Revised Concept Report | 04200 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Develop Revised Concept Report | Revised Concept Report Review and Comments (with steps) | 2.1 | Revised Concept (only needed if intended to be critical path) | 0d | PM Submit Revised Concept Report | [9 empty] | n/a |  |  |  |  | N | n/a | 41 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY Develop Revised Concept Report | 02100old | ROADWAY DESIGN | PAR;#10 | Task Dependent | Consultant Kick-Off Meeting, Notice to Proceed (NTP) for Consultant Contract, Notice to Proceed (NTP) for Consultant Contract, PE Funding Authorization | 2nd Concept Layout Revisions for PAR, PM Submit Revised Concept Report, Receive Layout for UST/HW Phase I | 2.1 | Revised Concept (only needed if intended to be critical path) | 30d | Develop Revised Concept Report- 04100 This activity consists of revising the approved concept report. | This activity is needed for any project that requires a revised concept report. | This activity is not needed when a project does not require a revised concept report. | The start date means that the concept report has been approved and a scope change has occurred that requires a revised concept report. | The report has been submitted to PM for submission to Design Policy and Support. The PAR has been completed and submitted to appropriate resource agencies. | [5 empty] | Roadway Design Engineer |  |  |  |  | Y | Roadway Design Engineer | 42 | Item | employeecenter/SAM/Lists/SAM
Management Revised Concept Approval Complete | 04400 | DESIGN POLICY & SUPPORT | Concept;#20 | Finish Milestone | Revised Concept Report Review and Comments (with steps) | Environmental Approval Complete | 2.1 | Revised Concept (only needed if intended to be critical path) | 0d | Management revised concept approval complete – this activity is similar to 03000 and is simply the date the Chief Engineer approves the concept report. | required whenever a revised concept report is required by the PDP | not required whenever a concept report is not required by the PDP, or when no changes requiring a revised concept report occur during design phase | – Date revised concept approved by chief; preceded by activity 04300 | Date revised concept approved by chief | [10 empty] | N |  | 43 | Item | employeecenter/SAM/Lists/SAM
VE Study Request (OES) | 08100 | ENGINEERING SERVICES | VE;#46 | Task Dependent | PM Request VE Study | VE Study Preparation | 6 | VE Study (if needed) | 5d | VE Study begins when Engineering Services receives a complete VE study request package. VE study is assigned to the appropriate consultant through a contract based on North and South sections of the state. | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date VE Study request received from PM | Date VE Study scheduled |  | The PM must email the Value Engineer Specialist/Coordinator a VE Study request with a list of all potential consultants involved with the project and a description of the project and major structures. The PM must request a 1625 when the cost of the study is determined. The PM must inform their Design Team and provide the requested information to all team members two weeks prior to the week of the VE Study. |  |  |  | n/a |  |  |  |  | N | n/a | 44 | Item | employeecenter/SAM/Lists/SAM
VE Study Summary | 08000 | ENGINEERING SERVICES | VE;#46 | WBS Summary |  |  | 6 | VE Study (if needed) | 134d | Beginning to end of the Value Engineering Study process | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | This date is automatically filled from start date of 08100 | This date is automatically filled from end date of 08600 |  | The Value Engineering Study is a value driven systematic problem solving process mandated by state and federal law (MAP - 21) for all projects that cost more than $50 million dollars. | Link to PDP - Value Engineering Study, Policy 2450-1 Value Engineering, VE Study powerpoint presentation |  |  | n/a |  |  |  | 9 | N | n/a | 45 | Item | employeecenter/SAM/Lists/SAM
VE Study Preparation | 08200 | ENGINEERING SERVICES | VE;#46 | Task Dependent | VE Study Request (OES) | VE Study | 6 | VE Study (if needed) | 60d | The Value Engineer Specialist/Coordinator manages the the task order process and consultant coordination | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date VE Study scheduled | Day before VE Study is held |  | Procurement process takes about 30 days and then the Value Engineer Specialist/Coordinator assigns the project to a consultant. The consultant team begins the evaluation of the project.Teams of Consultant subject matter experts including Certified Value Specialists, Construction SMEs, Road Design SMEs, etc., work on the VE Study. |  |  |  | n/a |  |  |  |  | N | n/a | 46 | Item | employeecenter/SAM/Lists/SAM
VE Report Preparation | 08400 | ENGINEERING SERVICES | VE;#46 | Task Dependent | VE Study | VE Report Presentation to Implementation Team | 6 | VE Study (if needed) | 10d | gives consultants 2 weeks to do coordination and final VE Study report | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date VE Study ends | Date VE Report is distributed |  | Final VE Study report is posted on GeoPi and Project Wise. PM is notified that the Implementation Phase has begun and that any responses are due within 30 days. |  |  |  | n/a |  |  |  |  | N | n/a | 47 | Item | employeecenter/SAM/Lists/SAM
VE Report Presentation to Implementation Team | 08500 | ENGINEERING SERVICES | VE;#46;#PM;#18 | Task Dependent | VE Report Preparation | Implementation Team Recommendations Approval | 6 | VE Study (if needed) | 30d | PM has 30 days to respond to report and conclude any back and forth with consutants; Task order process including getting signtures, sometimes take more than 30 days | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date VE Report is distributed | Date Implementation Team meets to discuss recommendations |  | The Office of Engineering Services manages the process of getting the VE Study done, but has little control over most of the timeframe for completion including procurement and getting signatures. |  | OES name change recommendation since there is no implementation team 08500 VE Report distribution |  | n/a |  |  |  |  | N | n/a | 48 | Item | employeecenter/SAM/Lists/SAM
Implementation Team Recommendations Approval | 08600 | ENGINEERING SERVICES | VE;#46 | Task Dependent | VE Report Presentation to Implementation Team | Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | 6 | VE Study (if needed) | 25d | Upper management signature, questions, answers, and approval of selected alternative. | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date Implementation letter sent out for signatures | Date Approved implementation letter is distributed |  |  |  | OES name change recommendation since there is no implementation team 08600 Implementation Letter Approval |  | n/a |  |  |  |  | N | n/a | 49 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09025 | PROGRAM DELIVERY | PIOH;#28;#PM;#18 | Start Milestone | Initial Concept Meeting, Concept Meeting, Develop Concept Layout of Preferred Alternate (with steps), Environmental Resource Identification Complete, Management Concept Approval Complete | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.4 | PIOH | 0d | Request Public Information Open House (PIOH) | [14 empty] | N |  | 50 | Item | employeecenter/SAM/Lists/SAM
VE Study | 08300 | ENGINEERING SERVICES | VE;#46 | Task Dependent | VE Study Preparation | VE Report Preparation | 6 | VE Study (if needed) | 4d | VE Study workshop scheduled Monday through Thursday where consultants present a summary of their recommendations to the PM and the Design Team on the 4th day of the VE Study. | for all projects $50M(state, fed or local) except Design Build and P3 projects | for Design Build and P3 projects | Date VE Study begins | Date VE Study ends - may be the same day |  | VE Study Workshop typically lasts 3 1/2 days. On the first day, GDOT and FHWA team members provide input during the initial project overview meeting, Project Overview, Review Commitments, Constraints & Sacred Items, and review of alternates previously eliminated are presented and the Function of the project is explored. During the next 2-3 days the Investigative, Speculative, Evaluation, Development, and Presentation phases of the VE study are completed (see VE Study PowerPoint ). On the last day, the consultants present a summary of the recommendations of VE Study to the PM and Design Team. |  |  |  | n/a |  |  |  |  | N | n/a | 51 | Item | employeecenter/SAM/Lists/SAM
PIOH Summary | 09000 | ENVIRONMENTAL SERVICES | PIOH;#28;#Environmental;#5 | WBS Summary |  |  | 16.4 | PIOH | 130d | PIOH Summary | [9 empty] | n/a |  |  |  |  | N | n/a | 52 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE PM Request Visual Engineering | 09127 | PROGRAM DELIVERY | PM;#18 | Start Milestone | Database Complete, Develop Preliminary Cross Sections, Preliminary Roadway Plans (consultant design) | Receive Request for Visual Engineering | 2.5.1 | Visual Engineering | 0d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE | [14 empty] | Y |  | 53 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09050 | DISTRICT OFFICE | PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.4 | PIOH | 5d | [10 empty] | n/a |  |  |  |  | N | n/a | 54 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Receive Request for Visual Engineering (Concept Phase) | 09132 | DESIGN POLICY & SUPPORT | Concept;#20 | Task Dependent | PM Request Visual Engineering | Produce Preliminary Visual Engineering Deliverable | 2.5.1 | Visual Engineering | 5d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Receive Request for Vis. Eng. (5d)Receive request for Vis. Eng. Deliverables, schedule a meeting to determine Vis. Eng. needs and receive files(dgn files from Roadway Design, Inroads file, and traffic files) necessary to proceed. It is important to submit a VERG request with the appropriate files as early in the process as possible so that the work can be completed before it is needed. | When visual aids can help communicate aspects of a project to the public, stakeholders or property owners. PM typically requests VERG deliverables by email to <a href="mailto:VERG@dot.ga.gov">VERG@dot.ga.gov</a>, but requests also come from Commissioner, Communications Office, ROW, Environmental, and Road Design. Requests usually come around the PTIP meeting. VERG group attends PTIP meeting to get input from SMEs for the project. They also attend some PIOH, PHOH, and some ROW property owners meetings. | When a project does not produce a significant change to the existing condition. VERG is not usually done on signal only projects, lighting projects, bike trails, multiuse trails, or widening projects without significant impacts to ROW. | Receive request for Vis. Eng. deliverable(s) | End - Receive necessary files for Vis. Eng. deliverables |  | The type and level of complexity of the project can affect the time required to produce deliverables as well as the nature of the request. Project requests can be filled in one day to up to 7 months. Keep in mind that VERG activities can be done anytime but if the request comes too late, there may not be time enough to complete them. Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 55 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09032 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Public Information Open House Held | 16.4 | PIOH | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held Public Involvement (100 days Total)*NEPA P6 Team Member Activity | if PIOH is needed | Only if public involvement is not needed on the project (no significant controversy, no change in access, etc.) | the PIOH process has begun | the Dry Run has been held |  | a. PMs want to know when activities will be complete and when they can go to the next step. PMs usually want to know if we are done with tech studies and/or resource ID. Can some of the milestone activities be auto-populated (Ex: resource ID complete could auto-populate based on when SMEs enter completion dates for their Resource ID activities).How can we use Scheduled dates/projected dates to effectively determine whether a project is actually behind schedule. 09032 (Env Prep for PIOH)- User not clear on what this activity includes. Is this activity designed to capture request for PIOH and approval to go the PIOH? Or the actual work being done to produce the materials needed for PIOH? |  | Agency coordination on state-aid projects is not reflected in the timeline for completion of state aid projects. The review times are not accounted for as they are with Federal aid projects. Logical termini issues (due to region) can impact preparation of Env doc, and FHWA approval of document /Env Approval complete. Where logical termini should be captured in the schedule is not apparent. Delayed NTP can impact the duration of project activities. Project (Design/ROW) changes can impact the duration of activities. Should be accommodated in the project schedule. ROW acquisition can impact the duration of certification of Let (schedule shifts due to ROW acquisitions impact BL Let certification).Phase 1, UST= If not done on time can impact the duration of activities related to document production. UST ph.1 needs an activity so we can track whether we will be on schedule to complete the document on time. | 3 | NEPA Analyst |  |  |  | a. Team leaders look at BL dates when trying to figure out consultant deliverables. A lot of the time BL schedules are way off so they aren’t reliable for tracking performance, etc a. Should be evaluated by management dates instead of BL dates. Especially when the schedules are shifted out and BL dates are not shifted and we are expected to recover the date that hasn’t been shifted. General culture shift.b. Can fold P6 schedules into consultant evaluations to determine if they meet schedule.c. There are certain offices working on totally different schedules than our office. (BL vs. management). Schedules should be evaluated on Management dates. Also, when schedules are recovering from day 1 due to late ntp, or other issues, they tend to lack credibility.3. How are your activities being evaluated outside your office (if applicable)?PM’s use activities to determine status of project schedule;Management evaluates for status meetings to determine risks 4. How are your activities being evaluated within your office (if applicable)?Managers don’t evaluate the activities;managers use activities to determine how project is tracking for next milestone;to identify challenges and any need for escalation;used for internal project status meetings5. How do you think these activities should be evaluated? took onP6 should be equally prioritized across sections so that NEPA isn’t spending substantial time reviewing schedules.Activities should be evaluated based on the planned duration and actual duration instead of BL start and finish dates. | N | NEPA Analyst | 56 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09100 | DISTRICT OFFICE | PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Public Information Open House Held | 16.4 | PIOH | 60d | [9 empty] | 3 | n/a |  |  |  |  | N | n/a | 57 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Visual Engineering Deliverable (Concept Phase) | 09159 | DESIGN POLICY & SUPPORT | Concept;#20 | Finish Milestone | Review Preliminary Visual Engineering Deliverable | Public Hearing Held, Public Information Open House Held | 2.5.1 | Visual Engineering | 0d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Vis. Eng. Deliv. (0d)Deliverables are submitted to requestor. OPD does a QA meeting with SMEs on the deliverables before they are accepted. | 3) The project includes an alternative intersection (Roundabout, Diverging Diamond, CFI, R-Cut, DDI) Sometimes more than one deliverable is prepared, for example, they may do an illustration of the Concept Design and then later do one for Final Design. |  | Submit Vis. Eng. Deliv. | – Submit Vis. Eng. Deliv. In |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | The current method works. | Y |  | 58 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Produce Preliminary Visual Engineering Deliverable (Concept Phase) | 09142 | DESIGN POLICY & SUPPORT | Concept;#20 | Task Dependent | Receive Request for Visual Engineering | Review Preliminary Visual Engineering Deliverable | 2.5.1 | Visual Engineering | 30d | Produce Vis. Eng. Deliverable (30d)VERG team prepares deliverables (Deliverables are usually provided in jpeg or MP4 video format; they are 2D, 3D, or video representations done using Bentley software products including Microstation, Adobe, and Vissim. The Visual Eng. staff either takes photos of the project location or gets imagery from Web Mapping Services. They are exploring using drones to get images.) | Examples include when a project: 1) Produces a significant change to the existing condition (ie going from an at grade to grade separated intersection), major interchanges, bike lanes, staging, detours, alternates |  | VERG begins work on deliverable(s) | VERG completes work on deliverable(s) |  | The duration for the 9142, 9242 and 9342 can require up to 8 weeks but 4 weeks is suitable for most projects. The goal is to have VERG ready for the dry run meeting before the Concept meeting so that any issues can be worked out and deliverables can be complete for PIOH and PHOH meetings. Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 59 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Review Preliminary Visual Engineering Deliverable (Concept Phase) | 09152 | DESIGN POLICY & SUPPORT | Concept;#20 | Task Dependent | Produce Preliminary Visual Engineering Deliverable | Submit Visual Engineering Deliverable | 2.5.1 | Visual Engineering | 5d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Review Prelim. Vis. Eng. Deliv. (5d)Meet (typically the dry run for PIOH requests) to review preliminary deliverables, VERG incorporates changes (if any) | 2) Has a significant impact on ROW (contentious property owners, HOAs, environmental groups, Tribal Councils, …) or |  | Meet (typically the dry run for PIOH requests) | VERG completes final deliverable(s) |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | By the requestor(s) during the review | Y |  | 60 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Receive Request for Visual Engineering (Prelim Phase) | 09232 | DESIGN POLICY & SUPPORT | Preliminary Plans;#40 | Task Dependent | PM Request Visual Engineering | Produce Preliminary Visual Engineering Deliverable | 2.5.2 | Visual Engineering (2nd) | 5d | Receive Request for Vis. Eng. (5d)Receive request for Vis. Eng. Deliverables, schedule a meeting to determine Vis. Eng. needs and receive files(dgn files from Roadway Design, Inroads file, and traffic files) necessary to proceed. It is important to submit a VERG request with the appropriate files as early in the process as possible so that the work can be completed before it is needed. | When visual aids can help communicate aspects of a project to the public, stakeholders or property owners. PM typically requests VERG deliverables by email to <a href="mailto:VERG@dot.ga.gov">VERG@dot.ga.gov</a>, but requests also come from Commissioner, Communications Office, ROW, Environmental, and Road Design. Requests usually come around the PTIP meeting. VERG group attends PTIP meeting to get input from SMEs for the project. They also attend some PIOH, PHOH, and some ROW property owners meetings. | When a project does not produce a significant change to the existing condition. VERG is not usually done on signal only projects, lighting projects, bike trails, multiuse trails, or widening projects without significant impacts to ROW. | Receive request for Vis. Eng. deliverable(s) | End - Receive necessary files for Vis. Eng. deliverables |  | The type and level of complexity of the project can affect the time required to produce deliverables as well as the nature of the request. Project requests can be filled in one day to up to 7 months. Keep in mind that VERG activities can be done anytime but if the request comes too late, there may not be time enough to complete them. Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 61 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE PM Request Visual Engineering | 09227 | PROGRAM DELIVERY | PM;#18 | Start Milestone | Database Complete, Develop Preliminary Cross Sections, Preliminary Roadway Plans (consultant design) | Receive Request for Visual Engineering | 2.5.2 | Visual Engineering (2nd) | 0d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE; see 09127 | [14 empty] | Y |  | 62 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Produce Preliminary Visual Engineering Deliverable (Prelim Phase) | 09242 | DESIGN POLICY & SUPPORT | Preliminary Plans;#40 | Task Dependent | Receive Request for Visual Engineering | Review Preliminary Visual Engineering Deliverable | 2.5.2 | Visual Engineering (2nd) | 30d | Produce Vis. Eng. Deliverable (30d)VERG team prepares deliverables (Deliverables are usually provided in jpeg or MP4 video format; they are 2D, 3D, or video representations done using Bentley software products including Microstation, Adobe, and Vissim. The Visual Eng. staff either takes photos of the project location or gets imagery from Web Mapping Services. They are exploring using drones to get images.) | Examples include when a project: 1) Produces a significant change to the existing condition (ie going from an at grade to grade separated intersection), major interchanges, bike lanes, staging, detours, alternates |  | VERG begins work on deliverable(s) | VERG completes work on deliverable(s) |  | The duration for the 9142, 9242 and 9342 can require up to 8 weeks but 4 weeks is suitable for most projects. The goal is to have VERG ready for the dry run meeting before the Concept meeting so that any issues can be worked out and deliverables can be complete for PIOH and PHOH meetings. Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 63 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Review Preliminary Visual Engineering Deliverable (Prelim Phase) | 09252 | DESIGN POLICY & SUPPORT | Preliminary Plans;#40 | Task Dependent | Produce Preliminary Visual Engineering Deliverable | Submit Visual Engineering Deliverable | 2.5.2 | Visual Engineering (2nd) | 5d | Review Prelim. Vis. Eng. Deliv. (5d)Meet (typically the dry run for PIOH requests) to review preliminary deliverables, VERG incorporates changes (if any) | 2) Has a significant impact on ROW (contentious property owners, HOAs, environmental groups, Tribal Councils, …) or |  | Meet (typically the dry run for PIOH requests) | VERG completes final deliverable(s) |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | By the requestor(s) during the review | Y |  | 64 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Visual Engineering Deliverable (Prelim Phase) | 09259 | DESIGN POLICY & SUPPORT | Preliminary Plans;#40 | Finish Milestone | Review Preliminary Visual Engineering Deliverable | Public Hearing Held, Public Information Open House Held | 2.5.2 | Visual Engineering (2nd) | 0d | Submit Vis. Eng. Deliv. (0d)Deliverables are submitted to requestor. OPD does a QA meeting with SMEs on the deliverables before they are accepted. | 3) The project includes an alternative intersection (Roundabout, Diverging Diamond, CFI, R-Cut, DDI) Sometimes more than one deliverable is prepared, for example, they may do an illustration of the Concept Design and then later do one for Final Design. |  | Submit Vis. Eng. Deliv. | – Submit Vis. Eng. Deliv. In |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | The current method works. | Y |  | 65 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Public Information Open House Held | 09300 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Start Milestone |  | Develop, Approve & Publish Notice of Decision (NOD), Environmental Approval Complete, Respond to PIOH Comments | 16.4 | PIOH | 0d | Environmental Preparation for PIOH (with steps), 1. Public Information Open House Advertisement (with steps), 2. Prepare Handout, 3. Dry Run Held ; *Dry Run meeting consists of Project team (PM, designers, NEPA, district, OES, SMEs) that gets together to review the materials for public display, discuss project related issues, and prep for the PIOH meeting; they also schedule the Debrief Meeting for after the PIOH to go over comments | Public Involvement (70 days)*NEPA P6 Team Member Activity | Only if public involvement is not needed on the project (no significant controversy, no change in access, etc.) | once PIOH process has begun - PM sends email with PIOH worksheet in official OPD letter to Office Head of OES. District works with NEPA person to get PIOH meeting scheduled. | day when PIOH meeting concludes | [10 empty] | Y |  | 66 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Public Information Open House Held (70 days) | 09302 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 |  |  |  |  | PIOH | 0d | HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Public Information Open House Held (70 days) | (0 days) Milestone Activity *NEPA P6 Team Member Activity |  |  | day when PIOH meeting concludes | [10 empty] | Y |  | 67 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE PM Request Visual Engineering | 09327 | PROGRAM DELIVERY | PM;#18 | Start Milestone | Database Complete, Develop Preliminary Cross Sections, Preliminary Roadway Plans (consultant design) | Receive Request for Visual Engineering | 2.5.3 | Visual Engineering (3rd) | 0d | see 09127 | [14 empty] | Y |  | 68 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09312 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Public Information Open House Held | Environmental Approval Complete | 16.4 | PIOH | 30d | Respond to PIOH Comments- Comments are accepted up to 10 days after the meeting. For each project, there are usually 0 - 200 comments. A Debrief meeting is held with the project team (OES, OPD, ROW, district, ...) to discuss comments collected from the PIOH meeting and the NEPA team member makes a summary of the comments and the coordinated project team responses in a PIOH response letter. If a comment is received multiple times, the letter answers combines the related questions/comments into one response. OPD gets a 2 week review of the final PIOH response letter. | when comments are received from the PIOH meeting, each one is addressed by …Public Involvement (30 days Total)*NEPA P6 Team Member Activity This is a difficult deadline to meet; need 45 - 60 days. Following the collection of comments from the PIOH meeting, OES reviews the comments and writes up a PIOH comment response OPD takes about 2 weeks to review the PIOH comment response letter, then OES has to update the letter as needed and send it to the PM or Project Team. Delays in this activity could delay the CE especially for large projects or lead to supplemental procurement. | if there are no comments from the PIOH meeting (rarely happens) | day following PIOH | 1 1/2 months after PIOH meeting |  | Activity #09312 (20 days) is not enough time for the needed coordination and completion of the actual letter. |  | Summary activities are not needed- PMs often ask for updates to summary activities.& 09312 duration for respond to PIOH comments is usually not long enough. There should be an added activity to compile the information before the clock runs to actually produce the response letter (add steps or new activity with those steps). Environmental justice (extensive Public involvement), stakeholder meetings on a project could slow down Public Involvement activities (09312), and subsequent Env document activities (14523/14533). |  | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 69 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Receive Request for Visual Engineering (Final Plan Phase) | 09332 | DESIGN POLICY & SUPPORT | General;#26;#PM;#18 | Task Dependent | PM Request Visual Engineering | Produce Preliminary Visual Engineering Deliverable | 2.5.3 | Visual Engineering (3rd) | 5d | Receive Request for Vis. Eng. (5d)Receive request for Vis. Eng. Deliverables, schedule a meeting to determine Vis. Eng. needs and receive files(dgn files from Roadway Design, Inroads file, and traffic files) necessary to proceed. It is important to submit a VERG request with the appropriate files as early in the process as possible so that the work can be completed before it is needed. | When visual aids can help communicate aspects of a project to the public, stakeholders or property owners. PM typically requests VERG deliverables by email to <a href="mailto:VERG@dot.ga.gov">VERG@dot.ga.gov</a>, but requests also come from Commissioner, Communications Office, ROW, Environmental, and Road Design. Requests usually come around the PTIP meeting. VERG group attends PTIP meeting to get input from SMEs for the project. They also attend some PIOH, PHOH, and some ROW property owners meetings. | When a project does not produce a significant change to the existing condition. VERG is not usually done on signal only projects, lighting projects, bike trails, multiuse trails, or widening projects without significant impacts to ROW. | Receive request for Vis. Eng. deliverable(s) | End - Receive necessary files for Vis. Eng. deliverables |  | The type and level of complexity of the project can affect the time required to produce deliverables as well as the nature of the request. Project requests can be filled in one day to up to 7 months. Keep in mind that VERG activities can be done anytime but if the request comes too late, there may not be time enough to complete them.Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 70 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Produce Preliminary Visual Engineering Deliverable (Final Plan Phase) | 09342 | DESIGN POLICY & SUPPORT | General;#26 | Task Dependent | Receive Request for Visual Engineering | Review Preliminary Visual Engineering Deliverable | 2.5.3 | Visual Engineering (3rd) | 30d | Produce Vis. Eng. Deliverable (30d)VERG team prepares deliverables (Deliverables are usually provided in jpeg or MP4 video format; they are 2D, 3D, or video representations done using Bentley software products including Microstation, Adobe, and Vissim. The Visual Eng. staff either takes photos of the project location or gets imagery from Web Mapping Services. They are exploring using drones to get images.) | Examples include when a project: 1) Produces a significant change to the existing condition (ie going from an at grade to grade separated intersection), major interchanges, bike lanes, staging, detours, alternates |  | VERG begins work on deliverable(s) | VERG completes work on deliverable(s) |  | The duration for the 9142, 9242 and 9342 can require up to 8 weeks but 4 weeks is suitable for most projects. The goal is to have VERG ready for the dry run meeting before the Concept meeting so that any issues can be worked out and deliverables can be complete for PIOH and PHOH meetings. Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | N/A | Y |  | 71 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Review Preliminary Visual Engineering Deliverable (Final Plan Phase) | 09352 | DESIGN POLICY & SUPPORT | General;#26 | Task Dependent | Produce Preliminary Visual Engineering Deliverable | Submit Visual Engineering Deliverable | 2.5.3 | Visual Engineering (3rd) | 5d | Review Prelim. Vis. Eng. Deliv. (5d)Meet (typically the dry run for PIOH requests) to review preliminary deliverables, VERG incorporates changes (if any) | 2) Has a significant impact on ROW (contentious property owners, HOAs, environmental groups, Tribal Councils, …) or |  | Meet (typically the dry run for PIOH requests) | VERG completes final deliverable(s) |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | By the requestor(s) during the review | Y |  | 72 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Visual Engineering Deliverable (Final Plan Phase) | 09359 | DESIGN POLICY & SUPPORT | General;#26 | Finish Milestone | Review Preliminary Visual Engineering Deliverable | Public Hearing Held, Public Information Open House Held | 2.5.3 | Visual Engineering (3rd) | 0d | Submit Vis. Eng. Deliv. (0d)Deliverables are submitted to requestor. OPD does a QA meeting with SMEs on the deliverables before they are accepted. | 3) The project includes an alternative intersection (Roundabout, Diverging Diamond, CFI, R-Cut, DDI) Sometimes more than one deliverable is prepared, for example, they may do an illustration of the Concept Design and then later do one for Final Design. |  | Submit Vis. Eng. Deliv. | – Submit Vis. Eng. Deliv. In |  | Contacts: Frank Flanders, Kristi Patterson, Tiffany Turner |  | N/A | [5 empty] | The current method works. | Y |  | 73 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Interchange Modification Report (IMR) | 09382 | PROGRAM DELIVERY | General;#26 | Task Dependent | Consultant Acquisition (request through notification), Develop Project Framework Agreement (PFA), Notice to Proceed (NTP) for Consultant Contract, PE Funding Authorization, Project Justification (request and receive) | Review Draft EA, Review and Approve Environmental Effects Report (EER), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Submit CE to FHWA, Submit Draft EIS to FHWA for Approval | 2.8 | IMR (for design-build projects only) | 160d | This activity represents when the Interchange Modification Report should be requested, prepared and received.) An Interstate Modification Report (IMR) is a report that justifies the need for a modified version of a current interchange along an interstate. Both the IJR and IMR conduct an operation and safety analysis to verify that the proposed change does not have a significant adverse impact on the safety and operation of the interstate facility or the local street network. | An IMR can be initiated by GDOT or the local government when a need to modify the interchange is identified. The GDOT Design Office manages/prepares the design of any new GDOT lead IMRs. The Office of Planning reviews and comments on all IFRs, IMRs and IJRs. | If there’s no justification or feasibility for the interchange. Both the IMR and IJR must meet FHWA’s Policy of Access to the Interstate System (May 22, 2017). | The review of an IMR and IJR starts when a local government submits the document to the GDOT Office of Planning. The request will included all documents and data used to conduct/justify the request. GDOT has 30 days to review the materials and proved comments back to the local government or submit the IMR/IJR to FHWA for review. If additional information is needed, the Office of Planning will send the document back to the local government for changes and revisions. The review period begins again when a revised document is resubmitted to GDOT Planning. There is no timeline on FHWA’s review and FHWA can request additional documentation and revisions. | The end date for GDOT is when FHWA either denies the request or makes a determination that the IMR/IJR meets safety, operational, and engineering acceptability for the proposed project. Based on FHWA’s policy, if a project is delayed, Proposals may be reevaluated if the project has not progressed to construction within 3 years of receiving an affirmative determination of engineering and operational acceptability (23 CFR 625.2(a); see also 23 CFR 771.129. |  | Owner will be Planning, Bridge Office, or Traffic Operations. See PDP Chapter 5.3 Planning sends the Office of Roadway Design all IJR/IMRs to review/comment. If they have any comments or questions, they are sent back to the local government to address along with Planning’s comments. The type of project (IFR,IJR, or IMR) submitted for review does not generally impact the Office of Planning’s 30 day review period. The length of time from 1st submission to approval/denial by FHWA depends on the response time from the local government after GDOT and/or FHWA conduct their review and if there are any questions or updates requested throughout the process. |  | Internal performance is graded by Planning meeting the 30 day response time and the level of additional information later requested by FHWA. | [6 empty] | Y |  | 74 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09405 | RIGHT OF WAY | PIOH;#28;#ROW;#21 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.4.16.2 | PIOH (2nd) | 5d | See 09050 | [9 empty] | n/a |  |  |  |  | N | n/a | 75 | Item | employeecenter/SAM/Lists/SAM
PIOH (2nd) Summary | 09400 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.4.16.2 | PIOH (2nd) | 130d | See 09000 | [9 empty] | n/a |  |  |  |  | N | n/a | 76 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09402 | ENVIRONMENTAL SERVICES | PIOH;#28;#Environmental;#5 | Start Milestone | Define Project Concept (scoping or pre-concept), Consultant Acquisition (request through notification), Data Acquisition for Scoping or Concept (with steps) | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.4.16.2 | PIOH (2nd) | 0d | See 09025 | [14 empty] | N |  | 77 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09403 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Public Information Open House Held (Scoping Pre-Concept or Concept) | 16.4.16.2 | PIOH (2nd) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 78 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09410 | DISTRICT OFFICE | PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Public Information Open House Held (Scoping Pre-Concept or Concept) | 16.4.16.2 | PIOH (2nd) | 60d | See 09100 | [8 empty] | 3 | n/a |  |  |  |  | N | n/a | 79 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Held (Scoping Pre-Concept or Concept) | 09430 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Respond to PIOH Comments | 16.4.16.2 | PIOH (2nd) | 0d | Public Information Open House Held |  |  | day of PIOH | day of PIOH when meeting concludes | [10 empty] | N |  | 80 | Item | employeecenter/SAM/Lists/SAM
PIOH (3rd) Summary | 09500 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.4.16.3 | PIOH (3rd) | 130d | See 09000 | [9 empty] | n/a |  |  |  |  | N | n/a | 81 | Item | employeecenter/SAM/Lists/SAM
Scoping PIOH (for EIS) Summary | 09600 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.10.4.1.1 | Scoping PIOH (for EIS) | 120d | [10 empty] | n/a |  |  |  |  | N | n/a | 82 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09432 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Public Information Open House Held (Scoping Pre-Concept or Concept) | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.4.16.2 | PIOH (2nd) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | 1 1/2 months after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 83 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09502 | PROGRAM DELIVERY | PIOH;#28;#PM;#18 | Start Milestone | Define Project Concept, Data Acquisition for Concept (with steps) | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.4.16.3 | PIOH (3rd) | 0d | See 09025 | [14 empty] | N |  | 84 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09532 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Public Information Open House Held (Concept Phase) | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.4.16.3 | PIOH (3rd) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | 1 1/2 months after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 85 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09510 | DISTRICT OFFICE | PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Public Information Open House Held (Concept Phase) | 16.4.16.3 | PIOH (3rd) | 60d | See 09100 | [8 empty] | 3 | n/a |  |  |  |  | N | n/a | 86 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09505 | RIGHT OF WAY | PIOH;#28;#ROW;#21 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.4.16.3 | PIOH (3rd) | 5d | See 09050 | [9 empty] | n/a |  |  |  |  | N | n/a | 87 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09602 | PROGRAM DELIVERY | Environmental;#5;#PIOH;#28;#EIS;#37 | Start Milestone | Prepare Scoping and Outreach Materials | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.10.4.1.1 | Scoping PIOH (for EIS) | 0d | [15 empty] | N |  | 88 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09503 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Held (Concept Phase), Public Information Open House Advertisement (with steps) | 16.4.16.3 | PIOH (3rd) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 89 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Held (Concept Phase) | 09530 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Respond to PIOH Comments | 16.4.16.3 | PIOH (3rd) | 0d | Public Information Open House Held |  |  | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 90 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09606 | DISTRICT OFFICE | EIS;#37;#PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Scoping Public Information Open House Held (for EIS) | 16.10.4.1.1 | Scoping PIOH (for EIS) | 60d | [9 empty] | 3 | n/a |  |  |  |  | N | n/a | 91 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09603 | ENVIRONMENTAL SERVICES | Environmental;#5;#PIOH;#28;#EIS;#37 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Scoping Public Information Open House Held (for EIS) | 16.10.4.1.1 | Scoping PIOH (for EIS) | 70d | Scoping Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 92 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09605 | RIGHT OF WAY | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.10.4.1.1 | Scoping PIOH (for EIS) | 5d | [10 empty] | n/a |  |  |  |  | N | n/a | 93 | Item | employeecenter/SAM/Lists/SAM
Screen 1 PIOH (for EIS) Summary | 09610 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 120d | [10 empty] | n/a |  |  |  |  | N | n/a | 94 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09608 | ENVIRONMENTAL SERVICES | Environmental;#5;#EIS;#37;#PIOH;#28 | Task Dependent | Scoping Public Information Open House Held (for EIS) | Finalize Scoping and Outreach Materials | 16.10.4.1.1 | Scoping PIOH (for EIS) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | One month after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 95 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09613 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Screen 1 Public Information Open House Held (for EIS) | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 96 | Item | employeecenter/SAM/Lists/SAM
Scoping Public Information Open House Held (for EIS) | 09607 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Finalize Scoping and Outreach Materials, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Respond to PIOH Comments | 16.10.4.1.1 | Scoping PIOH (for EIS) | 0d | Scoping Public Information Open House Held (for EIS |  |  | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 97 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09612 | PROGRAM DELIVERY | PIOH;#28;#PM;#18;#EIS;#37 | Start Milestone | FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), Prepare Screen 1 Analysis/Report | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 0d | [15 empty] | N |  | 98 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09615 | RIGHT OF WAY | EIS;#37;#PIOH;#28;#ROW;#21 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 5d | [10 empty] | n/a |  |  |  |  | N | n/a | 99 | Item | employeecenter/SAM/Lists/SAM
Screen 1 Public Information Open House Held (for EIS) | 09617 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Finalize Screen 1 Report, Prepare Screen 2 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Respond to PIOH Comments | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 0d | Screen 1 Public Information Open House Held (for EIS | Kay: This activity is needed for EIS projects that have a preliminary screening needed for the project's PIOH | when the screening has been shown to indicate that an a PIOH isn't needed.. | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 100 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09618 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Screen 1 Public Information Open House Held (for EIS) | Finalize Screen 1 Report, Prepare Screen 2 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | One month after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 101 | Item | employeecenter/SAM/Lists/SAM
Screen 2 PIOH (for EIS) Summary | 09620 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 102 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09616 | DISTRICT OFFICE | EIS;#37;#PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Screen 1 Public Information Open House Held (for EIS) | 16.10.4.2.1.1 | Screen 1 PIOH (for EIS) | 60d | [9 empty] | 3 | n/a |  |  |  |  | N | n/a | 103 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09622 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Start Milestone | FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), Prepare Screen 2 Analysis/Report | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 0d | [15 empty] | N |  | 104 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09623 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Screen 2 Public Information Open House Held (for EIS) | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held | This activity is needed as the preparation that comes before a formal PIOH needed. |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 105 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09625 | RIGHT OF WAY | EIS;#37;#PIOH;#28;#ROW;#21 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 5d | [10 empty] | n/a |  |  |  |  | N |  | 106 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09626 | DISTRICT OFFICE | EIS;#37;#PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Screen 2 Public Information Open House Held (for EIS) | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 60d | [9 empty] | 3 | n/a |  |  |  |  | N |  | 107 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09628 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Screen 2 Public Information Open House Held (for EIS) | Finalize Screen 2 Report, Prepare Screen 3 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | One month after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 108 | Item | employeecenter/SAM/Lists/SAM
Screen 2 Public Information Open House Held (for EIS) | 09627 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Finalize Screen 2 Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Respond to PIOH Comments | 16.10.4.2.2.1 | Screen 2 PIOH (for EIS) | 0d | Screen 2 Public Information Open House Held (for EIS |  |  | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 109 | Item | employeecenter/SAM/Lists/SAM
Screen 3 PIOH (for EIS) Summary | 09630 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 110 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09632 | PROGRAM DELIVERY | EIS;#37;#PIOH;#28;#PM;#18 | Start Milestone | FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps), Prepare Screen 3 Analysis/Report | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 0d | [15 empty] | N |  | 111 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09635 | RIGHT OF WAY | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 5d | [10 empty] | n/a |  |  |  |  | N |  | 112 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09633 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps), Screen 3 Public Information Open House Held (for EIS) | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 113 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09636 | DISTRICT OFFICE | EIS;#37;#PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Screen 3 Public Information Open House Held (for EIS) | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 60d | [9 empty] | 3 | n/a |  |  |  |  | N |  | 114 | Item | employeecenter/SAM/Lists/SAM
Screen 3 Public Information Open House Held (for EIS) | 09637 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Finalize Screen 3 Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Respond to PIOH Comments | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 0d | Screen 3 Public Information Open House Held (for EIS |  |  | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 115 | Item | employeecenter/SAM/Lists/SAM
Pre-CTM PIOH (for EIS) Summary | 09640 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | WBS Summary |  |  | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 116 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09638 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Screen 3 Public Information Open House Held (for EIS) | Finalize Screen 3 Report, Receive Environmental Study Area Layout / Start Environmental Studies | 16.10.4.2.3.1 | Screen 3 PIOH (for EIS) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | One month after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 117 | Item | employeecenter/SAM/Lists/SAM
Request Public Information Open House (PIOH) | 09642 | PROGRAM DELIVERY | EIS;#37;#PIOH;#28;#PM;#18 | Start Milestone | Data Acquisition for Concept (with steps), Define Project Concept, Finalize Scoping and Outreach Materials, Finalize Screen 1 Report, Finalize Screen 2 Report, Finalize Screen 3 Report, Initial Concept Meeting, Scoping Public Information Open House Held (for EIS), Screen 1 Public Information Open House Held (for EIS), Screen 2 Public Information Open House Held (for EIS), Screen 3 Public Information Open House Held (for EIS) | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Public Information Open House Advertisement (with steps) | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 0d | [15 empty] | N |  | 118 | Item | employeecenter/SAM/Lists/SAM
Environmental Preparation for PIOH (with steps) | 09643 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Request Public Information Open House (PIOH) | Pre-CTM Public Information Open House Held (for EIS), Public Information Open House Advertisement (with steps) | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 70d | Environmental Preparation for PIOH (with steps)Applicable Tasks (3 Steps)-Prepare Advertisement-Prepare Handout-Dry Run Held |  |  | the PIOH process has begun | the Dry Run has been held |  | don’t use |  |  | 3 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 119 | Item | employeecenter/SAM/Lists/SAM
Property Research for PIOH | 09645 | RIGHT OF WAY | EIS;#37;#PIOH;#28;#ROW;#21 | Task Dependent | Request Public Information Open House (PIOH) | Public Information Open House Advertisement (with steps) | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 5d | [10 empty] | n/a |  |  |  |  | N |  | 120 | Item | employeecenter/SAM/Lists/SAM
Environmental Resource Identification Summary | 10411 | ENVIRONMENTAL SERVICES | Environmental;#5 | WBS Summary |  |  | 16.7 | Environmental Resource Identification | 245d | [10 empty] | n/a |  |  |  |  | N | n/a | 121 | Item | employeecenter/SAM/Lists/SAM
Respond to PIOH Comments | 09648 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#PIOH;#28 | Task Dependent | Pre-CTM Public Information Open House Held (for EIS) | Concept Meeting, Review Local/Consultant Draft Concept for Concept Meeting, Submit Draft to PM for Concept Team Meeting | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 20d | Respond to PIOH Comments | when comments are received from the PIOH meeting, each one is addressed by … | if there are no comments from the PIOH meeting | day following PIOH | One month after PIOH meeting | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 122 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Study Area Layout / Start Environmental Studies | 10412 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Define Project Concept(scoping or pre-concept), Initial Concept Meeting | Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps), Conduct Ecology Survey for Seasonal Species, Conduct History Survey (with steps), Environmental Resource Identification Complete, Receive Environmental Resource Boundaries (in-house design), Receive Local/Consultant or review in-house History Survey, Receive Local/Consultant or review in-house Archaeology Survey, Receive Local/Consultant or review in-house Ecology Survey | 16.7 | Environmental Resource Identification | 5d | Receive Environmental Study Layout/Start Environmental Studies ; It’s not clear for some when to enter the start date in the schedule whether activity should start when SME has everything needed included in a complete/accurate request form, on the date when the SME receives the layout even if no request form is received, or the date the request form is received (whether complete or incomplete. | Environmental Resource Identification (185 –245 days) *NEPA P6 Team Member Activity Study area layout and is received from |  | when all adequate information including study area layout and RERI (request for Environmental ID) request is received from PM or from a consultant. | After OES office head signs off on document and when the Studies Request has been transmitted to other groups in Environmental including History, Archeology, and Ecology so that they can begin their work on the project. (Air and Noise work starts later.) |  | a. Titles should be more relevant to the work being done. Change Conduct Eco with steps to conduct Resource ID; Conduct agency consultation should be conduct Ecology technical studies. (standardize activity names since those names are used across the office d. 13464=Bat counties, aquatics, NMFS, time of year can all impact Agency consultation activities/aquatic surveys due to survey seasons; SMEs have noticed a pattern of when NMFS, bat coordination, and aquatics will be needed which impact the schedule. a. Providing more input from SMEs earlier, and if there are changes there should be flexibility to accommodate those changes. The duration set by the P6 Schedule is allotted for the NEPA Analyst to obtain any additional information immediately upon being assigned a project or when the request has been routed to the PM? |  |  |  | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 123 | Item | employeecenter/SAM/Lists/SAM
Conduct Ecology Survey (with steps) | 10413 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Ecology Survey | Conduct Ecology Survey for Seasonal Species, Environmental Resource Identification Complete, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.1 | Ecological Survey | 120d | Conduct Ecology Survey (with steps) Applicable tasks (6 Steps) • Conduct Background Research & Early Coordination• Conduct Ecology Survey for Protected Water & Habitats• USACE & EPD Field Visits (if needed)• Prepare ERSR• GDOT Review of ERSR• Submit Ecology Resource Boundaries to PM/Design etc. | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity This activity is done when a RERI (Request for Resource Identification) is received from NEPA or an ecologist receives an environmental survey boundary from the Roadway or Bridge Office. Usually 2 ecologists and someone for GPS conduct the ecology survey to check if the habitat is good for any Georgia endangered? species. | 11413/11414=Resource ID activities not needed on some maintenance projects. g. 14447 is already built into 11413. 11413 allots time for GDOT review of survey report, while 14447 is a separate milestone for receiving the survey report. Maybe adding the receive activity as a step of the other would be helpful. | When the Ecologist receives the Request for Technical Studies from NEPA and once the ecologist has received all required items to begin surveys In-House OES staff: This activity begins with the receipt of requests for Resource Identification form from NEPA & once the ERSR has been approved and Ecology Boundaries have been submitted to the Design a. 11413= Start date not clear. Some users click start when they receive the Request for Environmental Resource ID from NEPA; others click start when they request early coordination which is usually a month after receiving the request from NEPA. | When the ERSR has been completed and Ecology Boundaries have been submitted to the PM a. 11413= not clear. Does activity end when survey report has been completed or when the report is completed AND boundaries have been submitted to PM/Design? Sometimes (when Ecology does a joint survey/AOE report) there won’t be a survey report so we can’t click finish. |  |  |  |  | 6 | Ecologist |  |  |  |  | N | Ecologist | 124 | Item | employeecenter/SAM/Lists/SAM
Public Information Open House Advertisement (with steps) | 09646 | DISTRICT OFFICE | EIS;#37;#PIOH;#28 | Task Dependent | Environmental Preparation for PIOH (with steps), Property Research for PIOH, Request Public Information Open House (PIOH) | Pre-CTM Public Information Open House Held (for EIS) | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 60d | [9 empty] | 3 | n/a |  |  |  |  | N |  | 125 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Ecology Survey | 10447 | ENVIRONMENTAL SERVICES | Environmental;#5;#Ecology;#2 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Ecology Survey (with steps) non-seasonal, Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant Ecology Survey - If a consultant and/or local government is performing the ecology survey, this is the date that the ecology survey is received by the Environmental Office for review. Ecology Survey (240 days Total) *Ecology P6 Team Member Activity a. 11447=Receive local/consultant survey—are we receiving actual survey report or delineations. We don’t actually receive a survey; Is it when field survey ends, (the understanding is it means when we receive the report. Sometimes there is no report so it’s ambiguous in that case. Could this name be changed to include receiving the consultant survey report? | When a consultant and/or local government is performing the ecology survey. | If ecology work is done in house. However, we typically do not delete this activity from the schedule since the status could change during the course of the project. | When the ecology survey is received by the consultant and/or local government. For In-house projects only: when Ecology team member has received the consultant survey report for review/provided the document to their manager | When the ecology survey is received by the consultant and/or local government | This activity is on the critical path for completion and review of the ecology survey and subsequently the completion of environmental resource identification. | Ecology surveys for seasonal species are not a predecessor for this activity. * Another activity for approval of a consultant report may be needed. 11447 is a predecessor to the A3M. Sometimes the A3M is done before the report is actually approved but after the major conclusions of the ecology survey are settled. This happens with in house and consultant surveys. |  |  |  |  | constraint to start as late as possible with a lag of 40 days so that the activity occurs at the time it is needed for review (typically 40 days) | As Late As Possible |  |  | N |  | 126 | Item | employeecenter/SAM/Lists/SAM
Environmental Activity Summary (11412 through 18100) | 10000 | ENVIRONMENTAL SERVICES | Environmental;#5 | Level Of Effort | Receive Environmental Study Area Layout / Start Environmental Studies | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16 | Environmental Activities during prelim. Plans | 1,288d | [10 empty] | n/a |  |  |  |  | N |  | 127 | Item | employeecenter/SAM/Lists/SAM
Conduct Ecology Survey for Seasonal Species | 10414 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Conduct Ecology Survey (with steps), Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Agency Consultation for Ecology (with steps), Environmental Resource Identification Complete, PM Request PFPR, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.1 | Ecological Survey | 60d | Conduct Ecology Survey for Seasonal Species | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity If a specific species is identified during activity 11413, this survey is done to look for the particular species found during the 11413 survey. Some surveys are consulted out. Early coordination with agencies like Fish and Wildlife and the Department of Natural Resources is done before the surveys so the ecologists know what species to look for. | a. Time for 4 seasonal surveys is not needed in the schedule for signal projects, and other types of projects. In most cases we don’t need all seasonal surveys but sometimes we do so it should be built in. c. Majority of the time (11414/11424/11434) conduct seasonal survey can be taken out. | When the season for this species begins | When the survey for this species is complete | [5 empty] | Ecologist |  |  |  |  | N | Ecologist | 128 | Item | employeecenter/SAM/Lists/SAM
Pre-CTM Public Information Open House Held (for EIS) | 09647 | ENVIRONMENTAL SERVICES | Environmental;#5;#EIS;#37;#PIOH;#28 | Start Milestone | Environmental Preparation for PIOH (with steps), Public Information Open House Advertisement (with steps) | Concept Meeting, Respond to PIOH Comments, Review Local/Consultant Draft Concept for Concept Meeting | 16.10.4.3.1 | Pre-Concept Team Meeting PIOH (for EIS) | 0d | Pre-CTM Public Information Open House Held (for EIS |  |  | day of PIOH | day of PIOH when meeting concludes |  | don’t use | [8 empty] | N |  | 129 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant History Survey | 10457 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct History Survey (with steps), Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant History Survey History Survey (120 days Total) History P6 Team Member Activity consultant provides survey developed with the same guidelines as in house surveys | When a consultant and/or local government is performing the history survey. | Activities are not needed if project is in-house. | When the History team member receives the consultant history survey report for review and provides the document to their manager (in-house projects only) | When the History Survey is received by OES | [7 empty] | As Late As Possible |  |  | N |  | 130 | Item | employeecenter/SAM/Lists/SAM
Conduct Archaeological Survey (with steps) | 10463 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Archaeology Survey | Environmental Resource Identification Complete, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.3 | Archaeological Survey | 120d | Conduct Archaeology Survey (with steps) Applicable tasks (8 Steps) • Conduct Background Research & Phase I Field Work • Conduct Phase I Testing• Prepare Archaeology Survey Report• GDOT Review of Archaeology Survey Report• Submit Archaeology Draft Survey Report to SHPO• Final Submission of Archaeology Survey Report• SHPO (State Historical Preservation Office) Review and Concurrence• Submit Archaeology Survey Boundaries to PM/Design etc. Resource Identification Archeology Survey (240 days Total) *Archeology P6 Team Member Activity | This activity is needed for most state and federally funded projects. Some state projects require a lower level of coordination. A request is received for Resource ID from NEPA. | 11463, 13473 and 11453 are not needed for maintenance projects. | In-house: When the Archaeologist receives the Request for Resource Identification form from NEPA or Consultant: when the archaeologist receives the required items to begin surveys. The Environment Survey Boundary from Roadway Design is required.; Consultants need the ESB (Environment Survey Boundary) to start, too. The SME seem to be confused by this step. Three SME gave three different start dates for this activity. Some users start when project is assigned by manager, some start on their first day in the field, and some start on date listed on transmittal form. | When the Archaeology Report has been approved and boundaries have been submitted to the PM (for Design) |  | Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done. Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. |  | Does not consider all the surveys that may be required to conduct for this activity. • Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done.• Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier.• Add a “Phase 2 Testing” activity added to the schedule. This would add time to a step and provide flexibility.• If one person is taking too long it delays the AOE for everyone.• The 120 day review period time isn’t ideal; it should be based on individual projects or surveys. It would be nice to adjust or add time after you started.• Managers should look at the schedule beforehand on certain projects based on the number of resources.• Add a check list after the scoping meeting.• If the project is more complex then reach out to Project Managers and request more time for reviews; better duration plan from the beginning. | 8 | Archaeologist |  |  |  |  | N | Archaeologist | 131 | Item | employeecenter/SAM/Lists/SAM
Conduct History Survey (with steps) | 10453 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant History Survey | Environmental Resource Identification Complete, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.2 | History Survey | 120d | Conduct History Survey (with steps) Applicable tasks (7 Steps) • Conduct Background Research & Early Coordination• Conduct History Survey• Write History Survey Report• GDOT Review of History Survey Report• Submit History Survey Report to SHPO• SHPO Review and Concurrence• Submit History Survey Boundaries to PM/Design; History Survey (120 days Total) History P6 Team Member Activity | This activity is needed for all projects. | 11463, 13473 and 11453 are not needed for maintenance projects. | When the Historian receives the Request for Resource Identification form from NEPA and has received all required items to begin surveys. In house OES Staff: This activity begins with the receipt of the Request for Resource Identification form from NEPA | When the History Report has been completed and boundaries have been submitted to the PM/Design |  | Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done. Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. |  |  | 7 | Historian |  |  |  |  | N | Historian | 132 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant or review in-house Archaeology Survey | 10467 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5;#Consultant;#51 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Archaeological Survey (with steps), Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant Archaeology Survey Resource Identification Archeology Survey (240 days Total)&nbsp; *Archeology P6 Team Member Activity | Activity is needed for Local/Consultant Archeology Surveys - digital and hard copies must be submitted. | Activities are not needed if project is in-house. | When the Archaeology team member receives the consultant survey report for review and provides the document to their manager | When the Archaeology Survey is received by OES Confusion on how this information is being collected and used in the rest of the schedule. Maybe this activity should be clearer or another step should be created in this section. Their needs to be more awareness of what consultants are inputting in this step. | [7 empty] | As Late As Possible |  |  | N |  | 133 | Item | employeecenter/SAM/Lists/SAM
Environmental Resource Identification Complete | 10499 | ENVIRONMENTAL SERVICES | Environmental;#5 | Finish Milestone | Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps) non-seasonal, Conduct History Survey (with steps), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Archaeology Survey, Receive Local/Consultant or review in-house Ecology Survey, Receive Local/Consultant or review in-house History Survey | Receive Environmental Resource Boundaries (in-house design), Receive Environmental Resource Boundaries (consultant design) for scoping phase, PAR Checkpoint 3a - Prepare PAR Report | 16.7 | Environmental Resource Identification | 0d | Environmental Resource Identification Complete & Environmental Technical Studies Complete (if state funded, NEPA sends letter to PM with Environmental Tech Studies Complete Form.) Environmental Resource Identification (185 –245 days) *NEPA P6 Team Member Activity Technical Studies (120 days); *NEPA P6 Team Member Activity | - 11499=(Resource ID complete) Activity is being held up because Resource reports are not being completed prior to delineations being transmitted to design. Should this activity capture the completion of resource reports or just when delineations are being transmitted? (issue is usually with Ecology since they sometimes do joint resource reports and AOEs; the joint document is never complete until much later than Rsrc ID complete although the resources have been delineated per BL). |  | When the last survey report has been approved by the specialists and resources(as appropriate) have been transmitted to Design and the last Agency Concurrence has been received by OES. | When the last survey report has been approved by the specialists and resources(as appropriate) have been transmitted to Design and the last Agency Concurrence has been received by OES and AOEs (Assessment of Effects) approved Agencies include SHPO, Fish and Wildlife, Corp of Engineers Confusion on when to push the green arrow and to push the save button/icon in p6 team member. |  | Confusion on how this information is being collected and used in the rest of the schedule. Maybe this activity should be clearer or another step should be created in this section. Their needs to be more awareness of what consultants are inputting in this step. A3M is next step after Technical Studies Complete. | [8 empty] | N |  | 134 | Item | employeecenter/SAM/Lists/SAM
Environmental Resource Identification Summary | 11411 | ENVIRONMENTAL SERVICES | Environmental;#5 | WBS Summary |  |  | 16.7 | Environmental Resource Identification | 245d | [10 empty] | n/a |  |  |  |  | N | n/a | 135 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Study Area Layout / Start Environmental Studies | 11412 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Consultant Kick-Off Meeting, Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Define Project Concept, FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps), Finalize Scoping and Outreach Materials, Finalize Screen 1 Report, Finalize Screen 2 Report, Finalize Screen 3 Report, Initial Concept Meeting, Notice to Proceed (NTP) for Consultant Contract, Respond to PIOH Comments, Scoping Public Information Open House Held (for EIS), Screen 1 Public Information Open House Held (for EIS), Screen 2 Public Information Open House Held (for EIS), Screen 3 Public Information Open House Held (for EIS), | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Conduct Agency Consultation for Ecology (with steps), Conduct Air Quality Analysis (with steps), Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps) non-seasonal, Conduct Ecology Survey for Seasonal Species, Conduct History Survey (with steps), Conduct Noise Analysis (with steps), Conduct Section 106 Consultation- History (with steps), Develop Draft Section 4(f) Evaluation (previously 15200), Develop, Approve & Publish Notice of Decision (NOD), Draft Environmental Impact Statement (EIS) Development, Environmental Resource Identification Complete, Initial PAR Layout, PFPR Request (OES), PM Request PFPR, Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Receive Environmental Resource Boundaries, Review and Approve GEPA Type B Letter, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Environmental Activity Summary (11412 through 18100), Receive Local/Consultant or review in-house Ecology Survey, Receive Local/Consultant Assessment of Effects (AOE) - History, Receive Local/Consultant Assessment of Effects (AOE) - History, Receive Local/Consultant Air Quality Analysis, Receive Local/Consultant Noise Analysis, Receive Environmental Resource Boundaries (in-house design) | 16.7 | Environmental Resource Identification | 5d | Receive Environmental Study Layout/Start Environmental Studies ; It’s not clear for some when to enter the start date in the schedule - whether activity should start when SME has everything needed included in a complete/accurate request form, on the date when the SME receives the layout even if no request form is received, or the date the request form is received (whether complete or incomplete. | Environmental Resource Identification (185 –245 days) *NEPA P6 Team Member Activity Study area layout and is received from |  | when all adequate information including study area layout and RERI (request for Environmental ID) request is received from PM or from a consultant. | After OES office head signs off on document and when the Studies Request has been transmitted to other groups in Environmental including History, Archeology, and Ecology so that they can begin their work on the project. (Air and Noise work starts later.) |  | a. Titles should be more relevant to the work being done. Change Conduct Eco with steps to conduct Resource ID; Conduct agency consultation should be conduct Ecology technical studies. (standardize activity names since those names are used across the office) d. 13464=Bat counties, aquatics, NMFS, time of year can all impact Agency consultation activities/aquatic surveys due to survey seasons; SMEs have noticed a pattern of when NMFS, bat coordination, and aquatics will be needed which impact the schedule. a. Providing more input from SMEs earlier, and if there are changes there should be flexibility to accommodate those changes. The duration set by the P6 Schedule is allotted for the NEPA Analyst to obtain any additional information immediately upon being assigned a project or when the request has been routed to the PM? |  |  |  | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 136 | Item | employeecenter/SAM/Lists/SAM
Conduct Ecology Survey (with steps) non-seasonal | 11413 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Ecology Survey | Conduct Agency Consultation for Ecology (with steps), Conduct Ecology Survey for 2nd Seasonal Species, Conduct Ecology Survey for 3rd Seasonal Species, Conduct Ecology Survey for 4th Seasonal Species, Conduct Ecology Survey for Seasonal Species, Environmental Resource Identification Complete, Initial PAR Layout, PM Request PFPR, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.1 | Ecological Survey | 120d | Conduct Ecology Survey (with steps) Applicable tasks (6 Steps) • Conduct Background Research & Early Coordination• Conduct Ecology Survey for Protected Water & Habitats• USACE & EPD Field Visits (if needed)• Prepare ERSR• GDOT Review of ERSR• Submit Ecology Resource Boundaries to PM/Design etc. | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity This activity is done when a RERI (Request for Resource Identification) is received from NEPA or an ecologist receives an environmental survey boundary from the Roadway or Bridge Office. Usually 2 ecologists and someone for GPS conduct the ecology survey to check if the habitat is good for any Georgia endangered? species. | 11413/11414=Resource ID activities not needed on some maintenance projects. g. 14447 is already built into 11413. 11413 allots time for GDOT review of survey report, while 14447 is a separate milestone for receiving the survey report. Maybe adding the receive activity as a step of the other would be helpful. | When the Ecologist receives the Request for Technical Studies from NEPA and once the ecologist has received all required items to begin surveys In-House OES staff: This activity begins with the receipt of requests for Resource Identification form from NEPA & once the ERSR has been approved and Ecology Boundaries have been submitted to the Design a. 11413= Start date not clear. Some users click start when they receive the Request for Environmental Resource ID from NEPA; others click start when they request early coordination which is usually a month after receiving the request from NEPA. | When the ERSR has been completed and Ecology Boundaries have been submitted to the PM a. 11413= not clear. Does activity end when survey report has been completed or when the report is completed AND boundaries have been submitted to PM/Design? Sometimes (when Ecology does a joint survey/AOE report) there won’t be a survey report so we can’t click finish. |  |  |  |  | 6 | Ecologist |  |  |  |  | N | Ecologist | 137 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL - Conduct Ecology Survey for 2nd Seasonal Species | 11424 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Conduct Ecology Survey (with steps), Conduct Ecology Survey for Seasonal Species, Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Agency Consultation for Ecology (with steps), Conduct Ecology Survey for 3rd Seasonal Species, Environmental Resource Identification Complete, PM Request PFPR, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.1 | Ecological Survey | 60d | Conduct Ecology Survey for 2nd Seasonal Species | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity | e. 11424/11434/11444= all additional species surveys that are often not needed. It may help for the SME to be involved during SRC to confirm the amount of seasonal surveys needed. Having activities removed on the front end. | When the season for this species begins | When the survey for this species is complete | [5 empty] | Ecologist |  |  |  |  | Y | Ecologist | 138 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL - Conduct Ecology Survey for 4th Seasonal Species | 11444 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Conduct Ecology Survey (with steps), Conduct Ecology Survey for 3rd Seasonal Species, Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Agency Consultation for Ecology (with steps), PM Request PFPR | 16.7.1 | Ecological Survey | 60d | Conduct Ecology Survey for 4th Seasonal Species; Ecology Survey (240 days Total) *Ecology P6 Team Member Activity |  | a. 11424/11434/11444= all additional species surveys that are often not needed. It may help for the SME to be involved during SRC to confirm the amount of seasonal surveys needed. Having activities removed on the front end. | When the season for this species begins | When the survey for this species is complete | [5 empty] | Ecologist |  |  |  |  | Y | Ecologist | 139 | Item | employeecenter/SAM/Lists/SAM
Conduct Ecology Survey for Seasonal Species | 11414 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Conduct Ecology Survey (with steps), Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Agency Consultation for Ecology (with steps), Conduct Ecology Survey for Seasonal Species, Environmental Resource Identification Complete, PM Request PFPR, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design), Initial Par Layout | 16.7.1 | Ecological Survey | 60d | Conduct Ecology Survey for Seasonal Species | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity If a specific species is identified during activity 11413, this survey is done to look for the particular species found during the 11413 survey. Some surveys are consulted out. Early coordination with agencies like Fish and Wildlife and the Department of Natural Resources is done before the surveys so the ecologists know what species to look for. | a. Time for 4 seasonal surveys is not needed in the schedule for signal projects, and other types of projects. In most cases we don’t need all seasonal surveys but sometimes we do so it should be built in. c. Majority of the time (11414/11424/11434) conduct seasonal survey can be taken out. | When the season for this species begins | When the survey for this species is complete | [5 empty] | Ecologist |  |  |  |  | N | Ecologist | 140 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant or review in-house Ecology Survey | 11447 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Ecology Survey (with steps) non-seasonal, Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant Ecology Survey - If a consultant and/or local government is performing the ecology survey, this is the date that the ecology survey is received by the Environmental Office for review. Ecology Survey (240 days Total) *Ecology P6 Team Member Activity. a. 11447=Receive local/consultant survey—are we receiving actual survey report or delineations. We don’t actually receive a survey; Is it when field survey ends, (the understanding is it means when we receive the report. Sometimes there is no report so it’s ambiguous in that case. Could this name be changed to include receiving the consultant survey report? | When a consultant and/or local government is performing the ecology survey. | If ecology work is done in house. However, we typically do not delete this activity from the schedule since the status could change during the course of the project. | When the ecology survey is received by the consultant and/or local government For In-house projects only: when Ecology team member has received the consultant survey report for review/provided the document to their manager | When the ecology survey is received by the consultant and/or local government | This activity is on the critical path for completion and review of the ecology survey and subsequently the completion of environmental resource identification. | Ecology surveys for seasonal species are not a predecessor for this activity. * Another activity for approval of a consultant report may be needed. 11447 is a predecessor to the A3M. Sometimes the A3M is done before the report is actually approved but after the major conclusions of the ecology survey are settled. This happens with in house and consultant surveys. |  |  |  |  | constraint to start as late as possible with a lag of 40 days so that the activity occurs at the time it is needed for review (typically 40 days) | As Late As Possible |  |  | N |  | 141 | Item | employeecenter/SAM/Lists/SAM
Initial Concept Meeting | 10750 | PROGRAM DELIVERY | Concept;#20;#PM;#18;#Meeting;#4 | Task Dependent | Define Project Concept (scoping or pre-concept), Data Acquisition for Scoping or Concept (with steps) | Request Public Information Open House (PIOH), Create & Submit Environmental Study Area Layout, Receive Environmental Study Area Layout / Start Environmental Studies, Concept Meeting, Develop Alternatives |  | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 1d | Concept Activities for all projects (Scoping Pre-Concept or Concept) | [14 empty] | N |  | 142 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL - Conduct Ecology Survey for 3rd Seasonal Species | 11434 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Conduct Ecology Survey (with steps), Conduct Ecology Survey for 2nd Seasonal Species, Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Agency Consultation for Ecology (with steps), Conduct Ecology Survey for 4th Seasonal Species, PM Request PFPR | 16.7.1 | Ecological Survey | 60d | Conduct Ecology Survey for 3rd Seasonal Species | Ecology Survey (240 days Total) *Ecology P6 Team Member Activity | a. 11424/11434/11444= all additional species surveys that are often not needed. It may help for the SME to be involved during SRC to confirm the amount of seasonal surveys needed. Having activities removed on the front end. | When the season for this species begins | When the survey for this species is complete | [5 empty] | Ecologist |  |  |  |  | Y | Ecologist | 143 | Item | employeecenter/SAM/Lists/SAM
Conduct History Survey (with steps) | 11453 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house History Survey | Conduct Section 106 Consultation - History (with steps), Environmental Resource Identification Complete, PM Request PFPR, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.2 | History Survey | 120d | Conduct History Survey (with steps)&nbsp;&nbsp; Applicable tasks (7 Steps) • Conduct Background Research & Early Coordination• Conduct History Survey• Write History Survey Report• GDOT Review of History Survey Report• Submit History Survey Report to SHPO• SHPO Review and Concurrence• Submit History Survey Boundaries to PM/Design History Survey (120 days Total) History P6 Team Member Activity | This activity is needed for all projects. | 11463, 13473 and 11453 are not needed for maintenance projects. | When the Historian receives the Request for Resource Identification form from NEPA and has received all required items to begin surveys. In house OES Staff: This activity begins with the receipt of the Request for Resource Identification form from NEPA | When the History Report has been completed and boundaries have been submitted to the PM/Design |  | Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done.Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. |  |  | 7 | Historian |  |  |  |  | N | Historian | 144 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant or review in-house History Survey | 11457 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct History Survey (with steps), Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant History Survey History Survey (120 days Total) History P6 Team Member Activity consultant provides survey developed with the same guidelines as in house surveys | When a consultant and/or local government is performing the history survey. | Activities are not needed if project is in-house. | When the History team member receives the consultant history survey report for review and provides the document to their manager (in-house projects only) | When the History Survey is received by OES | [7 empty] | As Late As Possible |  |  | N |  | 145 | Item | employeecenter/SAM/Lists/SAM
Concept Development Summary | 12000 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | WBS Summary |  |  | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 1283d | [15 empty] | N |  | 146 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant or review in-house Archaeology Survey | 11467 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Archaeological Survey (with steps), Environmental Resource Identification Complete | 16.7.4 | Receive Local/Consultant Environmental Resource Identification | 0d | Receive Local/Consultant Archaeology Survey Resource Identification - Archeology Survey (240 days Total) *Archeology P6 Team Member Activity | Activity is needed for Local/Consultant Archeology Surveys - digital and hard copies must be submitted. | Activities are not needed if project is in-house. | When the Archaeology team member receives the consultant survey report for review and provides the document to their manager | When the Archaeology Survey is received by OES Confusion on how this information is being collected and used in the rest of the schedule. Maybe this activity should be clearer or another step should be created in this section. Their needs to be more awareness of what consultants are inputting in this step. | [7 empty] | As Late As Possible |  |  | N |  | 147 | Item | employeecenter/SAM/Lists/SAM
Conduct Archaeological Survey (with steps) | 11463 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Task Dependent | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Archaeology Survey | Environmental Resource Identification Complete, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design) | 16.7.3 | Archaeological Survey | 120d | Conduct Archaeology Survey (with steps) Applicable tasks (8 Steps)• Conduct Background Research & Phase I Field Work • Conduct Phase I Testing• Prepare Archaeology Survey Report• GDOT Review of Archaeology Survey Report• Submit Archaeology Draft Survey Report to SHPO• Final Submission of Archaeology Survey Report• SHPO (State Historical Preservation Office) Review and Concurrence• Submit Archaeology Survey Boundaries to PM/Design etc. Resource Identification - Archeology Survey (240 days Total) *Archeology P6 Team Member Activity | This activity is needed for most state and federally funded projects. Some state projects require a lower level of coordination. A request is received for Resource ID from NEPA. | 11463, 13473 and 11453 are not needed for maintenance projects. | In-house: When the Archaeologist receives the Request for Resource Identification form from NEPA or Consultant: when the archaeologist receives the required items to begin surveys. The Environment Survey Boundary from Roadway Design is required. Consultants need the ESB (Environment Survey Boundary) to start, too. The SME seem to be confused by this step. Three SME gave three different start dates for this activity. Some users start when project is assigned by manager, some start on their first day in the field, and some start on date listed on transmittal form. | When the Archaeology Report has been approved and boundaries have been submitted to the PM (for Design) |  | Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done. Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. |  | Does not consider all the surveys that may be required to conduct for this activity. • Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done.• Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier.• Add a “Phase 2 Testing” activity added to the schedule. This would add time to a step and provide flexibility.• If one person is taking too long it delays the AOE for everyone.• The 120 day review period time isn’t ideal; it should be based on individual projects or surveys. It would be nice to adjust or add time after you started.• Managers should look at the schedule beforehand on certain projects based on the number of resources.• Add a check list after the scoping meeting.• If the project is more complex then reach out to Project Managers and request more time for reviews; better duration plan from the beginning. | 8 | Archaeologist |  |  |  |  | N | Archaeologist | 148 | Item | employeecenter/SAM/Lists/SAM
PM Reviews Concept Report | 12722 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Local/Consultant Finalize Concept Report,Concept Meeting,Define Project Concept (scoping or pre-concept), Submit Concept Report to PM | Management Concept Approval Complete, Respond to Concept Report Comments, PM Submit Concept Report, Concept Report Review and Comments | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 10d | [15 empty] | N |  | 149 | Item | employeecenter/SAM/Lists/SAM
PM Submit Concept Report | 12800 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Start Milestone | Submit Draft to PM for Concept Team Meeting, PM Reviews Concept Report, Receive Environmental Resource Boundaries (in-house design), Receive Environmental Resource Boundaries (consultant design) for scoping phase, Respond to Concept Report Comments, PM Reviews Concept Report, Define Project Concept (scoping or pre-concept), Concept Meeting | Concept Report Review and Comments | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 0d | [15 empty] | N |  | 150 | Item | employeecenter/SAM/Lists/SAM
Concept Meeting | 12600 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | Data Acquisition for Scoping or Concept (with steps), Submit Draft to PM for Concept Team Meeting, Review Local/Consultant Draft Concept for Concept Meeting, Review Local/Consultant Draft Concept for Concept Meeting, Initial Concept Meeting, Define Project Concept (scoping or pre-concept) | PM Reviews Concept Report, Local/Consultant, Finalize Concept Report, Finalize Concept Report, PM Submit Concept Report | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 1d | [15 empty] | N |  | 151 | Item | employeecenter/SAM/Lists/SAM
Environmental Resource Identification Complete | 11499 | ENVIRONMENTAL SERVICES | Environmental;#5 | Finish Milestone | Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps) non-seasonal, Conduct History Survey (with steps), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant or review in-house Archaeology Survey, Receive Local/Consultant or review in-house Ecology Survey, Receive Local/Consultant or review in-house History Survey | Conduct Agency Consultation for Ecology (with steps), Conduct Avoidance and Minimization Measures Meeting (A3M), Conduct Section 106 Consultation - History (with steps), Develop Draft Section 4(f) Evaluation (previously 15200), Draft Environmental Impact Statement (EIS) Development, Environmental Approval Complete (If state funds: Env. Activities Complete), PM Request PFPR, Preliminary Roadway Plans (consultant design), Prepare CE, Prepare Draft EA (with steps), Prepare Environmental Effects Report (EER), Prepare Final EA/FONSI (with steps), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Receive Environmental Resource Boundaries (consultant design), Receive Environmental Resource Boundaries (in-house design), Receive Local/Consultant Draft EA/FONSI, Request Public Information Open House (PIOH), Review and Approve Environmental Effects Report (EER), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Start Preliminary Roadway Plans,PAR Checkpoint 3a - Prepare PAR Report | 16.7 | Environmental Resource Identification | 0d | Environmental Resource Identification Complete & Environmental Technical Studies Complete (if state funded, NEPA sends letter to PM with Environmental Tech Studies Complete Form.) Environmental Resource Identification (185 –245 days) *NEPA P6 Team Member Activity Technical Studies (120 days) *NEPA P6 Team Member Activity | - 11499=(Resource ID complete) Activity is being held up because Resource reports are not being completed prior to delineations being transmitted to design. Should this activity capture the completion of resource reports or just when delineations are being transmitted? (issue is usually with Ecology since they sometimes do joint resource reports and AOEs; the joint document is never complete until much later than Rsrc ID complete although the resources have been delineated per BL). |  | When the last survey report has been approved by the specialists and resources(as appropriate) have been transmitted to Design and the last Agency Concurrence has been received by OES. | When the last survey report has been approved by the specialists and resources(as appropriate) have been transmitted to Design and the last Agency Concurrence has been received by OES and AOEs (Assessment of Effects) approved. Agencies include SHPO, Fish and Wildlife, Corp of Engineers Confusion on when to push the green arrow and to push the save button/icon in p6 team member. |  | Confusion on how this information is being collected and used in the rest of the schedule. Maybe this activity should be clearer or another step should be created in this section. Their needs to be more awareness of what consultants are inputting in this step. A3M is next step after Technical Studies Complete. | [8 empty] | N |  | 152 | Item | employeecenter/SAM/Lists/SAM
Concept Report Review and Comments | 12900 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Task Dependent | PM Submit Concept Report, Receive Environmental Resource Boundaries (in-house design), PAR Checkpoint 3d - Submit least damaging alternative to design, Receive Environmental Resource Boundaries (consultant design) for scoping phase, Respond to Concept Report Comments, PM Reviews Concept Report | Management Concept Approval Complete | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 47d | [15 empty] | N |  | 153 | Item | employeecenter/SAM/Lists/SAM
Management Concept Approval Complete | 13000 | PROGRAM DELIVERY | Concept;#20;#PM;#18 | Finish Milestone | Concept Report Review and Comments, PM Reviews Concept Report, Receive Environmental Resource Boundaries (in-house design), Receive Environmental Resource Boundaries (consultant design) for scoping phase, Respond to Concept Report Comments, | Concept Approval to PFPR Inspection, Request Public Information Open House (PIOH), Start Database Preparation | 5 | Concept Activities for all projects (Scoping Pre-Concept or Concept) | 0d | [15 empty] | N |  | 154 | Item | employeecenter/SAM/Lists/SAM
Receive Preliminary Plans to Begin Technical Studies | 13417 | ENVIRONMENTAL SERVICES | Environmental;#5 | Start Milestone | Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Develop Draft Section 4(f) Evaluation, Conduct Section 106 Consultation - Archaeology (with steps), Start Technical Studies to Environmental Completion, Receive Local/Consultant Air Quality Analysis, Conduct Noise Analysis (with steps), Receive Local/Consultant Noise Analysis, Develop Draft Section 4(f) Evaluation (previously 15200), Receive Local/Consultant Assessment of Effects (AOE) - History, Conduct Agency Consultation for Ecology (with steps), Conduct Air Quality Analysis (with steps), Conduct Section 106 Consultation - History (with steps), Prepare Draft EA (with steps), Receive Local/Consultant Agency Consultation for Ecology, Environmental Technical Studies Complete | 16.8 | Technical Studies | 0d | Receive Preliminary Plans to Begin Technical Studies ( in house - Request RTCS from PM/Road Design handled like a request for Resource ID) | 13417 (Receive plans to being tech studies) When project is consulted out in-house SMEs are unaware of whether this activity is starting. R203Technical Studies (120 days); *NEPA P6 Team Member Activity |  | When the least damaging alternative and appropriate avoidance and mitigation measures have been taken into account by Design. The PM will provide OES with preliminary plans to begin Assessment of Effects by the SME’s. | When the least damaging alternative and appropriate avoidance and mitigation measures have been taken into account by Design. The PM will provide OES with preliminary plans to begin Assessment of Effects by the SME’s. | [10 empty] | N |  | 155 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Agency Consultation for Ecology | 13467 | ENVIRONMENTAL SERVICES | Environmental;#5;#Ecology;#2 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Preliminary Plans to Begin Technical Studies | Conduct Agency Consultation for Ecology (with steps), Environmental Technical Studies Complete | 16.8.5 | Agency Consultation for Ecology | 0d | Receive Local/Consultant Agency Consultation for Ecology Agency Consultation for Ecology (120 days Total) & Ecology P6 Team Member Activity Receive FHWA/USFWS concurrence Receive consultant assessment; may need 2nd round | needed for all consultant projects | 13467 (Receive local/consultant agency consultation) is already built into 13463 as one of the steps. It is confusing because 13463 allots time for GDOT review of the AOE, while 13467 is a separate milestone for receiving the AOE. | When the Ecology AOER is received by OES and the document is provided to the ecology section manager. (In-house projects only) | When the consultant Ecology AOER is received by OES for review and a copy is provided to the NEPA manager.. |  | 13467=Receive local/consultant Agency consultation—We don’t actually receive “consultation”, we receive “concurrence”. P6 Language should be more in line with the section’s terminology. (Title should reflect more with the work being done). Is that when we receive concurrence or when we receive AOE? (Not clear). | [5 empty] | As Late As Possible |  |  | N |  | 156 | Item | employeecenter/SAM/Lists/SAM
Conduct Noise Analysis (with steps) | 13483 | ENVIRONMENTAL SERVICES | Environmental;#5;#Noise;#31 | Task Dependent | Conduct QA of Preliminary Geometry, Management Concept Approval Complete, Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant Noise Analysis, Receive Preliminary Plans to Begin Technical Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Environmental Technical Studies Complete | 16.8.3 | Noise Analysis | 120d | Conduct Noise Analysis Applicable Tasks (6 Steps)-Field Work, Run Noise Mode; Study Noise Abatement Measures, Prepare Noise Analysis Report, GDOT Review of Noise Report, Submit Noise Wall Envelopes to Design, PM, and Bridge Design(Predecessor: Receive Technical Studies Request from NEPA (in-house Air/Noise P6 Team Member Activity | activity 13483 is needed for all projects except state funded projects. Small maintenance projects and some bridge replacements don't require a full assessment, but a memo is written up. | activity 13483 is not needed for state funded projects. For state funded projects, the same date is entered for beginning and completion dates. | WhenOES has received all items needed to begin Noise Assessment including a RTCS from NEPA, preliminary plans, and traffic projections. | When Noise Assessment is GDOT approved/signed and transmitted to FHWA. |  |  |  |  | 6 | AIr and Noise Specialist |  |  |  |  | N | AIr and Noise Specialist | 157 | Item | employeecenter/SAM/Lists/SAM
Conduct Section 106 Consultation - History (with steps) | 13473 | ENVIRONMENTAL SERVICES | History;#8 | Task Dependent | Conduct History Survey (with steps), Conduct QA of Preliminary Geometry, Develop Concept Layout of Preferred Alternate (with steps), Environmental Resource Identification Complete, Management Concept Approval Complete, Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant Assessment of Effects (AOE) - History, Receive Preliminary Plans to Begin Technical Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Environmental Technical Studies Complete | 16.8.2 | Cultural Resource Assessment of Effects (AOE) - History | 120d | Conduct Section 106 Consultation (with steps) Applicable tasks (6 Steps) • Prepare AOE(Assessment of Effects Report) (& MOA (mitigation Memorandum of Agreement between GDOT and other agencies), if needed)• GDOT Review of AOE (& MOA)• Submit AOE (& MOA) to SHPO• SHPO Review and Concurrence• ACHP Review (only if adverse impact)• MOA Ratification (only if adverse impact - not very common) Cultural Resources Assessment of Effects (AOE) (120 days Total) *Archeology P6 Team Member Activity | This activity is needed for most in house projects. *The historian and archaeologist will determine responsibility for activities 13473 and 13477. Nepa sends a request for Technical Studies or request for Phase 2 surveys. | 11463, 13473 and 11453 are not needed for maintenance projects. May not be needed If there are no Arch/History resources on the project and Archaeology is preparing a No Potential To Cause Effect document (History preparing a No Historic Properties Affected document). Resource ID and Technical Studies become one phase. (usually maintenance projects) | When the archaeology team member has started preparing the Assessment of Effects Report (additional procurement takes additional 3 - 6 months; MOA ratification takes additional 3 - 4 months; MOAs sometimes causes need for PCRFs) | If there is no adverse impacts, when concurrence from SHPO is received.If there are adverse impacts, when the MOA is ratified. |  | *This document is a combined effort of History and Archeology sections. The historian and archaeologist will determine responsibility for activities 13473 and 13477 listed below. ; There is some confusion with this step due to its name because the actual 106 survey process is much bigger. A name rec-change may be needed to provide clarity. Project managers are confused by this title which results in them asking the SME confusing questions. Remove certain activities as needed. Activities should be better framed for the type of documents being reviewed or the work being done. Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. |  | Cultural Resources Assessment of Effects (AOE) *The historian and archaeologist will determine responsibility for activities 13473 and 13477 Conduct Section 106 should be reworded to be more specific to completing the AOE, since 106 consultation technically occurs during activity #s 11453/11463 (Conduct History/Arch Survey) as well. • 13473: before the joint AOE (History & Arch) can be started, both Arch and History have to have completed resource ID. There have been instances where one section needed more time (due to project type) so they could not move forward with the activity.• 13473: 120 days could be insufficient if there are a larger number of resources. Also, complex resources take more time. | 6 | Historian |  |  |  |  | N | Historian | 158 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Assessment of Effects (AOE) - Archaeology | 13457 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies | Conduct Section 106 Consultation - Archaeology (with steps) | 16.8.2.5 | Cultural Resource Assessment of Effects (AOE) - Archaeology | 0d | [15 empty] | N |  | 159 | Item | employeecenter/SAM/Lists/SAM
Conduct Section 106 Consultation - Archaeology (with steps) | 13453 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Task Dependent | Receive Preliminary Plans to Begin Technical Studies, Receive Local/Consultant Assessment of Effects (AOE) - Archaeology | Environmental Technical Studies Complete | 16.8.2.5 | Cultural Resource Assessment of Effects (AOE) - Archaeology | 120d | Prepare AOE (& MOA, if needed), GDOT Review of AOE (& MOA), Submit AOE (& MOA) to SHPO, SHPO Review & Concurrence, ACHP Review, MOA Ratification (coordinate with History as needed) | This activity is needed for most in house projects. *The historian and archaeologist will determine responsibility for activities 13473 and 13477. Nepa sends a request for Technical Studies or request for Phase 2 surveys. | 11463, 13473 and 11453 are not needed for maintenance projects. May not be needed If there are no Arch/History resources on the project and Archaeology is preparing a No Potential To Cause Effect document (History preparing a No Historic Properties Affected document). Resource ID and Technical Studies become one phase. (usually maintenance projects) | Technical Studies Summary This activity should start with 13473 (Conduct Section 106 Consultation)…. | If there is no adverse impacts, when concurrence from SHPO is received.If there are adverse impacts, when the MOA is ratified. |  | *This document is a combined effort of History and Archeology sections. The historian and archaeologist will determine responsibility for activities 13473 and 13477 listed below ; There is some confusion with this step due to its name because the actual 106 survey process is much bigger. A name rec-change may be needed to provide clarity. Project managers are confused by this title which results in them asking the SME confusing questions. Remove certain activities as needed.; Activities should be better framed for the type of documents being reviewed or the work being done. Delay the assignment of certain task in P6 until the required documents are received. This ability should be given to managers, it would make reassignments easier. | [8 empty] | N | Archaeologist | 160 | Item | employeecenter/SAM/Lists/SAM
Conduct Air Quality Analysis (with steps) | 13493 | ENVIRONMENTAL SERVICES | Environmental;#5;#Air;#32 | Task Dependent | Management Concept Approval Complete, Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant Air Quality Analysis, Receive Preliminary Plans to Begin Technical Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), Conduct QA of Preliminary Geometry | Environmental Technical Studies Complete | 16.8.4 | Air Quality Analysis | 120d | Conduct Air Analysis Applicable Tasks (4 Steps) -Determine Level of Air Analysis, Run Air Quality Model, Prepare Air Quality Report, GDOT Review of Air Quality Report (Predecessor: Receive Technical Studies Request from NEPA (in-house) Air/Noise P6 Team Member Activity | This activity is needed for state and federally funded projects. | This activity is not needed for most Bridge Replacement or maintenance projects Not needed for projects with AADT 10,000. | When OES has received all items needed to begin Air Assessment.& Items needed include current traffic projections and LOS. | When Air Assessment has been signed as GDOT approved and transmitted to FHWA (as necessary). |  |  |  | Add a “Phase 2 Testing” activity added to the schedule. This would add time to a step and provide flexibility.• If one person is taking too long it delays the AOE for everyone. • The 120 day review period time isn’t ideal; it should be based on individual projects or surveys. It would be nice to adjust or add time after you started.• If the project is more complex then reach out to Project Managers and request more time for reviews; better duration plan from the beginning. • Project managers should look at the schedule beforehand on certain projects based on the number of resources. • Add a check list after the scoping meeting. | 5 | AIr and Noise Specialist |  |  |  |  | N | AIr and Noise Specialist | 161 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Assessment of Effects (AOE) - History | 13477 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Preliminary Plans to Begin Technical Studies | Conduct Section 106 Consultation - History (with steps), Environmental Technical Studies Complete | 16.8.5 | Cultural Resource Assessment of Effects (AOE) - History | 0d | Receive Local/Consultant Assessment of Effects (AOE) Cultural Resources Assessment of Effects (AOE) (120 days Total) *Archeology P6 Team Member Activity | needed for all consultant projects | needed for all non-consultant projects | When the archaeology team member receives the consultant AOE report for review and provides the document to their manager (In-house projects only) Similar additional time needed if MOA required. | When the archaeology team member receives the consultant AOE report for review and provides the document to their manager (In-house projects only) Users clear on when to click finish but concerned that “receive” task does not capture GDOT review time of the document. | [7 empty] | As Late As Possible |  |  | N |  | 162 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Noise Analysis | 13487 | ENVIRONMENTAL SERVICES | Environmental;#5;#Noise;#31 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Preliminary Plans to Begin Technical Studies | Conduct Noise Analysis (with steps), Environmental Technical Studies Complete | 16.8.5 | Noise Analysis | 0d | Receive Local/Consultant Noise Analysis Air/Noise P6 Team Member Activity | This activity is needed for state and federally funded projects. | This activity is not needed for most Bridge Replacement or maintenance projects. Not needed for projects with AADT 10,000. | when OES has received theconsultant document for review/ provided the document to your manager (In-house projects only) | when OES has received theconsultant document for review. | [7 empty] | As Late As Possible |  |  | N |  | 163 | Item | employeecenter/SAM/Lists/SAM
Conduct Agency Consultation for Ecology (with steps) | 13463 | ENVIRONMENTAL SERVICES | Environmental;#5;#Ecology;#2 | Task Dependent | Conduct Ecology Survey (with steps) non-seasonal, Conduct Ecology Survey for Seasonal Species, Conduct Ecology Survey for 3rd Seasonal Species, Conduct QA of Preliminary Geometry, Environmental Resource Identification Complete, Management Concept Approval Complete, Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Receive Local/Consultant Agency Consultation for Ecology, Receive Preliminary Plans to Begin Technical Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (with steps) | Environmental Technical Studies Complete | 16.8.1 | Agency Consultation for Ecology | 120d | Conduct Agency Consultation for Ecology (with steps)Applicable tasks (4 Steps)• Prepare AOER( Assessment of Effects Report), BE, or BA• GDOT Review of AOER, BE, or BA• Submit AOER, BE, or BA to FHWA for 30 - 60 day review• USFWS Review and Concurrence Agency Consultation for Ecology (120 days Total) *Ecology P6 Team Member ActivityAEOR report takes the information found during Resource ID and describes how a project may affect, will likely affect, or won't affect resources including species, water, or sensitive areas For maintenance projects, a a JCP memo is done | needed for all in-house projects | d. 13463= JCP project types need similar activities that correspond with document type because some JCP project types don’t need this activity. | when the Ecologist has received all the required items including Preliminary Plans from Roadway and RCTS from NEPA, to begin preparing the Ecology EAOER The SMEs seem to be confused by this step. Three SMEs gave three different start dates for this activity. | when the AOE is approved and you have received appropriate agency concurrence (when you have received concurrence from USFWS) |  | Does not consider all the surveys that may be required to conduct for this activity. Preliminary Plans are available when you get RCTS from NEPA. |  |  | 4 | Ecologist |  |  |  |  | N | Ecologist | 164 | Item | employeecenter/SAM/Lists/SAM
Technical Studies Summary | 13411 | ENVIRONMENTAL SERVICES | Environmental;#5 | WBS Summary |  |  | 16.8 | Technical Studies | 120d | [10 empty] | n/a |  |  |  |  | N | n/a | 165 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Air Quality Analysis | 13497 | ENVIRONMENTAL SERVICES | Air;#32;#Environmental;#5 | Start Milestone | Receive Environmental Study Area Layout / Start Environmental Studies, Receive Preliminary Plans to Begin Technical Studies | Conduct Air Quality Analysis (with steps), Environmental Technical Studies Complete | 16.8.5 | Air Quality Analysis | 0d | Receive Local/Consultant Air Analysis Air/Noise P6 Team Member Activity | This activity is needed for state and federally funded projects. | This activity is not needed for most Bridge Replacement or maintenance projects. Not needed for projects with AADT 10,000. | When OES has received the consultant document for review. | When OES has received the consultant document for review. | [7 empty] | As Late As Possible |  |  | N |  | 166 | Item | employeecenter/SAM/Lists/SAM
NEPA Document Summary | 14311 | ENVIRONMENTAL SERVICES | Environmental;#5;#NEPA;#45 | WBS Summary |  |  | 16.10 | NEPA Document | 2,018d | [10 empty] | n/a |  |  |  |  | N | n/a | 167 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Draft EA/FONSI | 14327 | ENVIRONMENTAL SERVICES | EA;#35;#Environmental;#5;#FONSI;#48 | Start Milestone | Environmental Resource Identification Complete, Prepare Draft EA (with steps) | FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Review Draft EA, Submit Draft EA | 16.10.1.1 | Receive Local/Consultant NEPA Document (EA only) | 0d | Receive Local/Consultant Draft EA/FONSI part of NEPA Document (150 days total for Draft EA) (0 days) *NEPA P6 Team Member Activity | When the environmental document is doneby consultants. | When the environmental document is done in house. | If the project is consulted out, when the completed document is received from the consultant, If In-House, when the first draft has been provided to Manager for review. | If the project is consulted out, when the completed document is received from the consultant, If In-House, when the first draft has been provided to Manager for review. | [7 empty] | As Late As Possible |  |  | N |  | 168 | Item | employeecenter/SAM/Lists/SAM
Prepare Draft EA (with steps) | 14323 | ENVIRONMENTAL SERVICES | EA;#35;#Environmental;#5 | Task Dependent | Environmental Resource Identification Complete, Preliminary Roadway Plans (consultant design), Receive Preliminary Plans to Begin Technical Studies, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Prepare For and Conduct PHOH (with steps), Receive Local/Consultant Draft EA/FONSI, Review Draft EA, Review Draft Section 4(f), Submit Draft EA | 16.10.1 | Draft EA | 60d | Prepare Draft EA and Review (with steps)Applicable tasks (3 Steps)• Prepare Draft EA• Prepare Draft 4(f) if needed• GDOT Review of Draft EA part of NEPA Document (150 days total for Draft EA) (60 days) *NEPA P6 Team Member Activity |  | When a consultant is doing the environmental document | When work begins on the NEPA Document (Draft EA), starts when technical studies are complete | When Draft EA document is finished |  |  |  |  | 2 | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 169 | Item | employeecenter/SAM/Lists/SAM
Environmental Technical Studies Complete | 13499 | ENVIRONMENTAL SERVICES | Environmental;#5 | Finish Milestone | Conduct Agency Consultation for Ecology (with steps), Conduct Air Quality Analysis (with steps), Conduct Noise Analysis (with steps), Conduct Section 106 Consultation (with steps), Receive Local/Consultant Agency Consultation for Ecology, Receive Local/Consultant Air Quality Analysis, Receive Local/Consultant Assessment of Effects (AOE), Receive Local/Consultant Noise Analysis, Receive Preliminary Plans to Begin Technical Studies | Develop Final EIS, Environmental Approval Complete, Prepare CE, Prepare Environmental Effects Report (EER), Prepare Final EA/FONSI (with steps), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Receive Local/Consultant Final EA/FONSI, Review and Approve Environmental Effects Report (EER), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Submit CE to FHWA, Submit Final EA/FONSI to FHWA | 16.8 | Technical Studies | 0d | [15 empty] | N |  | 170 | Item | employeecenter/SAM/Lists/SAM
Submit Draft EA | 14329 | ENVIRONMENTAL SERVICES | EA;#35;#Environmental;#5 | Finish Milestone | Prepare Draft EA (with steps), Receive Local/Consultant Draft EA/FONSI, Review Draft EA | FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Prepare Final EA/FONSI (with steps), Receive Local/Consultant Final EA/FONSI | 16.10.1.5 | Draft EA | 0d | Submit Draft EA part of NEPA Document (150 days total for Draft EA) (0 days) *NEPA P6 Team Member Activity | for all projects | for all projects | When the document has been submitted to FHWA | When the document has been submitted to FHWA | [7 empty] | As Late As Possible |  |  | N |  | 171 | Item | employeecenter/SAM/Lists/SAM
Review Draft EA | 14328 | ENVIRONMENTAL SERVICES | EA;#35;#Environmental;#5 | Task Dependent | Interchange Modification Report (IMR), Prepare Draft EA (with steps), Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant Draft EA/FONSI | Review Draft Section 4(f), Submit Draft EA | 16.10.1 | Draft EA | 40d | Review Draft EA | part of NEPA Document (150 days total for Draft EA) (30 days) Review Draft EA *NEPA P6 Team Member Activity consultant gets 1 week turnaround on edits, then PM will send the Draft EA to FHWA | always needed, this activity usually takes 1 1/2 months but can take much longer if Draft EA is of poor quality | when the GDOT review period of the document has started. | when the GDOT review period of the NEPA document has been completed | [10 empty] | N |  | 172 | Item | employeecenter/SAM/Lists/SAM
FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps) | 14333 | ENVIRONMENTAL SERVICES | EA;#35;#Environmental;#5;#FHWA;#6 | Task Dependent | Prepare Draft EA (with steps), Receive Local/Consultant Draft EA/FONSI, Submit Draft EA | PFPR Request (OES), PM Request PFPR, Prepare Final EA/FONSI (with steps), Prepare For and Conduct PHOH (with steps), Receive Local/Consultant Final EA/FONSI, Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 16.10.1 | Draft EA | 60d | FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps) part of NEPA Document (150 days total for Draft EA) (60 days) *NEPA P6 Team Member Activity |  |  | When the document has been submitted to FHWA | When the document has been approved by FHWA. |  |  |  |  | 1 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 173 | Item | employeecenter/SAM/Lists/SAM
Public Hearing Held | 14347 | ENVIRONMENTAL SERVICES | Environmental;#5;#PHOH;#33 | Start Milestone | Prepare For and Conduct PHOH (with steps) | Develop Final EIS, Develop, Approve & Publish Notice of Decision (NOD), Prepare CE, Prepare Final EA/FONSI (with steps), Receive Local/Consultant Final EA/FONSI, Respond to PHOH Comments, Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 16.4.26 | Public Hearing Open House (PHOH) | 0d | Public Hearing Held | part of Public Hearing Open House (PHOH) (60 days total) (0 days) *NEPA P6 Team Member Activity |  | when the PHOH has been held. | [11 empty] | N |  | 174 | Item | employeecenter/SAM/Lists/SAM
Review Draft Section 4(f) | 14348 | ENVIRONMENTAL SERVICES | 4f;#34;#Environmental;#5 | Task Dependent | Receive Local/Consultant Draft 4F (for EA), Review Draft EA, Prepare Draft EA (with steps) | Submit Draft EA/4(f) Evaluation to FHWA for Approval | 16.10.1.11 | 4F (In conjunction with EA) | 30d | [15 empty] | N |  | 175 | Item | employeecenter/SAM/Lists/SAM
Prepare For and Conduct PHOH (with steps) | 14343 | ENVIRONMENTAL SERVICES | Environmental;#5;#PHOH;#33 | Task Dependent | Draft Environmental Impact Statement (EIS) Development, FHWA Approval of Draft EIS, FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Prepare Draft EA (with steps), Prepare Environmental Effects Report (EER), Review Local/Consultant Draft EIS, Review and Approve Environmental Effects Report (EER), Submit Draft EIS to FHWA for Approval | Environmental Approval Complete, Public Hearing Held | 16.4.26 | Public Hearing Open House (PHOH) | 30d | Prepare For and Conduct PHOH (with steps)Applicable tasks (5 steps)• Order Signs• Prepare Advertisement• Prepare Handout• Dry Run Held• Confirm Ad Publication | part of Public Hearing Open House (PHOH) (60 days total) Prepare For and Conduct PHOH (with steps) (30days) *NEPA P6 Team Member Activity |  | once the PHOH process has begun. | once the Dry Run has been held. |  |  |  |  | 5 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 176 | Item | employeecenter/SAM/Lists/SAM
Develop Draft Section 4(f) Evaluation | 14345 | ENVIRONMENTAL SERVICES | 4f;#34;#Environmental;#5 | Task Dependent | Receive Preliminary Plans to Begin Technical Studies | Receive Local/Consultant Draft 4F (for EA), Submit Draft EA/4(f) Evaluation to FHWA for Approval | 16.10.1.11 | 4F (In conjunction with EA) | 130d | [15 empty] | N |  | 177 | Item | employeecenter/SAM/Lists/SAM
Respond to PHOH Comments | 14352 | ENVIRONMENTAL SERVICES | Environmental;#5;#PHOH;#33 | Task Dependent | Public Hearing Held | Environmental Approval Complete (If state funds: Env. Activities Complete), Review Final EA/FONSI, Submit CE to FHWA, Submit Final EA/FONSI to FHWA | 16.4.26 | Public Hearing Open House (PHOH) | 30d | Respond to PHOH Comments part of Public Hearing Open House (PHOH) (60 days) (30 days)*NEPA P6 Team Member Activity |  |  | when you begin coordinating with OPD/ Design to draft Response Letter. | when the Response Letter has been mailed to commenters. | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 178 | Item | employeecenter/SAM/Lists/SAM
Review Final EA/FONSI | 14428 | ENVIRONMENTAL SERVICES | EA;#35;#CE;#47;#FONSI;#48;#Environmental;#5 | Task Dependent | Prepare Final EA/FONSI (with steps), Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant Final EA/FONSI, Respond to PHOH Comments | Review Final Section 4(f), Submit Final EA/FONSI to FHWA | 16.10.2 | Final EA | 40d | · Prepare CE or Revised /EA FONSI | part of NEPA Document (CE or Final EA) (30 days - could be longer with consultant review) *NEPA P6 Team Member Activity |  | when the GDOT review period of the document has started. | once the GDOT review period of the NEPA document has been completed. (manager review and approval is complete, before submission to FHWA) | [10 empty] | N |  | 179 | Item | employeecenter/SAM/Lists/SAM
Prepare Final EA/FONSI (with steps) | 14423 | ENVIRONMENTAL SERVICES | EA;#35;#CE;#47;#FONSI;#48;#Environmental;#5 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Draft Section 4(f) Evaluation (previously 15200), Environmental Resource Identification Complete, Environmental Technical Studies Complete, FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), PM Distributes PFPR Responses, Preliminary Roadway Plans (consultant design), Public Hearing Held, Submit Draft EA, Submit Draft EA/4(f) for Legal Review and Revisions (1st), Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), UST/HW Phase I Report Preparation | Submit Final EA/FONSI to FHWA, Review Final EA/FONSI, Review Final Section 4(f), Receive Local/Consultant Final EA/FONSI, FHWA Review and Approval of the Final EA/FONSI (with steps), Develop Final Section 4(f) Evaluation | 16.10.2 | Final EA | 60d | Prepare CE or Revised EA/FONSI (with steps) Applicable tasks (2 Steps) Prepare CE or Revised /EA FONSI OR Consultant Review of CE or Revised EA/ FONSI part of NEPA Document (CE or Final EA) (60 days)*NEPA P6 Team Member Activity |  |  | when work on the NEPA Document (CE or EA/FONSI) begins. | when the document is complete and is ready to be transmitted to FHWA. |  |  |  |  | 2 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 180 | Item | employeecenter/SAM/Lists/SAM
Submit Draft EA/4(f) for Legal Review and Revisions (1st) | 14363 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#Environmental;#5 | Task Dependent | Receive Local/Consultant Draft 4F (for EA), FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Submit Draft EA/4(f) Evaluation to FHWA for Approval | Prepare Final EA/FONSI (with steps), Develop Final Section 4(f) Evaluation, FHWA Review of the Final EA/FONSI (with steps),Draft EA/4(f) Interior Review | 16.10.1.11 | 4F (In conjunction with EA) | 80d | [15 empty] | N |  | 181 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Draft 4F (for EA) | 14357 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#Environmental;#5 | Start Milestone | Develop Draft Section 4(f) Evaluation | Submit Draft EA/4(f) for Legal Review and Revisions (1st), Review Draft Section 4(f), Submit Draft EA/4(f) Evaluation to FHWA for Approval | 16.10.2.2.1 | Receive Local/Consultant 4F (when needed with EA or Reeval) | 0d | Receive Local/Consultant Draft 4F (for EA) | [14 empty] | N |  | 182 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Final EA/FONSI | 14427 | ENVIRONMENTAL SERVICES | EA;#35;#CE;#47;#Environmental;#5 | Start Milestone | Conduct QA of Preliminary Geometry, Environmental Technical Studies Complete, FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Preliminary Roadway Plans (consultant design), Prepare Final EA/FONSI (with steps), Public Hearing Held, Submit Draft EA, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Environmental Approval Complete(If state funds: Env. Activities Complete), FHWA Review of the Final EA/FONSI (with steps), Review Final EA/FONSI, Submit Final EA/FONSI to FHWA | 16.10.2.1 | Receive Local/Consultant NEPA Document (EA) | 0d | Review CE/Review Final EA/FONSI | part of NEPA Document (CE or Final EA Milestone (0 days) *NEPA P6 Team Member Activity | 14527 (Receive local/consultant..)= When project is in-house this activity is not needed (or express in the activity description that this activity should be used to capture the start of manager review when project is in-house). | when the completed document is received from the consultant. | when the completed document is received from the consultant. | [7 empty] | As Late As Possible |  |  | N |  | 183 | Item | employeecenter/SAM/Lists/SAM
Draft EA/4(f) Interior Review | 14373 | ENVIRONMENTAL SERVICES | 4f;#34;#Environmental;#5;#EA;#35 |  | Submit Draft EA/4(f) for Legal Review and Revisions (1st) | Submit Draft EA/4(f) Evaluation to FHWA for Approval |  | 4F (In conjunction with EA) | 40d | [15 empty] | N |  | 184 | Item | employeecenter/SAM/Lists/SAM
FHWA Review and Approval of the Final EA/FONSI (with steps) | 14433 | ENVIRONMENTAL SERVICES | FHWA;#6;#FONSI;#48;#CE;#47;#Environmental;#5;#EA;#35 | Task Dependent | Prepare Final EA/FONSI (with steps), Receive Local/Consultant Final EA/FONSI, Submit Final EA/FONSI to FHWA | Environmental Approval Complete(If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350), Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments, Submit Final EA/4(f) Evaluation to FHWA for Approval | 16.10.2 | Final EA | 60d | * |  |  | when the document has been submitted to FHWA. | when the document has been approved by FHWA. |  |  |  |  | 1 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 185 | Item | employeecenter/SAM/Lists/SAM
Submit Final EA/FONSI to FHWA | 14429 | ENVIRONMENTAL SERVICES | EA;#35;#CE;#47;#FONSI;#48;#Environmental;#5 | Finish Milestone | Environmental Technical Studies Complete, PM Distributes PFPR Responses, Prepare Final EA/FONSI (with steps), Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant Final EA/FONSI, Respond to PHOH Comments, Review Final EA/FONSI | Environmental Approval Complete (If state funds: Env. Activities Complete), FHWA Review of the Final EA/FONSI (with steps) | 16.10.2 | Final EA | 0d | Submit CE or Revised EA/FONSI to FHWA part of NEPA Document (CE or Final EA) (0 days ) Milestone activity *NEPA P6 Team Member Activity |  |  | when the document has been submitted to FHWA. | when the document has been submitted to FHWA. | [10 empty] | N |  | 186 | Item | employeecenter/SAM/Lists/SAM
Develop Final Section 4(f) Evaluation | 14445 | ENVIRONMENTAL SERVICES | 4f;#34;#Environmental;#5 | Task Dependent | Submit Draft EA/4(f) for Legal Review and Revisions (1st), FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Prepare Final EA/FONSI (with steps) | Receive Local/Consultant Final 4F (for EA),Review Final Section 4(f) | 16.10.1.11 | 4F (In conjunction with EA) | 60d | [15 empty] | N |  | 187 | Item | employeecenter/SAM/Lists/SAM
Submit Draft EA/4(f) Evaluation to FHWA for Approval | 14353 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#FHWA;#6;#Environmental;#5 | Task Dependent | FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Develop Draft Section 4(f) Evaluation, Review Draft Section 4(f), Receive Local/Consultant Draft 4F (for EA) | Submit Draft EA/4(f) for Legal Review and Revisions (1st) | 16.10.1.11 | 4F (In conjunction with EA) | 60d | [15 empty] | N |  | 188 | Item | employeecenter/SAM/Lists/SAM
Review Final Section 4(f) | 14448 | ENVIRONMENTAL SERVICES | 4f;#34;#Environmental;#5 | Task Dependent | Review Final EA/FONSI, Develop Final Section 4(f) Evaluation, Prepare Final EA/FONSI (with steps), Receive Local/Consultant Final 4F (for EA) | Submit Final EA/4(f) Evaluation to FHWA for Approval | 16.10.1.11 | 4F (In conjunction with EA) | 30d | [15 empty] | N |  | 189 | Item | employeecenter/SAM/Lists/SAM
Prepare CE | 14523 | ENVIRONMENTAL SERVICES | CE;#47;#Environmental;#5 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Draft Section 4(f) Evaluation (previously 15200), Environmental Resource Identification Complete, Environmental Technical Studies Complete, Preliminary Roadway Plans (consultant design), Public Hearing Held, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), UST/HW Phase I Report Preparation | FHWA Review and Approval of the CE (If 4F: advance to legal review), Receive Local/Consultant CE, Review CE, Review Draft Section 4(f), Submit CE to FHWA | 16.10.3 | CE | 60d |  |  | 14523/14527/1452814529/14533 (Activities related to Env document completion)= Are not needed when the project is state funded and does not require an Env Document. | [7 empty] | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 190 | Item | employeecenter/SAM/Lists/SAM
Final EA/4(f) Interior Review | 14473 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#Environmental;#5 | Task Dependent | Submit Final EA/4(f) for Legal Review and Revisions (2nd) | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.10.1.11 | 4F (In conjunction with EA) | 40d | [15 empty] | N |  | 191 | Item | employeecenter/SAM/Lists/SAM
Review CE | 14528 | ENVIRONMENTAL SERVICES | Environmental;#5;#EA;#35;#CE;#47 | Task Dependent | Prepare CE, Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant CE | FHWA Review and Approval of the CE (If 4F: advance to legal review), Review Draft Section 4(f), Submit CE to FHWA | 16.10.3 | CE | 30d | · Prepare CE or Revised /EA FONSI | part of NEPA Document (CE or Final EA) (30 days - could be longer with consultant review) *NEPA P6 Team Member Activity |  | when the GDOT review period of the document has started. | once the GDOT review period of the NEPA document has been completed. (manager review and approval is complete, before submission to FHWA) | [7 empty] | As Late As Possible |  |  | N |  | 192 | Item | employeecenter/SAM/Lists/SAM
FHWA Review and Approval of the CE (If 4F: advance to legal review) | 14533 | ENVIRONMENTAL SERVICES | 4f;#34;#FHWA;#6;#Environmental;#5;#CE;#47 | Task Dependent | PM Distributes PFPR Responses, Prepare CE, Receive Local/Consultant CE, Review CE, Submit CE to FHWA | 4(f)/CE Legal Review and Revisions, Environmental Approval Complete (If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350), Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments | 16.10.3 | CE | 60d |  |  | 14533/14529 Lower scale projects (PCEs) don’t need submit FHWA activities because they are approved in-house. 14523/14527/1452814529/14533 (Activities related to Env document completion)= Are not needed when the project is state funded and does not require an Env Document. |  |  |  | New activity or additional steps needed= steps or separate activity needed for gathering information and coordinating to prepare response letter. Activity (20 days) is not enough time for the needed coordination and completion of the actual letter. Activity #09312 (20 days) is not enough time for the needed coordination and completion of the actual letter. |  |  |  | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 193 | Item | employeecenter/SAM/Lists/SAM
Submit CE to FHWA | 14529 | ENVIRONMENTAL SERVICES | Environmental;#5;#FHWA;#6;#CE;#47 | Finish Milestone | Environmental Technical Studies Complete, PM Distributes PFPR Responses, Prepare CE, Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant CE, Respond to PHOH Comments, Review CE | Environmental Approval Complete (If state funds: Env. Activities Complete), FHWA Review and Approval of the CE (If 4F: advance to legal review), Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 16.10.3 | CE | 0d |  |  | 14533/14529 Lower scale projects (PCEs) don’t need submit FHWA activities because they are approved in-house.& 14523/14527/14528/14529/14533 (Activities related to Env document completion)= Are not needed when the project is state funded and does not require an Env Document. | [12 empty] | N |  | 194 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Final 4F (for EA) | 14457 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#Environmental;#5 | Start Milestone | Develop Final Section 4(f) Evaluation | Review Final Section 4(f), Submit Final EA/4(f) for Legal Review and Revisions (2nd), Submit Final EA/4(f) Evaluation to FHWA for Approval | 16.10.2.2.1 | Receive Local/Consultant Final 4F (for EA) | 0d | [15 empty] | N |  | 195 | Item | employeecenter/SAM/Lists/SAM
Submit Final EA/4(f) Evaluation to FHWA for Approval | 14453 | ENVIRONMENTAL SERVICES | EA;#35;#FONSI;#48;#CE;#47;#Environmental;#5;#FHWA;#6 | Task Dependent | Draft EA/4(f) Interior Review, Review Final Section 4(f), FHWA Review of the Final EA/FONSI (with steps), Receive Local/Consultant Draft 4F (for EA) | Submit Draft EA/4(f) for Legal Review and Revisions (2nd) | 16.10.2 | 4F (In conjunction with EA) | 60d | FHWA Review of Approval of the CE or Revised EA/FONSI (with steps) Applicable tasks (1 Step)• If Individual 4(f) is needed, add 40 days | part of NEPA Document (CE or Final EA) (60 days *NEPA P6 Team Member Activity |  | when the document has been submitted to FHWA. | when the document has been approved by FHWA. |  |  |  |  | 1 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 196 | Item | employeecenter/SAM/Lists/SAM
Submit Final EA/4(f) for Legal Review and Revisions (2nd) | 14463 | ENVIRONMENTAL SERVICES | 4f;#34;#EA;#35;#Environmental;#5 | Task Dependent | Receive Local/Consultant Draft 4F (for EA), Submit Final EA/4(f) Evaluation to FHWA for Approval | Environmental Approval Complete (If state funds: Env. Activities Complete), Final EA/4(f) Interior Review | 16.10.1.11 | 4F (In conjunction with EA) | 40d | [15 empty] | N |  | 197 | Item | employeecenter/SAM/Lists/SAM
Prepare GEPA Type A Letter | 14612 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, PM Distributes PFPR Responses, Receive Environmental Study Area Layout / Start Environmental Studies, UST/HW Phase I Report Preparation | Environmental Approval Complete(If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Review and Approve GEPA Type A Letter | 16.9.1 | GEPA Type A | 10d | [10 empty] | NEPA Analyst |  |  |  |  | N |  | 198 | Item | employeecenter/SAM/Lists/SAM
Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 14553 | ENVIRONMENTAL SERVICES | 4f;#34;#FHWA;#6;#Environmental;#5;#CE;#47 | Task Dependent | Develop Draft Section 4(f) Evaluation (previously 15200), FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Public Hearing Held, Receive Local/Consultant 4F (for CE or Reeval), Review Draft Section 4(f), Submit CE to FHWA | 4(f)/CE Legal Review and Revisions, Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.10.3.2 | 4F (only when needed in conjunction with CE or Reeval) | 60d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 199 | Item | employeecenter/SAM/Lists/SAM
Develop Draft Section 4(f) Evaluation (previously 15200) | 14543 | ENVIRONMENTAL SERVICES | CE;#47;#4f;#34;#Environmental;#5 | Task Dependent | Environmental Resource Identification Complete, Receive Environmental Study Area Layout / Start Environmental Studies, Receive Preliminary Plans to Begin Technical Studies | Prepare CE, Prepare Final EA/FONSI (with steps), Receive Local/Consultant 4F (for CE or Reeval), Review Local/Consultant Draft EIS, Submit Draft 4(f) Evaluation to FHWA for Approval (with CE or Reeval) (previously 17350), Submit Draft EIS to FHWA for Approval | 16.10.3.2 | 4F (only when needed in conjunction with CE or Reeval) | 130d | [10 empty] | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 200 | Item | employeecenter/SAM/Lists/SAM
Review Draft Section 4(f) | 14548 | ENVIRONMENTAL SERVICES | 4f;#34;#CE;#47;#Environmental;#5 | Task Dependent | Prepare CE, Prepare Draft EA (with steps), Receive Local/Consultant 4F (for CE or Reeval), Review CE, Review Draft EA | Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 16.10.3.2 | 4F (only when needed in conjunction with CE or Reeval) | 30d | [12 empty] | As Late As Possible |  |  | N |  | 201 | Item | employeecenter/SAM/Lists/SAM
Review and Approve GEPA Type A Letter | 14632 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, PM Distributes PFPR Responses, Prepare GEPA Type A Letter, Receive Environmental Study Area Layout / Start Environmental Studies, UST/HW Phase I Report Preparation | Environmental Approval Complete (If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 16.9.1 | GEPA Type A | 5d | [15 empty] | N |  | 202 | Item | employeecenter/SAM/Lists/SAM
EIS Screening Summary | 15700 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | WBS Summary |  |  | 16.10.4.2 | EIS Screening | 630d | [15 empty] | N |  | 203 | Item | employeecenter/SAM/Lists/SAM
Review and Approve GEPA Type B Letter | 14642 | ENVIRONMENTAL SERVICES | GEPA;#36;#Environmental;#5 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, PM Distributes PFPR Responses, Prepare GEPA Type B Letter, Receive Environmental Study Area Layout / Start Environmental Studies, UST/HW Phase I Report Preparation | Environmental Approval Complete (If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 16.9.2 | GEPA Type B | 10d | [10 empty] | NEPA Analyst |  |  |  |  | N |  | 204 | Item | employeecenter/SAM/Lists/SAM
Prepare GEPA Type B Letter | 14622 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, PM Distributes PFPR Responses, Receive Environmental Study Area Layout / Start Environmental Studies, UST/HW Phase I Report Preparation | Environmental Approval Complete (If state funds: Env. Activities Complete), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Review and Approve GEPA Type B Letter | 16.9.2 | GEPA Type B | 10d | [10 empty] | NEPA Analyst |  |  |  |  | N |  | 205 | Item | employeecenter/SAM/Lists/SAM
4(f)/CE Interior Review | 14573 | ENVIRONMENTAL SERVICES | 4f;#34;#CE;#47;#Environmental;#5 | Task Dependent | 4(f)/CE Legal Review and Revisions | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.10.3.2 | 4F (only when needed in conjunction with CE or Reeval) | 40d | [15 empty] | N |  | 206 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant 4F (for CE or Reeval) | 14547 | ENVIRONMENTAL SERVICES | 4f;#34;#CE;#47;#Environmental;#5 | Start Milestone | Develop Draft Section 4(f) Evaluation (previously 15200) | Environmental Approval Complete (If state funds: Env. Activities Complete), Review CE, Review Draft EA, Review Draft Section 4(f), Review Final EA/FONSI, Submit CE to FHWA, Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350), Submit Final EA/FONSI to FHWA | 16.10.3.2.1 | Receive Local/Consultant 4F (when needed with CE or Reeval) | 0d | [12 empty] | As Late As Possible |  |  | N |  | 207 | Item | employeecenter/SAM/Lists/SAM
Review and Approve Environmental Effects Report (EER) | 14662 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, Prepare Environmental Effects Report (EER), UST/HW Phase I Report Preparation | Develop, Approve & Publish Notice of Decision (NOD), PM Request PFPR, Prepare For and Conduct PHOH (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 16.9.3 | GEPA EER | 20d | [10 empty] | n/a |  | As Late As Possible |  |  | N |  | 208 | Item | employeecenter/SAM/Lists/SAM
Develop, Approve & Publish Notice of Decision (NOD) | 14682 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | PM Distributes PFPR Responses, Prepare Environmental Effects Report (EER), Public Hearing Held, Public Information Open House Held, Receive Environmental Study Area Layout / Start Environmental Studies, Review and Approve Environmental Effects Report (EER), UST/HW Phase I Report Preparation | Environmental Approval Complete (If state funds: Env. Activities Complete), Environmental Certification for Let Complete (If state funds: Env. Activities Complete), Environmental Certification for ROW Authorization Complete, L & D Approval, PM Submit L & D Report, ROW Negotiations and Acquisition Work, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 16.9.3 | GEPA EER | 50d | [10 empty] | NEPA Analyst |  |  |  |  | N |  | 209 | Item | employeecenter/SAM/Lists/SAM
4(f)/CE Legal Review and Revisions | 14563 | ENVIRONMENTAL SERVICES | 4f;#34;#CE;#47;#Environmental;#5 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350) | 4(f)/CE Interior Review | 16.10.3.2 | 4F (only when needed in conjunction with CE or Reeval) | 80d | [15 empty] | N |  | 210 | Item | employeecenter/SAM/Lists/SAM
Prepare Environmental Effects Report (EER) | 14652 | ENVIRONMENTAL SERVICES | Environmental;#5;#GEPA;#36 | Task Dependent | Environmental Resource Identification Complete, Environmental Technical Studies Complete, UST/HW Phase I Report Preparation | Develop, Approve & Publish Notice of Decision (NOD), PM Request PFPR, Prepare For and Conduct PHOH (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Review and Approve Environmental Effects Report (EER) | 16.9.3 | GEPA EER | 10d | [10 empty] | NEPA Analyst |  | As Late As Possible |  |  | N |  | 211 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant CE | 14527 | ENVIRONMENTAL SERVICES | CE;#47;#Environmental;#5;#NEPA;#45 | Start Milestone | Prepare CE | Environmental Approval Complete (If state funds: Env. Activities Complete), FHWA Review of CE (If 4F: advance to legal review), Review CE, Submit CE to FHWA | 16.10.3.1 | Receive Local/Consultant NEPA Document (CE) | 0d |  |  | 14527 (Receive local/consultant..)= When project is in-house this activity is not needed (or express in the activity description that this activity should be used to capture the start of manager review when project is in-house). 14523/14527/1452814529/14533 (Activities related to Env document completion)= Are not needed when the project is state funded and does not require an Env Document. 14527 (Receive local/consultant..)= When project is in-house this activity is not needed (or express in the activity description that this activity should be used to capture the start of manager review when project is in-house). | [9 empty] | As Late As Possible |  |  | N |  | 212 | Item | employeecenter/SAM/Lists/SAM
Prepare Scoping and Outreach Materials | 15702 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Notice to Proceed (NTP) for Consultant Contract | GDOT Review of Scoping and Outreach Materials (with steps), Request Public Information Open House (PIOH) | 16.10.4.1 | EIS Scoping | 30d | [15 empty] | N |  | 213 | Item | employeecenter/SAM/Lists/SAM
GDOT Review of Scoping and Outreach Materials (with steps) | 15703 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Prepare Scoping and Outreach Materials | FHWA Review of Scoping and Outreach Materials (with steps), Finalize Scoping and Outreach Materials | 16.10.4.1 | EIS Scoping | 30d | [9 empty] | 3 | [5 empty] | N |  | 214 | Item | employeecenter/SAM/Lists/SAM
FHWA Review of Scoping and Outreach Materials (with steps) | 15706 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | GDOT Review of Scoping and Outreach Materials (with steps) | Finalize Scoping and Outreach Materials | 16.10.4.1 | EIS Scoping | 30d | [9 empty] | 5 | [5 empty] | N |  | 215 | Item | employeecenter/SAM/Lists/SAM
Prepare Screen 1 Analysis/Report | 15712 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Finalize Scoping and Outreach Materials, Request and Receive Traffic Data Volumes | GDOT Review of Screen 1 Analysis/Report (with steps), Request Public Information Open House (PIOH) | 16.10.4.2.1 | Screen 1 | 30d | [15 empty] | N |  | 216 | Item | employeecenter/SAM/Lists/SAM
GDOT Review of Screen 1 Analysis/Report (with steps) | 15713 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Prepare Screen 1 Analysis/Report | FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps) | 16.10.4.2.1 | Screen 1 | 30d | [9 empty] | 3 | [5 empty] | N |  | 217 | Item | employeecenter/SAM/Lists/SAM
FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps) | 15716 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | GDOT Review of Screen 1 Analysis/Report (with steps) | Data Acquisition for Concept (with steps), Define Project Concept, Finalize Screen 1 Report, Prepare Screen 2 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.1 | Screen 1 | 30d | [9 empty] | 5 | [5 empty] | N |  | 218 | Item | employeecenter/SAM/Lists/SAM
Finalize Scoping and Outreach Materials | 15708 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | FHWA Review of Scoping and Outreach Materials (with steps), GDOT Review of Scoping and Outreach Materials (with steps), Respond to PIOH Comments, Scoping Public Information Open House Held (for EIS) | Data Acquisition for Concept (with steps), Define Project Concept, Prepare Screen 1 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.1 | EIS Scoping | 20d | [15 empty] | N |  | 219 | Item | employeecenter/SAM/Lists/SAM
Finalize Screen 1 Report | 15718 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), Respond to PIOH Comments, Screen 1 Public Information Open House Held (for EIS) | Data Acquisition for Concept (with steps), Define Project Concept, Prepare Screen 2 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.1 | Screen 1 | 20d | [15 empty] | N |  | 220 | Item | employeecenter/SAM/Lists/SAM
FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps) | 15726 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | GDOT Review of Screen 2 Analysis/Report (with steps) | Data Acquisition for Concept (with steps), Define Project Concept, Finalize Screen 2 Report, Prepare Screen 3 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.2 | Screen 2 | 30d | [9 empty] | 5 | [5 empty] | N |  | 221 | Item | employeecenter/SAM/Lists/SAM
GDOT Review of Screen 2 Analysis/Report (with steps) | 15723 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Prepare Screen 2 Analysis/Report | FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps) | 16.10.4.2.2 | Screen 2 | 30d | [9 empty] | 3 | [5 empty] | N |  | 222 | Item | employeecenter/SAM/Lists/SAM
Prepare Screen 2 Analysis/Report | 15722 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), Finalize Screen 1 Report, Respond to PIOH Comments, Screen 1 Public Information Open House Held (for EIS) | GDOT Review of Screen 2 Analysis/Report (with steps), Request Public Information Open House (PIOH) | 16.10.4.2.2 | Screen 2 | 30d | [15 empty] | N |  | 223 | Item | employeecenter/SAM/Lists/SAM
Finalize Screen 2 Report | 15728 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), Respond to PIOH Comments, Screen 2 Public Information Open House Held (for EIS) | Data Acquisition for Concept (with steps), Define Project Concept, Prepare Screen 3 Analysis/Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.2 | Screen 2 | 20d | [15 empty] | N |  | 224 | Item | employeecenter/SAM/Lists/SAM
GDOT Review of Screen 3 Analysis/Report (with steps) | 15733 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Prepare Screen 3 Analysis/Report | FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps) | 16.10.4.2.3 | Screen 3 | 30d | [9 empty] | 3 | [5 empty] | N |  | 225 | Item | employeecenter/SAM/Lists/SAM
Prepare Screen 3 Analysis/Report | 15732 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), Finalize Screen 2 Report, Respond to PIOH Comments | GDOT Review of Screen 3 Analysis/Report (with steps), Request Public Information Open House (PIOH) | 16.10.4.2.3 | Screen 3 | 30d | [15 empty] | N |  | 226 | Item | employeecenter/SAM/Lists/SAM
Draft Environmental Impact Statement (EIS) Development | 15800 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Environmental Resource Identification Complete, Preliminary Roadway Plans (consultant design), Receive Environmental Study Area Layout / Start Environmental Studies, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Prepare For and Conduct PHOH (with steps), Review Local/Consultant Draft EIS, Submit Draft EIS to FHWA for Approval | 16.10.4.4 | Draft EIS | 120d | [10 empty] | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 227 | Item | employeecenter/SAM/Lists/SAM
FHWA Develop & Publish Record Of Decision (ROD) | 18110 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Submit Final EIS To FHWA for Approval | Environmental Approval Complete (If state funds: Env. Activities Complete) | 16.10.4.5 | Final EIS | 25d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 228 | Item | employeecenter/SAM/Lists/SAM
Submit Draft EIS to FHWA for Approval | 15875 | ENVIRONMENTAL SERVICES | FHWA;#6;#EIS;#37;#Environmental;#5 | Task Dependent | Develop Draft Section 4(f) Evaluation (previously 15200), Draft Environmental Impact Statement (EIS) Development, Review Local/Consultant Draft EIS | FHWA Approval of Draft EIS, Prepare For and Conduct PHOH (with steps) | 16.10.4.4 | Draft EIS | 60d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 229 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Final EIS & Final 4(f) Evaluation | 17450 | ENVIRONMENTAL SERVICES | 4f;#34;#EIS;#37;#Environmental;#5 | Task Dependent | Develop Final EIS | Submit Final EIS To FHWA for Approval | 16.10.4.5 | Final EIS | 40d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 230 | Item | employeecenter/SAM/Lists/SAM
Finalize Screen 3 Report | 15738 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps), Respond to PIOH Comments, Screen 3 Public Information Open House Held (for EIS) | Data Acquisition for Concept (with steps), Define Project Concept, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.3 | Screen 3 | 20d | [15 empty] | N |  | 231 | Item | employeecenter/SAM/Lists/SAM
Environmental Activities (Prelim. Plans Phase) | 18100 | ENVIRONMENTAL SERVICES | Environmental;#5 | Finish Milestone | 4(f)/CE Interior Review, Conduct Ecology Survey for 3rd Seasonal Species, Develop, Approve & Publish Notice of Decision (NOD), Environmental Document Approval Summary (11412 through 18100), Environmental Resource Identification Complete, Environmental Technical Studies Complete, FHWA Develop & Publish Record Of Decision (ROD), FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Management Revised Concept Approval Complete, Prepare For and Conduct PHOH (with steps), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Public Information Open House Held, Receive Local/Consultant 4F (for CE or Reeval), Receive Local/Consultant CE, Receive Local/Consultant Final EA/FONSI, Respond to PHOH Comments, Respond to PIOH Comments, Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Submit CE to FHWA, Submit Draft 4(f) Evaluation to FHWA for Approval with CE or Reeval) (previously 17350), Subm | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Complete/Submit Environmental Change Form, Environmental Certification for Let Complete, Environmental Certification for ROW Authorization Complete, Final Construction Plans, L & D Approval, Maintenance Project Final Plans Review by OES, OES Receives and Reviews Plans for Application, PM Request FFPR, Prepare Buffer Variance (with steps), ROW Authorization, ROW Plans Final Approval, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Start Final Roadway Plans | 16 | Environmental Activities (Prelim. Plans Phase) | 0d |  |  | 18100 (Env Approval complete) when project is state funded this activity doesn’t mean anything since Technical Studies complete (13499) signifies the completion of Env approval.If the project is state funded, then Activity 18100 stays in the schedule and signifies “Environmental Activities Complete.” This is an activity OPC created to serve as the endpoint of environmental to make schedules work better with logic. | [12 empty] | N |  | 232 | Item | employeecenter/SAM/Lists/SAM
FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps) | 15736 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | GDOT Review of Screen 3 Analysis/Report (with steps) | Data Acquisition for Concept (with steps), Define Project Concept, Finalize Screen 3 Report, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH) | 16.10.4.2.3 | Screen 3 | 30d | [9 empty] | 5 | [5 empty] | N |  | 233 | Item | employeecenter/SAM/Lists/SAM
FHWA Approval of Draft EIS | 15910 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Finish Milestone | Submit Draft EIS to FHWA for Approval | Develop Final EIS, PFPR Request (OES), PM Request PFPR, Prepare For and Conduct PHOH (with steps), ROW Plans Final Approval | 16.10.4.4 | Draft EIS | 0d | [15 empty] | N |  | 234 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Draft EIS | 15870 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Develop Draft Section 4(f) Evaluation (previously 15200), Draft Environmental Impact Statement (EIS) Development | Prepare For and Conduct PHOH (with steps), Submit Draft EIS to FHWA for Approval | 16.10.4.4 | Draft EIS | 60d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 235 | Item | employeecenter/SAM/Lists/SAM
Submit Final EIS To FHWA for Approval | 17500 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5;#FHWA;#6 | Task Dependent | Develop Final EIS, Review Local/Consultant Final EIS & Final 4(f) Evaluation | FHWA Develop & Publish Record Of Decision (ROD) | 16.10.4.5 | Final EIS | 140d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 236 | Item | employeecenter/SAM/Lists/SAM
Develop Final EIS | 17400 | ENVIRONMENTAL SERVICES | EIS;#37;#Environmental;#5 | Task Dependent | Environmental Technical Studies Complete, FHWA Approval of Draft EIS, PM Distributes PFPR Responses, Public Hearing Held, UST/HW Phase I Report Preparation | Review Local/Consultant Final EIS & Final 4(f) Evaluation, Submit Final EIS To FHWA for Approval | 16.10.4.5 | Final EIS | 90d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 237 | Item | employeecenter/SAM/Lists/SAM
Update Ecology Studies | 18414 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5;#ROW;#21 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete | 16.13.1 | Update Environmental Studies for ROW Auth (does not get included for initial schedules) | 40d | Update Ecology Studies | Update Environmental Studies for CST Authorization (20 days Total) *Ecology P6 Team Member Activity |  | when OES has started preparing the Ecology Addendum. When the ecology team member has received the information needed to update ecology studies/prepare the Ecology Addendum closer to LET. | when OES has received concurrence from USFWS. |  | 20d suggestion? Shows 40d on GENESIS template |  |  |  | Ecologist |  |  |  |  | N | Ecologist | 238 | Item | employeecenter/SAM/Lists/SAM
Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 18112 | ENVIRONMENTAL SERVICES | ROW;#21;#Environmental;#5 | Task Dependent | Develop, Approve & Publish Notice of Decision (NOD), Environmental Approval Complete (If state funds: Env. Activities Complete), FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Implementation of ROW Footprint Comments (with steps), PM Distributes PFPR Responses, Prepare Environmental Effects Report (EER), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Review and Approve Environmental Effects Report (EER), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete, Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments | 16.13 | Environmental Certification for ROW Authorization | 5d | Received Revised Plans and Change Form (If changes made as a result of PFPR, circulate to Env. Team) Environmental Certification for ROW Authorization *NEPA P6 Team Member Activity |  |  | When a Project Change Request to Assess Potential Impacts (PCRAPI) form is received from Design/PM. | when the PCRAPI form has been trans- mitted to the SME’s. | [5 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 239 | Item | employeecenter/SAM/Lists/SAM
Update History Studies | 18454 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8;#ROW;#21 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete | 16.13.1 | Update Environmental Studies for ROW Auth (does not get included for initial schedules) | 40d | [10 empty] | Historian |  |  |  |  | N | Historian | 240 | Item | employeecenter/SAM/Lists/SAM
Update Air Quality Analysis | 18494 | ENVIRONMENTAL SERVICES | Air;#32;#Environmental;#5;#ROW;#21 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete | 16.13.1 | Update Environmental Studies for ROW Auth (does not get included for initial schedules) | 40d | [10 empty] | AIr and Noise Specialist |  |  |  |  | N | AIr and Noise Specialist | 241 | Item | employeecenter/SAM/Lists/SAM
Update Archaeology Studies | 18464 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5;#ROW;#21 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete | 16.13.1 | Update Environmental Studies for ROW Auth (does not get included for initial schedules) | 40d | [10 empty] | Archaeologist |  |  |  |  | N | Archaeologist | 242 | Item | employeecenter/SAM/Lists/SAM
Update Noise Assessments | 18484 | ENVIRONMENTAL SERVICES | Environmental;#5;#Noise;#31;#ROW;#21 | Task Dependent | FHWA Review and Approval of the CE (If 4F: advance to legal review), FHWA Review and Approval of the Final EA/FONSI (with steps), Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | Complete Environmental Reevaluation (with steps), Environmental Certification for ROW Authorization Complete | 16.13.1 | Update Environmental Studies for ROW Auth (does not get included for initial schedules) | 40d | [10 empty] | AIr and Noise Specialist |  |  |  |  | N | AIr and Noise Specialist | 243 | Item | employeecenter/SAM/Lists/SAM
Submit Environmental Reevaluation to FHWA | 18527 | ENVIRONMENTAL SERVICES | Environmental;#5;#FHWA;#6;#ROW;#21 | Start Milestone | Complete Environmental Reevaluation (with steps) | Environmental Certification for ROW Authorization Complete, FHWA Approval of Environmental Reevaluation | 16.13.2 | Environmental Reevaluation for ROW Authorization (does not get included for initial schedules) | 0d | [15 empty] | N |  | 244 | Item | employeecenter/SAM/Lists/SAM
Complete Environmental Reevaluation (with steps) | 18523 | ENVIRONMENTAL SERVICES | Environmental;#5;#ROW;#21 | Task Dependent | Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments | Environmental Certification for ROW Authorization Complete, Submit Environmental Reevaluation to FHWA | 16.13.2 | Environmental Reevaluation for ROW Authorization (does not get included for initial schedules) | 30d | [9 empty] | 2 | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 245 | Item | employeecenter/SAM/Lists/SAM
FHWA Approval of Environmental Reevaluation | 18532 | ENVIRONMENTAL SERVICES | Environmental;#5;#FHWA;#6;#ROW;#21 | Task Dependent | Submit Environmental Reevaluation to FHWA | Environmental Certification for ROW Authorization Complete, ROW Authorization | 16.13.2 | Environmental Reevaluation for ROW Authorization (does not get included for initial schedules) | 30d | [10 empty] | NEPA Analyst |  |  |  |  | N | NEPA Analyst | 246 | Item | employeecenter/SAM/Lists/SAM
Receive FFPR Plans & Change Form (if needed); Circulate to Environmental Team | 18712 | ENVIRONMENTAL SERVICES | Environmental;#5;#NEPA;#45 | Task Dependent | Complete/Submit Environmental Change Form, PM Request FFPR | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete, FHWA Approval of Environmental Reevaluation, Submit Environmental Reevaluation to FHWA, Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments and Public Outreach (with steps) | 16.15 | Environmental Certification for CST Authorization | 20d | Received Revised Plans and Change Form (If changes made as a result of PFPR, circulate to Env. Team)Environmental Revaluation and Certification for Let (80-90 days) *NEPA P6 Team Member Activity |  |  | when you receive a Project Change Request to Assess Potential Impacts (PCRAPI) form from Design/PM. | when the PCRAPI form has been transmitted to the SME’s. |  | 18712 (reeval activities) rarely occur within BL dates. Activities are potentially placed too soon in schedule. Perhaps we can pair this activity with Design. (**Are reeval activities placeholder activities?**) EA document: outlines details of project, existing, schedule funding, environmental impacts, public involvement, summary of reports from each environmental EOA, how the NEPA team member came to the decision that this project is the best solution for the problem. CE: includes the same details of EA but for a smaller project like operation, bridge, safety, limited impact. PCE: same but for very minor projects like maintenance, signal upgrades, with no 4f, minimum coordination, no specials, or not adverse effect issues. |  |  |  | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 247 | Item | employeecenter/SAM/Lists/SAM
Submit Environmental Reevaluation to FHWA | 18727 | ENVIRONMENTAL SERVICES | Environmental;#5;#FHWA;#6;#NEPA;#45 | Start Milestone | Complete Environmental Reevaluation for CST Authorization (with steps), Receive Plans & Change Form (if needed); Circulate to Environmental Team | FHWA Approval of Environmental Reevaluation | 16.15.2 | Environmental Reevaluation (delete if state funded) | 0d | Submit Environmental Revaluation to FHWA Environmental Revaluation and Certification for Let (80-90 days) *NEPA P6 Team Member Activity |  |  | when the Environmental Revaluation has been submitted to FHWA | when the Environmental Revaluation has been submitted to FHWA | [7 empty] | As Late As Possible |  |  | N |  | 248 | Item | employeecenter/SAM/Lists/SAM
Complete Environmental Reevaluation for CST Authorization (with steps) | 18723 | ENVIRONMENTAL SERVICES | Environmental;#5;#NEPA;#45 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team, Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments and Public Outreach (with steps) | Environmental Certification for Let Complete, Submit Environmental Reevaluation to FHWA | 16.15.2 | Environmental Reevaluation (delete if state funded) | 20d | Complete Environmental Revaluation for CST Authorization Environmental Revaluation and Certification for Let (80-90 days) *NEPA P6 Team Member Activity |  |  | when you have began preparing the Environmental Revaluation for Let | when the Environmental Revaluation is ready to be submitted to FHWA |  |  |  |  | 2 | n/a |  | As Late As Possible |  |  | N | n/a | 249 | Item | employeecenter/SAM/Lists/SAM
FHWA Approval of Environmental Reevaluation | 18732 | ENVIRONMENTAL SERVICES | Environmental;#5;#FHWA;#6 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team, Submit Environmental Reevaluation to FHWA | Environmental Certification for Let Complete | 16.15.2 | Environmental Reevaluation (delete if state funded) | 20d | FHWA Approval of Revaluation Environmental Revaluation and Certification for Let (80-90 days)&nbsp; *NEPA P6 Team Member Activity |  |  | when you have transmitted the Environmental Revaluation to FHWA for Review; | when the Environmental Revaluation has been approved by the FHWA | [5 empty] | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 250 | Item | employeecenter/SAM/Lists/SAM
Update Ecology Studies | 18814 | ENVIRONMENTAL SERVICES | Ecology;#16;#Environmental;#5 | Task Dependent | OES Receives and Reviews Plans for Application, Receive Plans & Change Form (if needed); Circulate to Environmental Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | Update Ecology Studies&nbsp; Update Environmental Studies for CST Authorization (20 days Total) *Ecology P6 Team Member Activity | when there are changes over time or design changes | when there are no changes | when the ecology team member has received the information needed to update ecology studies/prepare the Ecology addendum closer to LET & when the addendum has been approved by GDOT and Agency concurrence has been provided (as necessary). | when the addendum has been approved by GDOT and Agency concurrence has been provided (as necessary). |  | 18814- 20 days not enough for an addendum (4 months sometimes necessary). 88222= should be connected to 18814 (update ecology); the name of activity 88222 should include a reference to “lockdown plans” for the permit; because that is what the activity is used for. Maybe add 88222, 88233, 88253 altogether and make more steps. But if there is no permit, those activities should not be added together. |  |  |  | Ecologist |  | As Late As Possible |  |  | N | Ecologist | 251 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Update Ecology Studies | 18914 | ENVIRONMENTAL SERVICES | Ecology;#2;#Environmental;#5 | Task Dependent | Receive Updated Plans From Design-Build Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for CST Authorization | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | [10 empty] | Ecologist |  | As Late As Possible |  |  | Y | Ecologist | 252 | Item | employeecenter/SAM/Lists/SAM
Update Archaeology Studies | 18864 | ENVIRONMENTAL SERVICES | Archeology;#30;#Environmental;#5 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | Update Archaeology Studies | This activity can happen at PFPR, FFPR, or at LET before Lockdown Plans. It can happen several times during the life of a project due to a PCRAPPI (project change in or near project). It may be require a memo and some resurvey work. If it is requested near the LET date, the LET date doesn't change. The work has to be rushed. |  | When the archaeology team member receives the information needed to update the Archaeology studies and when they prepare the Archaeology Addendum closer to LET. Users expressed confusion in find the correct addendum in this activity. Users aren’t sure if they should click start since they complete several addendums/updates over the course of the project. | When the Archaeology Addendum has been approved by GDOT and has received concurrence from SHPO. Update Arch/History: users are inclined to wait to click finish until they know there won’t be other addendums because there are generally multiple updates and addendums. Need clarity on which update this task is capturing. |  | SME’s expressed confusion in find the correct addendum in this activity. • 18854: The Update for History Studies activity needs to be revised. SME’s have confusion on inserting information for this activity. • Add a step called “Survey Due to Age”.• Add a “Seasonal Survey” tab • 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days).• Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations).• Proposal for new activity/step: ARPA permit also not accounted for in schedule.• 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days).• Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations).• Proposal for new activity/step: ARPA permit also not accounted for in schedule. |  | there are multiple addendums (updates) so users don’t know which addendum the activity refers to. Requests specifics in the activity name or description on which update should be captured with these activities. • 18854/18864: Users expressed confusion in find the correct addendum in this activity. Users aren’t sure if they should click start since they complete several addendums/updates over the course of the project. |  | Archaeologist |  | As Late As Possible |  |  | N | Archaeologist | 253 | Item | employeecenter/SAM/Lists/SAM
Update History Studies | 18854 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | Update History Studies The historian usually waits until last to enter this documentation into the report done by archeology and history. Sometimes the updated history study is a memo. Update Environmental Studies for CST Authorization (20 days Total) *History P6 Team Member Activity | This additional documentation is needed when there is a change in the project or the project is extended. NEPA works with the project designers to determine the changes to the project and fills out a request form that is sent to the historians and details the changes. 4f and 6f can add time to complex | This activity is not needed unless there is a change in the project or the project is extended. | when the History Team member has received the information needed to update History studies and prepares the History addendum closer to LET. Users expressed confusion in find the correct addendum in this activity. Users aren’t sure if they should click start since they complete several addendums/updates over the course of the project. | when the addendum has been approved by GDOT has received concurrence from SHPO Update Arch/History: users are inclined to wait to click finish until they know there won’t be other addendums because there are generally multiple updates and addendums. Need clarity on which update this task is capturing. |  | SME’s expressed confusion in find the correct addendum in this activity. • 18854: The Update for History Studies activity needs to be revised. SME’s have confusion on inserting information for this activity.• Add a step called “Survey Due to Age”.• Add a “Seasonal Survey” tab. • 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days).• Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations).• Proposal for new activity/step: ARPA permit also not accounted for in schedule.• 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days).• Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations).• Proposal for new activity/step: ARPA permit also not accounted for in schedule.; • 18854/18864Update History studies: Should be revised to designate which update/addendum should be captured for this activity (since multiple addendums are usually completed); Suggested to add the optional activity “resurvey due to age” which will serve as an update activity that gives more time because it accounts for the additional work needed. |  | there are multiple addendums (updates) so users don’t know which addendum the activity refers to.; Requests specifics in the activity name or description on which update should be captured with these activities. The Update for History Studies activity needs to be revised. SME’s have confusion on inserting information for this activity.• Add a step called “Survey Due to Age”.• Add a “Seasonal Survey” tab. |  | Historian |  | As Late As Possible |  | Air and Noise: PM’s use the dates entered into P6 to evaluate whether project activities are on time. • within office: Project Managers are the only ones that really review or ask about my P6 work regularly.• within office: Project Managers don’t have a proper understanding of what we do and how to read activities. 5. How do you think these activities should be evaluated?• Actual durations needed by each user to complete a task can be useful, but ultimately there is a lot of nuance to a project schedule that is lost. outside your office:• Project Managers are evaluating the actual dates to determine where everyone is in the schedule.• Users have no idea how their work is being evaluated• Project Managers are the only ones that really review or ask about my P6 work regularly. Archeology/History: within your office: • No idea, I don’t know.• To determine how often are we meeting Baseline dates• Management comparing actuals to baselines. should be evaluated: • Should be living breathing, ongoing and ability to change schedules.• When having unique circumstances that software won’t account for it should be able to change. Should not be used as punitive.• People should not take schedule at face value because there are so many aggravating circumstances.• Use data to see if certain activities consistently take longer as a means to revamp activity durations, etc. • Use to adjust durations.• Data should be used to look at durations instead start/finish dates since things rarely start on time. | N | Historian | 254 | Item | employeecenter/SAM/Lists/SAM
Update Air Quality Analysis | 18894 | ENVIRONMENTAL SERVICES | Air;#32;#Environmental;#5 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | Update Air Quality Analysis (Predecessor: Receive Project Change Request form from NEPA or complete No Change Memo) Air/Noise P6 Team Member Activity | when there are changes over time or design changes | when there are no changes | when OES has received the information needed to update air quality analysis prior to Let. | when the Air Addendum/Memo has been completed. |  | This activity is often prompted close to LET and 20d is not enough time to complete the activity • Public meeting air quality final report is based on the final project design. 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days). • Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations). • Proposal for new activity/step: ARPA permit also not accounted for in schedule. |  |  |  | AIr and Noise Specialist |  | As Late As Possible |  |  | N | AIr and Noise Specialist | 255 | Item | employeecenter/SAM/Lists/SAM
Update Noise Assessments and Public Outreach (with steps) | 18884 | ENVIRONMENTAL SERVICES | Environmental;#5;#Noise;#31 | Task Dependent | Receive Plans & Change Form (if needed); Circulate to Environmental Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for Let Complete | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | Update Noise Assessments and Public Outreach Applicable Tasks (6 Steps)-Contact Property Owners, Send Surveys to Property owners, Schedule meeting with Property Owners, Receive Surveys from Property Owners, Send Results to Property Owners. (Predecessor: Receive Project Change Request form from NEPA or complete No Change Memo)Air/Noise P6 Team Member Activity | when there are changes over time or design changes | when there are no changes | when you have received the information needed to update noise assessments and conduct public outreach (if necessary) prior to Let. | when the Noise Addendum/Memo has been completed. |  | • Public meeting air and noise final report is based on the final project design. 18854/18864: Sometimes these update activities can actually require SMEs to have to completely resurvey the project (usually due to age). In this case, 20 days will not be enough time to complete the activity (will need at least 120 days).• Proposal for new activity: Arch phase 2 testing currently not accounted for in schedule (6 months additional). Relatively rare (depends on phase 1). Leaves conduct archaeology unfinished (need phase 2 to transmit delineations).• Proposal for new activity/step: ARPA permit also not accounted for in schedule. |  |  | 6 | AIr and Noise Specialist |  | As Late As Possible |  |  | N | AIr and Noise Specialist | 256 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Complete Environmental Reevaluation for CST Authorization (with steps) | 18923 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Receive Updated Plans From Design-Build Team, Update Air Quality Analysis, Update Archaeology Studies, Update Ecology Studies, Update History Studies, Update Noise Assessments and Public Outreach (with steps) | Environmental Certification for CST Authorization, Submit Environmental Reevaluation to FHWA | 16.15.2 | Environmental Reevaluation | 20d | [9 empty] | 2 | n/a |  | As Late As Possible |  |  | Y | n/a | 257 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE FHWA Approval of Environmental Reevaluation | 18932 | ENVIRONMENTAL SERVICES | FHWA;#6;#Environmental;#5 | Task Dependent | Receive Updated Plans From Design-Build Team, Submit Environmental Reevaluation to FHWA | Environmental Certification for CST Authorization | 16.15.2 | Environmental Reevaluation | 20d | [10 empty] | NEPA Analyst |  | As Late As Possible |  |  | Y | NEPA Analyst | 258 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Environmental Reevaluation to FHWA | 18927 | ENVIRONMENTAL SERVICES | Environmental;#5 | Start Milestone | Complete Environmental Reevaluation for CST Authorization (with steps), Receive Updated Plans From Design-Build Team | FHWA Approval of Environmental Reevaluation | 16.15.2 | Environmental Reevaluation | 0d | [12 empty] | As Late As Possible |  |  | Y |  | 259 | Item | employeecenter/SAM/Lists/SAM
Notice to Proceed (NTP) for Consultant Contract | 19229 | PROGRAM DELIVERY | NTP;#3;#PM;#18;#Procurement;#38 | Finish Milestone | Consultant Acquisition (request through notification), PE Funding Authorization | Consultant Kick-Off Meeting, Define Project Concept, Prepare Scoping and Outreach Materials, Receive Environmental Study Area Layout / Start Environmental Studies, Start Database Preparation | 1.2 | Procurement for Scoping (if needed)Procurement | 0d | [15 empty] | N |  | 260 | Item | employeecenter/SAM/Lists/SAM
Consultant Acquisition (request through notification) | 19222 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Task Dependent | PE Funding Authorization, Procurement Requisition Form Submitted by PM | Request Public Information Open House (PIOH), Notice to Proceed (NTP) for Consultant Contract | 1.2 | Procurement for Scoping (if needed) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 261 | Item | employeecenter/SAM/Lists/SAM
Roadway Design Concept Activities LOE (in house design) | 19311 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Level Of Effort | Data Acquisition for Concept (with steps) | Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities | 469d | This is the start milestone for concept development from the old Artemis schedule. | when concept work is being done in house by Roadway Design | When concept is consulted out | after project concept is determined, PE authorized, and project has scheduled | when concept is complete | [5 empty] | n/a |  |  |  |  | N | Roadway Design Engineer | 262 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Update Air Quality Analysis | 18954 | ENVIRONMENTAL SERVICES | Air;#32;#Environmental;#5 | Task Dependent | Receive Updated Plans From Design-Build Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for CST Authorization | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | [10 empty] | AIr and Noise Specialist |  | As Late As Possible |  |  | Y | AIr and Noise Specialist | 263 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Update History Studies | 18984 | ENVIRONMENTAL SERVICES | Environmental;#5;#History;#8 | Task Dependent | Receive Updated Plans From Design-Build Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for CST Authorization | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | [10 empty] | Historian |  | As Late As Possible |  |  | Y | Historian | 264 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Request and Receive Traffic Data Volumes | 19212old | PROGRAM DELIVERY | PM;#18 | Task Dependent | Consultant Kick-Off Meeting, Develop Project Framework Agreement (PFA), PE Funding Authorization, Project Justification (request and receive) | Conduct Air Quality Analysis (with steps), Conduct Evaluation of Alternatives, Conduct Feasability Study, Conduct Noise Analysis (with steps), Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Define Project Concept, Develop Alternatives, Preliminary Design (Design-Build), Preliminary Roadway Plans (consultant design), Prepare Screen 1 Analysis/Report, Start Preliminary Roadway Plans | 1 | Project Initialization | 120d | Activity represents PM requesting Traffic for Office of Planning or if prepared by consultant, Planning approving Traffic Data. Activity 19212 entails furnishing approved design traffic forecasts, including the approval letter, for any GDOT project delivered under the PDP. The design traffic group within the Office of Planning either prepares and delivers the design traffic forecasts to the GDOT PM or reviews and approves the design traffic forecasts (prepared by a consultant) submitted to the Office of Planning by the GDOT PM. Activity 19212 does NOT include tasks related to traffic analysis such as capacity analysis, ICE analysis, traffic impact studies, TE reports, etc., which are under the purview of the Office of Traffic Operations. | Activity 19212 is needed for all GDOT projects delivered under the PDP, with some exceptions. | Projects where design traffic forecasts are not needed for preparing the concept report or developing the construction plans do not require activity 19212. Projects such as sidewalk projects, bridge maintenance projects, ITS projects etc., that do not propose changes to roadway or intersection geometry, could be examples of projects where activity 19212 is not needed. In each of these cases, the GDOT PM makes this determination in consultation with the design traffic SME at the Office of Planning. | Activity 19212 is initiated by the GDOT PM with the completion and submittal of the Traffic Projections/Review Request Form to the Office of Planning. Activities, including PE funding authorization and project justification, should be complete before activity 19212 begins. Additionally, information, such as project scope, project limits, project study area, and a well-defined project alignment, should be made available at the start of activity 19212. | The end date for activity 19212 represents the date when the design traffic forecast activities have been completed, and the GDOT PM receives the approved design traffic forecast, including an approval letter from Office of Planning. |  | The steps required to complete activity 19212 is detailed in the GDOT Design Traffic Forecasting Manual , specifically under Chapter 3. Overview of Design Traffic Forecasting Process. These include: 1) developing a count map; 2) selecting and mobilizing a count vendor to collect, process, and deliver raw traffic counts; 3) preparing the traffic data report, which includes the existing condition traffic diagrams and the forecasting methodology; and 4) preparing the traffic forecasting report and traffic projections for the no-build and build, open year, design year, and +2 year conditions. Several factors could contribute to activity 19212 taking more time to complete than the established activity duration as listed below. Lack of project information, such as project scope, project limits, project study area, and a well-defined project alignment. Initializing activity 19212 when raw traffic counts cannot be collected without delay (e.g. when schools are not in session or during the holiday season)iii. Coordination with adjacent and concurrent projects and their schedules. The size and complexity of the project (i.e. the number of intersections, interchanges, and freeway junctions to be included in the design traffic forecasts) is among the primary factors in determining the duration for activity 19212. The type of project is also a significant factor in determining the duration for activity 19212. For example, the duration to complete this activity for a bridge project is significantly less compared to the time required to complete this activity for an interchange reconstruction project. Additionally, the project area could impact the duration for activity 19212. A project in an area with new proposed developments will require coordination with those developments, so that the design traffic developed for that project takes the trips generated by those developments into consideration. |  | Traffic analysis activities under the purview of the Office of Traffic Operations) and the duration for those activities, should NOT be included under activity 19212. Activities related to traffic analysis should be clearly identified elsewhere within the schedule template to minimize issues related to project schedule adherence. Activity 19212 should be evaluated based on adherence to the schedule established by the GDOT PM in consultation with the design traffic SME at the Office of Planning. Adherence to an established schedule is the primary performance metric for the Office of Planning for this activity. Revisions to this activity are determined by the GDOT PM in consultation with the design traffic SME at the Office of Planning. Delays in overall project delivery, leading to changes in open/design years, as well as changes in the scope of a project, including limits or alignment, could result in revisions to tasks completed under activity 19212. The need for revisions could also be necessitated by comments from FHWA and other GDOT departments during environmental review or other phases of the project. |  | n/a |  |  |  |  | Y |  | 265 | Item | employeecenter/SAM/Lists/SAM
Consultant Kick-Off Meeting | 19232 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Task Dependent | Notice to Proceed (NTP) for Consultant Contract | Define Project Concept, Develop Revised Concept Report, Receive Environmental Study Area Layout / Start Environmental Studies, Start Database Preparation,Define Project Concept (scoping or pre-concept), PAR Checkpoint 1a - Introduce Project to Agencies, | 1.2 | Procurement for Scoping (if needed) | 10d | [10 empty] | n/a |  |  |  |  | N |  | 266 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Update Noise Assessments and Public Outreach (with steps) | 18994 | ENVIRONMENTAL SERVICES | Environmental;#5;#Noise;#31 | Task Dependent | Receive Updated Plans From Design-Build Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for CST Authorization | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | [9 empty] | 6 | AIr and Noise Specialist |  | As Late As Possible |  |  | Y | AIr and Noise Specialist | 267 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Update Archaeology Studies | 18964 | ENVIRONMENTAL SERVICES | Environmental;#5;#Archeology;#30 | Task Dependent | Receive Updated Plans From Design-Build Team | Complete Environmental Reevaluation for CST Authorization (with steps), Environmental Certification for CST Authorization | 16.15.1 | Update Environmental Studies for CST Authorization | 20d | [10 empty] | Archaeologist |  | As Late As Possible |  |  | Y | Archaeologist | 268 | Item | employeecenter/SAM/Lists/SAM
Procurement Requisition Form Submitted by PM | 19217 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Start Milestone | Prepare Procurement Requisition Form | Consultant Acquisition (request through notification) | 1.2 | Procurement for Scoping (if needed) | 0d | [12 empty] | As Late As Possible |  |  | N |  | 269 | Item | employeecenter/SAM/Lists/SAM
Develop Alternatives | 19332 | ROADWAY DESIGN | Roadway;#22;#Concept;#20 | Task Dependent | Create & Submit Environmental Study Area Layout, Data Acquisition for Concept (with steps), Initial Concept Meeting | Conduct Evaluation of Alternatives | 5.2 | Roadway Design Concept Activities | 5d | Develop Alternatives - 19332 This activity consists of developing different alternatives to address the project need and purpose. | this activity is needed for all in house concept projects. | When concept is consulted out | after environmental study area is defined | when projects alternatives are developed |  | An additional activity is needed to request Right of Way, Utility and Environmental Mitigation cost estimates after alternatives are developed. |  | An additional activity is needed to request Right of Way, Utility and Environmental Mitigation cost estimates after alternatives are developed. |  | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 270 | Item | employeecenter/SAM/Lists/SAM
Create & Submit Environmental Study Area Layout | 19322 | ROADWAY DESIGN | Environmental;#5;#Roadway;#22;#Concept;#20 | Task Dependent | Data Acquisition for Concept (with steps), Initial Concept Meeting, PAR Checkpoint 1b - Decide if PAR process will continue | Develop Alternatives, Receive Environmental Study Area Layout / Start Environmental Studies, Receive Layout for UST/HW Phase I | 5.2 | Roadway Design Concept Activities | 5d | Create & Submit Environmental Study Area Layout - 19322 This activity consists of using aerial photography to plot a general box of the boundary that will include all possible alternatives for concept development so that environmental can perform windshield surveys of the project area to identify resources. | this activity is needed for all in house concept projects. | When concept is consulted out | when data acquisition is complete | when Environmental Study Area Layout or ESB - environmental survey boundary is completed and submitted to the office of Environmental Services |  | 19322 is a leading indicator for concept development. |  | leading indicator is an activity that has to start on time so as to not delay another activity. |  | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 271 | Item | employeecenter/SAM/Lists/SAM
Data Acquisition for Concept (with steps) | 19313 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | FHWA Review of Screen 1 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 2 Analysis/Report and CAC/TAC (with steps), FHWA Review of Screen 3 Analysis/Report and CAC/TAC (with steps), Finalize Scoping and Outreach Materials, Finalize Screen 1 Report, Finalize Screen 2 Report, Finalize Screen 3 Report, PAR Checkpoint 1b - Decide if PAR process will continue, PAR Checkpoint 2c - Submit range of alternatives | Concept Meeting, Conduct Evaluation of Alternatives, Create & Submit Environmental Study Area Layout, Develop Alternatives, Finalize Concept Report, PM Request VE Study, Receive Environmental Study Area Layout / Start Environmental Studies, Request Public Information Open House (PIOH), Respond to Concept Report Comments, Roadway Design Concept Activities LOE (in house design), Start Database Preparation, Concept Start to Preliminary Plans Start | 5.2 | Roadway Design Concept Activities | 90d | Data Acquisitions for concept (with steps) -19313 This activity consists of the data gathering necessary to develop a concept report such as requesting traffic diagrams, aerial photography, project justification statements, crash data, etc. | this activity is needed for all in house concept projects. Each project is assigned to a designer and that person does the work from beginning to end | When concept is consulted out | The start date means that PE has been authorized. | when data acquisition is complete |  |  |  |  | 9 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 272 | Item | employeecenter/SAM/Lists/SAM
Conduct Evaluation of Alternatives | 19342 | ROADWAY DESIGN | Roadway;#22;#Concept;#20 | Task Dependent | Data Acquisition for Concept (with steps), Develop Alternatives | Develop Concept Layout of Preferred Alternate (with steps) | 5.2 | Roadway Design Concept Activities | 15d | Conduct evaluation of Alternatives - 19342 This activity consists of reviewing each alternate to determine the best solution to address project need and purpose. This includes reviewing construction costs, right of way, and environmental impacts for each alternate. | this activity is needed for all in house concept projects. | When concept is consulted out | when projects alternatives are developed | when the evaluations of the project alternatives are completed | [5 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 273 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Resource Boundaries (in-house design) | 19349 | ROADWAY DESIGN | Roadway;#22;#Concept;#20 | Finish Milestone | Conduct Archaeological Survey (with steps), Conduct Ecology Survey (with steps) non-seasonal, Environmental Resource Identification Complete, Receive Environmental Study Area Layout / Start Environmental Studies, Conduct History Survey (with steps), PAR Checkpoint 3d - Submit least damaging alternative to design | Concept Report Review and Comments, Develop Concept Layout of Preferred Alternate (with steps), Management Concept Approval Complete, PM Submit Concept Report, Start Preliminary Roadway Plans, Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities | 0d | Receive Environmental Resource Boundaries (in-house design) -19349 : This activity consists of receiving environmental resource boundaries for inclusion in concept layout and evaluation of alternates. | this activity is needed for all in house concept projects. | When concept is consulted out | when projects alternatives are developed | when the evaluations of the project alternatives are completed |  | This activity should be a predecessor to activity 19342. | [8 empty] | N | Roadway Design Engineer | 274 | Item | employeecenter/SAM/Lists/SAM
Finalize Concept Report | 19362 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Concept Meeting, Data Acquisition for Concept (with steps), Submit Draft to PM for Concept Team Meeting | QA Concept Report (with steps), Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities | 10d | Finalize Concept Report -19362 This activity consists of incorporating any comments received during concept team meeting into final concept report. | this activity is needed for all in house concept projects. | When concept is consulted out | The start date means that the concept team meeting has been held. | when the concept layout of the preferred alternative is completed | [5 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 275 | Item | employeecenter/SAM/Lists/SAM
Submit Concept Report to PM | 19379 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Finish Milestone | Finalize Concept Report, QA Concept Report (with steps), Receive Environmental Resource Boundaries (in-house design), Roadway Design Concept Activities LOE (in house design) | PM Reviews Concept Report, Respond to Concept Report Comments | 5.2 | Roadway Design Concept Activities | 0d | Submit Concept Report to PM-19379 This activity consists of submitting the signed concept report to PM for submission for approval. | this activity is needed for all in house concept projects. | When concept is consulted out | The start date means the concept team meeting has been held and the final report is complete. | when the concept layout of the preferred alternative is completed | [9 empty] | This is a performance metric activity within our office that is measured based on baseline finish date. | N | Roadway Design Engineer | 276 | Item | employeecenter/SAM/Lists/SAM
QA Concept Report (with steps) | 19372 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Finalize Concept Report | Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities | 10d | QA concept report (with steps)-19372 This activity consists of review of the final concept report by AOH. | this activity is needed for all in house concept projects. | When concept is consulted out | The start date means the concept team meeting has been held and the final report is complete, but not approved. | when the concept layout of the preferred alternative is completed |  |  |  |  | 4 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 277 | Item | employeecenter/SAM/Lists/SAM
Develop Concept Layout of Preferred Alternate (with steps) | 19352 | ROADWAY DESIGN | Roadway;#22;#Concept;#20 | Task Dependent | Conduct Evaluation of Alternatives, Receive Environmental Resource Boundaries (in-house design) | Conduct Section 106 Consultation - History (with steps), Request Public Information Open House (PIOH), Submit Draft to PM for Concept Team Meeting | 5.2 | Roadway Design Concept Activities | 4d | Develop Concept Layout of Preferred Alternate (with steps) -19352 This activity consists of finalizing concept layout. | this activity is needed for all in house concept projects. | When concept is consulted out | when the evaluations of the project alternatives are completed | when the concept layout of the preferred alternative is completed |  |  |  |  | 6 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 278 | Item | employeecenter/SAM/Lists/SAM
Submit Draft to PM for Concept Team Meeting | 19357 | ROADWAY DESIGN | Concept;#20;#Roadway;#22;#PM;#18 | Start Milestone | Develop Concept Layout of Preferred Alternate (with steps), Respond to PIOH Comments | Concept Meeting, Finalize Concept Report, PM Submit Concept Report | 5.2 | Roadway Design Concept Activities | 0d | Submit Draft to PM for Concept Team Meeting - 19357 This activity consists of submitting a draft report with sufficient details to be reviewed by SMEs at concept team meeting. | this activity is needed for all in house concept projects. | When concept is consulted out | when the evaluations of the project alternatives are completed | when the concept layout of the preferred alternative is completed | [10 empty] | N | Roadway Design Engineer | 279 | Item | employeecenter/SAM/Lists/SAM
Respond to Concept Report Comments | 19382 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Data Acquisition for Concept (with steps), PM Reviews Concept Report, Submit Concept Report to PM | Concept Report Review and Comments, Management Concept Approval Complete, PM Submit Concept Report | 5.2 | Roadway Design Concept Activities | 10d | Respond to Concept Report Comments-19382 This activity consists of responding to review comments received from PM prior to PM submitting final report to Design Policy and Support for review and approval. | this activity is needed for all in house concept projects. | When concept is consulted out | Date signed report is submitted to PM. | Date report is resubmitted to PM after addressing Concept report comments. | [5 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 280 | Item | employeecenter/SAM/Lists/SAM
Data Acquisition for Concept (with steps) | 19413 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | PAR Checkpoint 1b - Decide if PAR process will continue, PAR Checkpoint 2c - Submit range of alternatives,PE Funding Authorization | Desktop Surveys (no review by OES), Finalize Concept Report, Partial Environmental Surveys (OES does not anticipate receiving docs that can be accepted), Conduct Evaluation of Alternatives, Initial Concept Meeting, Concept Start to Preliminary Plans Start, Request Public Information Open House (PIOH), Roadway Design Concept Activities LOE (in house design), Respond to Concept Report Comments, Concept Meeting, Create & Submit Environmental Study Area Layout, Receive Environmental Study Area Layout / Start Environmental Studies, Develop Alternatives | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 90d |  |  | added in for extra time to have steps completed: justification statement, traffic, initial pavement design, aerial photog., crash history … good sense of environmental | [12 empty] | N |  | 281 | Item | employeecenter/SAM/Lists/SAM
Roadway Design Concept Activities LOE (in house design) | 19411 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Level of Effort | Data Acquisition for Scoping or Concept (with steps) | Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 906d |  |  | for all activities under concept. first listed but concurrent | [12 empty] | N |  | 282 | Item | employeecenter/SAM/Lists/SAM
Create & Submit Environmental Study Area Layout | 19422 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | PAR Checkpoint 1b - Decide if PAR process will continue, Initial Concept Meeting,Data Acquisition for Scoping or Concept (with steps) | Desktop Surveys (no review by OES), Partial Environmental Surveys (OES does not anticipate receiving docs that can be accepted), Receive Environmental Study Area Layout / Start Environmental Studies, Develop Alternatives | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 5d | RW creates a boundary that OES uses to identify things in that area; OES responds with report of the things in that boundary |  | environmental survey boundary - good idea of project area - creating boundary and submitting it to Environmental, based on likelihood of impacting area(s) | [12 empty] | N |  | 283 | Item | employeecenter/SAM/Lists/SAM
Develop Alternatives | 19432 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Create & Submit Environmental Study Area Layout, Initial Concept Meeting,Data Acquisition for Scoping or Concept (with steps) | Conduct Evaluation of Alternatives | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 5d |  |  | development of all alternatives that will go in concept report, not just drawings, including layouts if needed, analysis of safety data, and general descriptions of alternatives | [12 empty] | N |  | 284 | Item | employeecenter/SAM/Lists/SAM
Develop Concept Layout of Preferred Alternate (with steps) | 19452 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Conduct Evaluation of Alternatives, Receive Environmental Resource Boundaries (in-house design) | Submit Draft to PM for Concept Team Meeting | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 4d |  |  | This is the development of the layouts. 2D map of alternative, but typical sections are a part; First time you can finalize cost of your preferred alternative. to submit with concept report | [12 empty] | N |  | 285 | Item | employeecenter/SAM/Lists/SAM
Finalize Concept Report | 19462 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Concept Meeting, Data Acquisition for Concept (with steps),Submit Draft to PM for Concept Team Meeting | Submit Concept Report to PM, QA Concept Report (with steps) | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 10d |  |  | this is implementing any comments from concept team meeting and general finalization of final concept report before submitting final concept report | [12 empty] | N |  | 286 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Conduct Peer Review of Feasibility Study | 19522 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Conduct Feasability Study | Develop Concept Layout of Preferred Alternate (with steps), Management Concept Approval Complete, PM Submit Concept Report, Review Local/Consultant Draft Concept for Concept Meeting, Submit Concept Report to PM | 5.3 | Roundabout Feasibility | 15d | [15 empty] | Y |  | 287 | Item | employeecenter/SAM/Lists/SAM
Database Summary | 20000 | DESIGN POLICY & SUPPORT | Survey;#19 | WBS Summary |  |  | 8 | Database Preparation | 131d | Database Summary(includes 50d Mapping and 81d Field survey summary - begins with 20050 and ends with 20650) | This activity is needed once a concept alignment is decided, although sometimes designers want to use the actual survey results to decide on the alignment during concept development phase. | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | Survey database/mapping starts when DPSS receives a request from a PM. Aerial photography should be requested by October 31st each year to plan for winter flying( when trees are bare). | when survey database passes QAQC and no further field survey corrections are needed and when PM receives approved letter from DPSS. There are often additional requests for survey enhancements after completion of the initial survey from the PM for the duration of some projects. Activity duration is affected by weather, topology, cell service access, and the presence of bodies of water which need to be surveyed with sonar. |  | Mapping and Field Survey is needed for most design work. GDOT designers are performing lots of concepts from Bing imagery or global mappers. Typically we don’t do survey on alignments that are not approved because it wastes money when survey work is done and the alignment is changed. Typically if a project is over 1 mile and requires in depth survey, we will do aerial mapping and enhancements. Each task duration depends on project length and width, whether project is rural or urban, and the property owners. Property owners who are against the project can delay survey by not allowing crews on their property for survey. |  |  |  | n/a |  |  |  | Baseline dates in the schedule must be met. Sometimes schedules are changed due to delays | N |  | 288 | Item | employeecenter/SAM/Lists/SAM
Submit Draft to PM for Concept Team Meeting | 19457 | ROADWAY DESIGN | Concept;#20;#PM;#18;#Roadway;#22;#Meeting;#4 | Start Milestone | Develop Concept Layout of Preferred Alternate (with steps), | Finalize Concept Report, PM Submit Concept Report (Scoping), Concept Meeting | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 0d |  |  | Roadway from design group manager reviewed by manager to submit draft to submit to concept team 3 weeks before team meeting | this is submit draft :19479 is final report after concept team meeting | [11 empty] | N |  | 289 | Item | employeecenter/SAM/Lists/SAM
Receive Environmental Resource Boundaries (in-house design) | 19449 | ROADWAY DESIGN | Concept;#20;#Roadway;#22;#Environmental;#5 | Finish Milestone | Conduct Ecology Survey (with steps) non-seasonal, Conduct Archaeological Survey (with steps), Receive Environmental Study Area Layout / Start Environmental Studies, Desktop Surveys (no review by OES), Partial Environmental Surveys (OES does not anticipate receiving docs that can be accepted), Environmental Resource Identification Complete, Conduct History Survey (with steps), PAR Checkpoint 3d - Submit least damaging alternative to design | Develop Concept Layout of Preferred Alternate (with steps), Management Concept Approval Complete, PM Submit Concept Report (Scoping), Submit Concept Report to PM, Concept Report Review and Comments | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 0d |  |  | after environmental surveys, they give roadway the boundaries for historical, plants, in the area that OES was given by Roadway; also archeology - the historians, A&N,take a good look at area without heavy work; archeologists have a heavier load because they have to dig below the ground; They sometimes wait or hang back until after A3M to do most of their work.; 19422 is a large area so they wait for preferred alterative by prelim design. receipt of activity to get resourse boundarites and they look at how the boundary affects alternatives ; leads to looking at a;; the utility, ROW, costs, safety, traffic impacts to minimize impacts | [12 empty] | N |  | 290 | Item | employeecenter/SAM/Lists/SAM
Conduct Evaluation of Alternatives | 19442 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Data Acquisition for Scoping or Concept (with steps), Develop Alternatives | Develop Concept Layout of Preferred Alternate (with steps) | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 15d |  |  | weighing alternatives and choosing preferred alternative based on data analysis | [12 empty] | N |  | 291 | Item | employeecenter/SAM/Lists/SAM
Submit Concept Report to PM | 19479 | ROADWAY DESIGN | Concept;#20;#PM;#18;#Roadway;#22 | Finish Milestone | Roadway Design Concept Activities LOE (in house design), Finalize Concept Report, QA Concept Report (with steps), Receive Environmental Resource Boundaries (in-house design) | Respond to Concept Report Comments, PM Reviews Concept Report | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 0d |  |  | handing final draft to OPD for their review and submission to Design Policy and Support | [12 empty] | N |  | 292 | Item | employeecenter/SAM/Lists/SAM
QA Concept Report (with steps) | 19472 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | Finalize Concept Report | Submit Concept Report to PM | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 10d |  |  | to different review engineer for QA for any final changes before submittal to OPD | [12 empty] | N |  | 293 | Item | employeecenter/SAM/Lists/SAM
Respond to Concept Report Comments | 19482 | ROADWAY DESIGN | Concept;#20;#Roadway;#22 | Task Dependent | PM Reviews Concept Report, Submit Concept Report to PM, Data Acquisition for Scoping or Concept (with steps) | PM Submit Concept Report (Scoping), Management Concept Approval Complete, Concept Report Review and Comments | 5.2 | Roadway Design Concept Activities (Scoping Pre-Concept or Concept) | 10d |  |  | responding to and making revisising concept report based off comments from review and comments from other offices mainly Design Policy and Support | [12 empty] | N |  | 294 | Item | employeecenter/SAM/Lists/SAM
Mapping | 20300 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | Control Surveys | Pre-Survey Field Meeting | 8.1 | Mapping | 15d | Mapping: The actual extraction of data from the aerial photography. Any feature visible from aerial is collected , digitized, and stored.(part of 50d Mapping activity) | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | After extraction of data from the aerial photography | After the aerial photography is complete and approved. |  | http://www.dot.ga.gov/PS/DesignManuals/DesignGuides |  |  |  | n/a |  |  |  |  | N |  | 295 | Item | employeecenter/SAM/Lists/SAM
SDE Process Work | 20600 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | Field Surveys | Database Complete, Review Local/Consultant Field Surveys | 8.2 | Field Surveys | 20d | SDE Process Work: Computer work to process the survey data, correct spikes, crossing, improper codes, clean edges, dtm. Perform property resolution using deeds, plats, field evidence, ROW plans. | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | After initial field surveys are completed | after computer work to process the survey data is completed |  | DESIGN POLICY & SUPPORT/DISTRICT OFFICE |  |  |  | n/a |  |  |  |  | N |  | 296 | Item | employeecenter/SAM/Lists/SAM
Control Surveys | 20200 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | Mapping Photography, Start Database Preparation | Database Complete, Mapping, Pre-Survey Field Meeting | 8.1 | Mapping | 20d | Control Surveys: Activity includes sending crews to field to run traverses, digital levels, collect photo points to bridge photography.(part of 50d Mapping activity) | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | Survey database/mapping starts when DPSS receives a request from a PM. | After extraction of data from the aerial photography |  | http://www.dot.ga.gov/PS/DesignManuals/DesignGuides |  |  |  | n/a |  |  |  |  | N |  | 297 | Item | employeecenter/SAM/Lists/SAM
Field Surveys | 20500 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | Pre-Survey Field Meeting | Database Complete, SDE Process Work | 8.2 | Field Surveys | 20d | Field surveys to enhance the mapping. Includes obscure areas, storm drainage, property, alignments of existing roadways, pavement, dtm - anything not on the mapping but inside the limits. | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | After the pre-survey field meeting set up by DPSS. | After initial field surveys are completed |  | DESIGN POLICY & SUPPORTDISTRICT OFFICE |  |  |  | n/a |  |  |  |  | N |  | 298 | Item | employeecenter/SAM/Lists/SAM
Mapping Photography | 20100 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | Start Database Preparation | Control Surveys | 8.1 | Mapping | 15d | Mapping Photography: Mobilize airplane to take aerial photography/lidar of entire project. Ground work is needed for lidar control.This activity is only done January - March 30th in winter - leaf off season.(part of 50d Mapping activity) | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | Survey database/mapping starts when DPSS receives a request from a PM. | Survey database/mapping starts when DPSS receives a request from a PM. |  | http://www.dot.ga.gov/PS/DesignManuals/DesignGuides |  |  |  | n/a |  |  |  |  | N |  | 299 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Conduct Feasability Study | 19512 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Data Acquisition for Concept (with steps), Define Project Concept, Develop Alternatives, Request and Receive Traffic Data Volumes | Conduct Peer Review of Feasibility Study | 5.3 | Roundabout Feasibility | 20d | [15 empty] | Y |  | 300 | Item | employeecenter/SAM/Lists/SAM
Start Database Preparation | 20050 | DESIGN POLICY & SUPPORT | Survey;#19 | Start Milestone | PAR Checkpoint 3d - Submit least damaging alternative to design, Concept Meeting, Consultant Kick-Off Meeting, Data Acquisition for Concept (with steps), Define Project Concept, Initial Concept Meeting, Management Concept Approval Complete, Notice to Proceed (NTP) for Consultant Contract, Review Local/Consultant Draft Concept for Concept Meeting, Management Concept Approval Complete | Control Surveys, Database Complete, Mapping Photography, Pre-Survey Field Meeting | 8 | Database Preparation | 0d | Start of database summary activity | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | Survey database/mapping starts when DPSS receives a request from a PM. | Survey database/mapping starts when DPSS receives a request from a PM. | [10 empty] | N |  | 301 | Item | employeecenter/SAM/Lists/SAM
Database Complete | 20650 | DESIGN POLICY & SUPPORT | Survey;#19 | Finish Milestone | Control Surveys, Field Surveys, Review Local/Consultant Field Surveys, SDE Process Work, Start Database Preparation | Bridge Hydraulic Study and Layout Development (over stream), Preliminary Bridge Layout Development (non-stream), Preliminary Roadway Plans (consultant design), Request Preliminary Bridge Layout, Request/Receive Utilities First Submission, Start Preliminary Roadway Plans, SUE Coordination (delete if no SUE) (Pilot testing this activity), | 8 | Database Preparation | 0d | Database Complete: End of database summary activity - The completion date is entered into P6 once the survey database passes QAQC. | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | after QAQC of survey database has been completed and the survey database deemed acceptable. | after QAQC of survey database has been completed and the survey database deemed acceptable. | [10 empty] | N |  | 302 | Item | employeecenter/SAM/Lists/SAM
Field Survey Summary | 20450 | DESIGN POLICY & SUPPORT | Survey;#19 | WBS Summary |  |  | 8.2 | Field Surveys | 81d | Field survey summary activity(starts with 20400 pre-survey 1d Field meeting and ends with 20650 finish milestone) | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | After the pre-survey field meeting set up by DPSS. | After the pre-survey field meeting set up by DPSS. | [5 empty] | n/a |  |  |  |  | N |  | 303 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Field Surveys | 20625 | DESIGN POLICY & SUPPORT | Survey;#19 | Task Dependent | SDE Process Work | Database Complete | 8.2 | Field Surveys | 40d | Review Local/Consultant Field Surveys: Field checks and inroads survey files checks for QAQC performed by SLB office. Usually prioritized by PFPR dates. This is to ensure survey databases performed by consultants are to GDOT standards for accuracy, completeness, and within guidelines for processing and survey. A completion letter is issued to OPD and the PM stating whether or not the database passes or fails QAQC. | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | after computer work to process the survey data is completed | after QAQC of survey database has been completed and the survey database deemed acceptable. | [5 empty] | n/a |  |  |  |  | N |  | 304 | Item | employeecenter/SAM/Lists/SAM
Pre-Survey Field Meeting | 20400 | DESIGN POLICY & SUPPORT | Survey;#19;#Meeting;#4 | Task Dependent | Control Surveys, Mapping, Start Database Preparation | Field Surveys | 8.2 | Field Surveys | 1d | Pre-survey field meeting between surveyors and project designer to discuss any special instruction/limits needed for design. This is usually one day.(part of 81d Field survey summary activity) | needed for most projects | Survey may not be needed on maintenance projects, striping projects, or some sign replacement projects. | After the aerial photography is complete and approved. | After the pre-survey field meeting set up by DPSS. |  | DESIGN POLICY & SUPPORT/DISTRICT OFFICE |  |  |  | n/a |  |  |  |  | N |  | 305 | Item | employeecenter/SAM/Lists/SAM
Preliminary Plans Phase Summary | 20700 | ROADWAY DESIGN | Roadway;#22 | WBS Summary |  |  | 12 | Preliminary Plans | 371d | [10 empty] | Project Manager |  |  |  |  | N |  | 306 | Item | employeecenter/SAM/Lists/SAM
Preliminary Roadway Plans (consultant design) | 20800 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Database Complete, Environmental Resource Identification Complete, Implementation Team Recommendations Approval, Management Concept Approval Complete, Receive Environmental Resource Boundaries (consultant design), PAR Checkpoint 3d - Submit least damaging alternative to design, Consultant Kick-Off Meeting | Conduct Noise Analysis (with steps), Conduct Air Quality Analysis (with steps), Draft Environmental Impact Statement (EIS) Development, Receive and Review PCSR, Conduct Pavement Evaluation, Request Soil Survey/Ex Pvmt Eval, Preliminary Plans Complete, Request/Receive Preliminary Lighting Plans, Prepare Draft EA (with steps), PM Submits PCSR to ODPS, Request/Receive Utilities First Submission Receive Preliminary Plans to Begin Technical Studies, Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS, Request/Receive Constructability Review, | 12.1 | Local and Consultant Design Activities for Preliminary Plans | 120d |  | needed for all consultant design projects - OPD will input | for in-house 23697 | [7 empty] | n/a |  |  |  |  | N |  | 307 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE ITS Development Summary | 20805 | TRAFFIC OPS | ITS;#27 | WBS Summary |  |  | 12.5 | ITS Development | 733d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 308 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN HISTORICAL: NOT IN GENESIS TEMPLATE Draft Special Provisions for ITS | 20810 | TRAFFIC OPS | ITS;#27 | Task Dependent | Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | Develop CMS Clearance Diagrams for ITS | 12.5 | ITS Development | 15d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 309 | Item | employeecenter/SAM/Lists/SAM
SUE Coordination (delete if no SUE) (Pilot testing this activity) | 20892 | UTILITIES | Utilities;#15 | Task Dependent | Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), Procurement for SUE (delete if no SUE) (Pilot testing this activity), Database Complete | Request/Receive Utilities First Submission | UTIL1 | SUE and 1st Submission Utilities | 60d | SUE Coordination (delete if no SUE) (Pilot testing this activity) | [14 empty] | N |  | 310 | Item | employeecenter/SAM/Lists/SAM
Conduct Utility Field Meeting | 20927 | PROGRAM DELIVERY | PM;#18;#Utilities;#15;#Meeting;#4 | Start Milestone | Preliminary Roadway Plans (consultant design), Request/Receive Utilities First Submission, Start Preliminary Roadway Plans | Start Final Roadway Plans, PM Distributes PFPR Responses, Final Construction Plans | 12 | SUE and 1st Submission Utilities | 0d |  | This activity is needed when there are RR active warning device equipment impacted by the project or recommended to be installed by the RR crossing Engineer | [13 empty] | N |  | 311 | Item | employeecenter/SAM/Lists/SAM
Conduct Avoidance and Minimization Measures Meeting (A3M) | 20937 | PROGRAM DELIVERY | A3M;#11;#Roadway;#22;#PM;#18;#Meeting;#4 | Start Milestone | Develop Preliminary Vertical Alignment, PAR Checkpoint 3d - Submit least damaging alternative to design, Environmental Resource Identification Complete, Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans, SHPO and Tribal Review of Phase II Report | Preliminary Plans Complete, Submit Preliminary Plans to GDOT Offices (with steps), Develop Preliminary Cross Sections, Submit Preliminary Plans to GDOT Offices (consultant design), Conduct QA of Preliminary Geometry | 12 | Preliminary Plans | 0d | [15 empty] | N |  | 312 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Develop CMS Clearance Diagrams for ITS | 20830 | TRAFFIC OPS | ITS;#27 | Task Dependent | Draft Special Provisions for ITS | Request/Receive Utilities First Submission/SUE Coordination | 12.5 | ITS Development | 10d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 313 | Item | employeecenter/SAM/Lists/SAM
Procurement for SUE (delete if no SUE) (Pilot testing this activity) | 20882 | UTILITIES | Utilities;#15 | Task Dependent | PE Funding Authorization | SUE Coordination (delete if no SUE) (Pilot testing this activity) | UTIL1 | SUE and 1st Submission Utilities | 60d | [15 empty] | N |  | 314 | Item | employeecenter/SAM/Lists/SAM
Utility and ROW field Meeting (Pilot testing this activity) | 20929 | PROGRAM DELIVERY | PM;#18;#Utilities;#15;#ROW;#21;#Meeting;#4 | Finish Milestone | Request/Receive Utilities First Submission | ROW Plans Preparation | UTIL1 | SUE and 1st Submission Utilities | 0d | [15 empty] | N |  | 315 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Preliminary Lighting Plans | 20940 | PROGRAM DELIVERY | PM;#18;#Lighting;#41;#Meeting;#4 | Task Dependent | Conduct QA of Preliminary Geometry, Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | QA Review of Preliminary Roadway Plans (with steps), Request/Receive Final Lighting Plans, PM Reviews PFPR Package, Preliminary Plans Complete | 12 | Preliminary Plans | 20d | [10 empty] | n/a |  |  |  |  | N |  | 316 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Utilities First Submission | 20900 | PROGRAM DELIVERY | PM;#18;#Utilities;#15 | Task Dependent | Conduct QA of Preliminary Geometry, Database Complete, SUE Coordination (delete if no SUE) (Pilot testing this activity), Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | Conduct Utility Field Meeting, Plot Existing Utility Locations, Preliminary Plans Complete, QA Review of Preliminary Roadway Plans (with steps), PM Reviews PFPR Package, Utility and ROW field Meeting (Pilot testing this activity) | 12 | SUE and 1st Submission Utilities | 60d | Submit plans to utilities RR Safety team who will review and forward to the impacted RR for RR signal design. | For the RR safety team: This activity is needed when there are RR active warning device equipment impacted by the project or recommended to be installed by the RR crossing Engineer |  | Start date is the date Utilities receives the plans | The date we get the Force account plans and estimate back from the RR |  | The number of crossings may affect the time the RR needs to return a complete signal design for the project. RR coordination team waits until FFPR to send plans to the RR. RR safety team needs to coordinate with the design team and the RR as early as first submission to minimize re design and ROW issues. |  |  |  | n/a |  |  |  |  | N |  | 317 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Horizontal Alignment | 21332 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Preliminary Typical Sections, Start Preliminary Roadway Plans | Develop Erosion Control Plans ), Conduct QA Review of Preliminary Roadway Plans (with steps), Place ROW and Easement Requirements, Place ROW and Easement Requirements, First Submission Utilities Plan to PM, Develop Preliminary Vertical Alignment, Develop Roadway Drainage Design, Conduct Constructability Review (with steps), Conduct QA of Preliminary Geometry, Submit Preliminary Plans to GDOT Offices (with steps), Develop Preliminary Cross Sections | 12.2 | Preliminary Roadway Plans | 5d | Develop Preliminary Horizontal Alignment | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 318 | Item | employeecenter/SAM/Lists/SAM
Preliminary Roadway Plans LOE (in house design) | 21311 | ROADWAY DESIGN | Roadway;#22 | Level Of Effort | Start Preliminary Roadway Plans | Submit Preliminary Plans to PM for PFPR | 12.2 | Preliminary Roadway Plans | 215d | usually handoff between 2 activities encompasses the development of Preliminary plans for inhouse design projects | [9 empty] | n/a |  |  |  |  | N |  | 319 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Vertical Alignment | 21342 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Start Preliminary Roadway Plans | Conduct Avoidance and Minimization Measures Meeting (A3M), Conduct Constructability Review (with steps), Conduct QA of Preliminary Geometry, Develop Erosion Control Plans, Develop Preliminary Cross Sections, Develop Roadway Drainage Design, Place ROW and Easement Requirements, Preliminary Roadway Plans Complete, Conduct QA Review of Preliminary Roadway Plans (with steps), Submit Preliminary Plans to GDOT Offices (with steps) | 12.2 | Preliminary Roadway Plans | 5d | Develop Preliminary Vertical Alignment | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 320 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Signing & Marking Plans | 21372 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Develop/Update Construction Cost Estimate, QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 15d | Develop Preliminary Signing & Marking Plans | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 321 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Typical Sections | 21322 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Start Preliminary Roadway Plans | Place ROW and Easement Requirements, Develop Roadway Drainage Design, First Submission Utilities Plan to PM, Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Conduct QA Review of Preliminary Roadway Plans (with steps), Develop Preliminary Horizontal Alignment, Develop Preliminary Vertical Alignment, Conduct Constructability Review (with steps), Submit Preliminary Plans to GDOT Offices (with steps), Develop Erosion Control Plans | 12.2 | Preliminary Roadway Plans | 5d | Develop Preliminary Typical Sections depicting the roadways principle elements in a typical cross section. These are activities required to complete a set of preliminary plans. | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | Concept report has been approved and database is complete. This activity is the start of Preliminary Roadway plans. |  |  | Yes- dependent on the project type and complexity the duration of these activities can vary. |  |  |  | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 322 | Item | employeecenter/SAM/Lists/SAM
First Submission Utilities Plan to PM | 21347 | ROADWAY DESIGN | Roadway;#22;#Utilities;#15 | Start Milestone | Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Start Preliminary Roadway Plans | Preliminary Roadway Plans Complete, Request/Receive Utilities First Submission/SUE Coordination | 12.2 | Preliminary Roadway Plans | 0d | First Submission Utilities Plan to PM | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | when preliminary design is complete. | When Roadway design send prelim. plans to the PM and the Office of Utilities. |  | 21347 is a leading indicator for preliminary design COMPLETE. | [8 empty] | N | Roadway Design Engineer | 323 | Item | employeecenter/SAM/Lists/SAM
Start Preliminary Roadway Plans | 21317 | ROADWAY DESIGN | Roadway;#22 | Start Milestone | PAR Checkpoint 3d - Submit least damaging alternative to design,Database Complete, Environmental Resource Identification Complete, Implementation Team Recommendations Approval, Management Concept Approval Complete, Receive Environmental Resource Boundaries (in-house design), Concept Start to Preliminary Plans Start | Conduct Agency Consultation for Ecology (with steps), Conduct Air Quality Analysis (with steps), Conduct Avoidance and Minimization Measures Meeting (A3M), Conduct Noise Analysis (with steps), Conduct QA of Preliminary Geometry, Conduct Section 106 Consultation - History (with steps), Conduct Utility Field Meeting, Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Develop Roadway Drainage Design, First Submission Utilities Plan to PM, Pavement Design Preparation, Review and Approval, Plot Existing Utility Locations, Preliminary Roadway Plans LOE (in house design), Prepare Draft EA (with steps), Prepare MS4 Design and PCSR; Submit to ODPS, Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS, QA Review of Preliminary Roadway Plans (with steps), Receive Preliminary Plans to Begin Technical Studies, Receive an | 12.2 | Preliminary Roadway Plans | 0d | Start Preliminary Roadway Plans-21317 This is a milestone activity for the beginning of preliminary design. | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | Concept report has been approved and database is complete. | When Preliminary Roadway Plans are started. | [10 empty] | N | Roadway Design Engineer | 324 | Item | employeecenter/SAM/Lists/SAM
Develop Roadway Drainage Design | 21382 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Start Preliminary Roadway Plans | Develop Wall Envelopes, Prepare MS4 Design and PCSR; Submit to ODPS, Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS, QA Review of Preliminary Roadway Plans (with steps), Request/Receive Landscaping Plans | 12.2 | Preliminary Roadway Plans | 5d | Develop Roadway Drainage Design | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 325 | Item | employeecenter/SAM/Lists/SAM
Conduct QA of Preliminary Geometry | 21362 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct Avoidance and Minimization Measures Meeting (A3M), Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Start Preliminary Roadway Plans | Receive Local/Consultant Final EA/FONSI, Develop Roadway Drainage Design, Conduct Section 106 Consultation (with steps), Request/Receive Landscaping Plans, Submit Preliminary Plans to GDOT Offices (with steps), Request/Receive Preliminary Lighting Plans, Develop Staging Plans, Conduct Agency Consultation for Ecology (with steps), Conduct Noise Analysis (with steps), QA Review of Preliminary Roadway Plans (with steps), Develop Preliminary Signing & Marking Plans, Conduct Air Quality Analysis (with steps), Request Soil Survey/Ex Pvmt Eval, Prepare Final EA/FONSI (with steps), , Prepare CE, Request/Receive Utilities First Submission, Develop Staging Cross Sections, Develop Wall Envelopes | 12.2 | Preliminary Roadway Plans | 8d | Conduct QA of Preliminary Geometry | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Quality Assurance |  |  |  |  | N | Roadway Design Engineer | 326 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Cross Sections | 21352 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Start Preliminary Roadway Plans, Conduct Avoidance and Minimization Measures Meeting (A3M), Develop Preliminary Horizontal Alignment | Conduct QA of Preliminary Geometry, Develop Roadway Submit Preliminary Plans to GDOT Offices (with steps), Develop Wall Envelopes, Develop Staging Cross Sections, Develop Staging Plans, QA Review of Preliminary Roadway Plans (with steps), Place ROW and Easement Requirements, Conduct QA of Preliminary Geometry | 12.2 | Preliminary Roadway Plans | 5d | Develop Preliminary Cross Sections | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 327 | Item | employeecenter/SAM/Lists/SAM
Submit Preliminary Plans to GDOT Offices (with steps) | 21397 | ROADWAY DESIGN | Roadway;#22 | Start Milestone | Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Start Preliminary Roadway Plans, Conduct Avoidance and Minimization Measures Meeting (A3M) | SUE Coordination (delete if no SUE) (Pilot testing this activity), Request Preliminary Bridge Layout, Prepare CE, Draft Environmental Impact Statement (EIS) Development, Receive Preliminary Plans to Begin Technical Studies, Conduct Pavement Evaluation, Conduct Agency Consultation for Ecology (with steps), Conduct Air Quality Analysis (with steps), Prepare Draft EA (with steps), QA Review of Preliminary Roadway Plans (with steps), Prepare Final EA/FONSI (with steps), Conduct Section 106 Consultation (with steps), Preliminary Bridge Layout Development (non-stream), Bridge Hydraulic Study and Layout Development (over stream), Conduct Pavement Type Selection Report, Receive Local/Consultant Final EA/FONSI, Develop Preliminary Signing & Marking Plans, Request/Receive Preliminary Lighting Plans, Conduct Noise Analysis (with steps), Receive Layout for UST/HW Phase II | 12.2 | Preliminary Roadway Plans | 0d | Submit Preliminary Plans to GDOT Offices (with steps) | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | when preliminary plans are completed. | when Roadway Design sends preliminary plans to GDOT Offices |  | 21397 is a leading indicator for preliminary design COMPLETE. |  |  | 4 | [5 empty] | N | Roadway Design Engineer | 328 | Item | employeecenter/SAM/Lists/SAM
Submit Preliminary Plans to Utilities for Impacted Railroads | 21500 | PROGRAM DELIVERY | PM;#18;#Railroad;#42;#Utilities;#15 | Task Dependent | PM Distributes PFPR Responses, Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans, Submit 1st Submission RR Package to PM | Final Construction Plans Complete, PM Request FFPR, Submit Final Plans to Utilities for Impacted RR | 13 | Railroad Activities (if needed) | 248d | Develop Wall Envelopes - Approximately 3 months after PFPR, using the Railroad Submission Checklist found on the Utilities website, the PM and Design team put together the Preliminary Railroad Submission Package. This Preliminary Railroad Submission Package which includes a cover letter, a location sketch, an electronic pdf of the plans, and a half size set Plan set is then sent to the Office of Utilities, who will review for completeness and then send it on to the appropriate railroad company for their review/approval. The PM is to submit the package to the Utilities office attention Railroad Liaison, currently Jill Franks, and Railroad Specialist, currently Marcela Coll. If the railroad has comments on the Preliminary Railroad Submission Package (which is nearly 100% of the time) then the PM and Design team review the railroad comments and revise their plans to address the comment(s). The PM and Design team also need to respond to the railroad’s comments in a written format explaining how they address the comment(s) or explain why they were unable to fulfill the railroad’s request. The Revised Preliminary plans along with the written responses are then put together in the REVISED Preliminary Railroad Submission Package, following the Railroad Submission Checklist found on the Utilities website and sent to the Office of Utilities, who will review for completeness and then send it on to the appropriate railroad company for their review/approval. This process is repeated until the Railroad has approved the Preliminary plan package. The next time plans need to be submitted would be when FFPR is requested. | This activity is needed for every project that required Railroad Coordination, which is determined by the Utilities Office. | This activity is not needed when the Office of Utilities deems railroad impacts do not exist. | The start date represent the date the Preliminary Railroad Submission Package is submitted to the Office of Utilities by the PM. | The end date represents the day the Railroad sends the Preliminary plans approval email/letter to the office of Utilities. |  | If a project has any length of railroad track design, the duration of the activity should be lengthen from 248 days (one year) to 496 days (two years). When our office submits the railroad’s comment to the PM & Designer, a date is given to submit the next revised submission package. This should be followed as closely as possible to ensure the project meets the let date. The railroads are very particular on the design of their railroad tracks and it generally takes two full years to get the railroad to approve the track design, especially with Norfolk Southern. This is why if there is track design we request two years for this activity. *Railroad Coordination Process-Concept phase: Determine if RR coordination is needed and include our Cost estimate-Preliminary phase: Submit plans after PFPR-Final phase: Submit plans at FFPR request or 28 weeks before letting-Construction: Construction revisions go through District Construction-Agreements: PM to ensure PE funds are available *Spec. Prov. for Protection of Railway Interest-Written by us and required on every project with RR impacts-PM to include in the PS&E package |  |  |  | n/a |  |  |  | We are tracking metrics to see if we are either sending comments back to the PM/Designer or sending out the Railroad Submission Package within 7 calendar days and the railroad is reviewing the submission package within 60 calendar days. We should be evaluated using the current method explained above. | N |  | 329 | Item | employeecenter/SAM/Lists/SAM
Develop Wall Envelopes | 21512 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Develop Roadway Drainage Design | Develop Staging Plans, Final Bridge Plans Preparation, QA Review of Preliminary Roadway Plans (with steps), Request BFI | 12.2 | Preliminary Roadway Plans | 5d | Develop Wall Envelopes | This activity is needed for most in house design projects. | When preliminary roadway plans are not needed or when the design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 330 | Item | employeecenter/SAM/Lists/SAM
Develop Staging Plans | 21522 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Develop Wall Envelopes, Prepare MS4 Design and PCSR; Submit to ODPS | Develop Staging Cross Sections, QA Review of Preliminary Roadway Plans (with steps), Request/Receive Landscaping Plans | 12.2 | Preliminary Roadway Plans | 10d | Develop Staging Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 331 | Item | employeecenter/SAM/Lists/SAM
Submit 1st Submission RR Package to PM | 21517 | ROADWAY DESIGN | Roadway;#22;#Railroad;#42;#PM;#18 | Start Milestone | PM Distributes PFPR Responses | Start Final Roadway Plans, Submit Preliminary Plans to Utilities for Impacted Railroads | 12.2 | Preliminary Roadway Plans | 0d | Submit 1st Submission RR Package to PM-21517 | [5 empty] | This activity should be deleted. It does not coincide with PDP or railroad submittal checklist. It occurs too early in the preliminary design phase. | [8 empty] | N | Roadway Design Engineer | 332 | Item | employeecenter/SAM/Lists/SAM
Plot Existing Utility Locations | 21542 | ROADWAY DESIGN | Roadway;#22;#Utilities;#15 | Task Dependent | Request/Receive Utilities First Submission, Start Preliminary Roadway Plans | QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 5d | Plot Existing Utility Locations | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 333 | Item | employeecenter/SAM/Lists/SAM
Develop Staging Cross Sections | 21532 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Develop Staging Plans | Conduct Constructability Review (with steps), Develop Erosion Control Plans | 12.2 | Preliminary Roadway Plans | 15d | Develop Staging Cross Sections | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 334 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Constructability Review | 21550 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | PM Reviews PFPR Package, Preliminary Plans Complete | 12.1 | Local and Consultant Design Activities for Preliminary Plans | 20d | Request/Receive Constructability Review | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | n/a |  |  |  |  | N | Roadway Design Engineer | 335 | Item | employeecenter/SAM/Lists/SAM
Conduct Constructability Review (with steps) | 21553 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Develop Staging Cross Sections | Develop Erosion Control Plans, QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 20d | Conduct Constructability Review (with steps) | This activity is needed for all in house design projects. | When design is consulted out. | [6 empty] | 3 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 336 | Item | employeecenter/SAM/Lists/SAM
Place ROW and Easement Requirements | 21572 | ROADWAY DESIGN | Roadway;#22;#ROW;#21 | Task Dependent | Develop Erosion Control Plans, Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment | Develop/Update Construction Cost Estimate, QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 10d | Place ROW and Easement Requirements | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 337 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Landscaping Plans | 21582 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct QA of Preliminary Geometry, Develop Erosion Control Plans, Develop Roadway Drainage Design, Develop Staging Plans | QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 30d | Request/Receive Landscaping Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer Group Manager |  |  |  |  | N | Roadway Design Engineer | 338 | Item | employeecenter/SAM/Lists/SAM
Develop Erosion Control Plans | 21562 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Conduct Constructability Review (with steps), Develop Preliminary Horizontal Alignment, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Develop Staging Cross Sections | Develop/Update Construction Cost Estimate, Place ROW and Easement Requirements, QA Review of Preliminary Roadway Plans (with steps), Request/Receive Landscaping Plans | 12.2 | Preliminary Roadway Plans | 10d | Develop Erosion Control Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 339 | Item | employeecenter/SAM/Lists/SAM
QA Review of Preliminary Roadway Plans (with steps) | 21713 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Start Preliminary Roadway Plans, Request/Receive Preliminary Lighting Plans, Conduct Pavement Evaluation, Develop Preliminary Vertical Alignment, Place ROW and Easement Requirements, Develop Preliminary Typical Sections, Request/Receive Utilities First Submission, Develop Roadway Drainage Design, Develop Preliminary Horizontal Alignment, Develop Erosion Control Plans, Develop Staging Plans, Develop/Update Construction Cost Estimate, Develop Preliminary Pavement Design, Plot Existing Utility Locations, Conduct Constructability Review (with steps), Develop Preliminary Signing & Marking Plans, Submit Preliminary Plans to GDOT Offices (with steps), Submit Pavement Design to OMAT for Approval, Request/Receive Landscaping Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Conduct QA of Preliminary Geometry, Develop Preliminary Cross Sections, Submit Pavement Evaluation to PM for PFPR, Develop Wall Envelopes | PM Reviews PFPR Package, Submit Preliminary Plans to PM for PFPR | 12.2 | Preliminary Roadway Plans | 5d | QA Review of Preliminary Roadway Plans (with steps) | This activity is needed for all in house design projects. | When design is consulted out. | Plans are ready for QA review. | [5 empty] | 4 | Roadway Design Quality Assurance |  |  |  |  | N | Roadway Design Engineer | 340 | Item | employeecenter/SAM/Lists/SAM
Develop/Update Construction Cost Estimate | 21592 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Erosion Control Plans, Develop Preliminary Signing & Marking Plans, Place ROW and Easement Requirements | QA Review of Preliminary Roadway Plans (with steps) | 12.2 | Preliminary Roadway Plans | 5d | Develop/Update Construction Cost Estimate | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 341 | Item | employeecenter/SAM/Lists/SAM
Submit Preliminary Plans to PM for PFPR | 21717 | ROADWAY DESIGN | PM;#18 | Finish Milestone | QA Review of Preliminary Roadway Plans (with steps),Preliminary Bridge Layout Development (non-stream), Bridge Hydraulic Study and Layout Development (over stream), Preliminary Roadway Plans LOE (in house design) | PM Reviews PFPR Package, Preliminary Plans Complete |  | Preliminary Roadway Plans | 0d | [15 empty] | N |  | 342 | Item | employeecenter/SAM/Lists/SAM
CONDUCT Pavement Evaluation | 21722 | OMAT | Pavement;#14 | Task Dependent | Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (with steps), Submit Preliminary Plans to GDOT Offices (consultant design), Start Preliminary Roadway Plans | QA Review of Preliminary Roadway Plans (with steps), Submit Pavement Evaluation, Conduct Pavement Type Selection Report | 12.2.1 | Pavement Evaluation | 120d | This is when we conduct the pavement evaluation.&nbsp; It contains historic plans research, field work, coring, testing, analysis and report generation Pavement Evaluation Summary (PES): Survey of the existing pavement structure to determine if the pavement can be retained for a project. | Per Chapter 6 of the PDP 6.3.4: For non-linear projects like intersection improvements, bridge replacements, etc. and for linear projects in rural environments, a PES report should be requested where a length of continuous overlay exeeds 2,500 ft. For linear projects in urban environments, a PES report should be requested where a length of continuous overlay exeeds 1,000 ft. | where previous guidelines are not met | The start date should be when the request is received to perform the pavement evaluation. Traffic must be complete. The preliminary design must have started and the horizontal and vertical alignment should be set. PM makes the request. | The end date represents the Pavement Evaluation Report being generated and sent to PM PES: When the report is issued by OMAT when performed internally. |  | PES: Generally 6 months but could be quicker if done by consultant due to limited field staff and traffic control for internal GDOT project work. Need review time of about 30-45 days for approval of consultant reports. Usually reports to back to consultant at least once so either resubmittal activity code or on average the review duration should be doubled to 60 days to cover the back and forth to consultants. The longer the project the more time it would generally take to do the field work and testing. We generally take a sample per lane mile so as the number of lanes and distance of the project increases so does our field work and testing. This activity is needed for PFPR. PES: The field work and report would be much more difficult on large widening jobs, like multi-mile corridors. OMAT must do PES for all interstate maintenance projects. | PDP 6.3.4 |  |  | Roadway Design Engineer Group Manager |  |  |  | This is a performance metric activity within our office that is measured based on baseline finish date. | N |  | 343 | Item | employeecenter/SAM/Lists/SAM
Review Pavement Evaluation | 21734 | OMAT | Pavement;#14 | Task Dependent | Submit Pavement Evaluation | Transmit Pavement Evaluation to PM for PFPR | 12.6.2 | Pavement Evaluation | 40d | Pavement Evaluation is reviewed by OMAT | When 21722 (CONDUCT Pavement Evaluation) is used | When 21722 (CONDUCT Pavement Evaluation) is not used | Day Pavement Evauation review starts | Day Pavement Evaluation review is completed | [5 empty] | n/a |  |  |  |  | N |  | 344 | Item | employeecenter/SAM/Lists/SAM
Transmit Pavement Evaluation to PM for PFPR | 21739 | OMAT | Pavement;#14;#PM;#18 | Finish Milestone | Review Pavement Evaluation | PM Reviews PFPR Package, QA Review of Preliminary Roadway Plans (with steps) | 12.6.2 | Pavement Evaluation | 0d | Zero day duration to document sending the Approved Pavement Evaluation to the PM | When 21722 (CONDUCT Pavement Evaluation) is used | When 21722 (CONDUCT Pavement Evaluation) is not used | Day the Pavement Evaluation is sent | Day the Pavement Evaluation is sent |  | Rated on 21722 (CONDUCT Pavement Evaluation), not this activity. | PDP 6.3.4 | [7 empty] | N |  | 345 | Item | employeecenter/SAM/Lists/SAM
Submit Pavement Design TO OMAT for Approval | 21759 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Preliminary Pavement Design | Submit Pavement Type Selection, QA Review of Preliminary Roadway Plans (with steps), Review Pavement Design | 12.2.1 | Pavement Design (Roadway Design) | 0d | Roadway sends Pavement Design Package to OMAT | When 81600 is used and project is in-house Design | When 81600 is not used or if design is done by consultant. | Date the package is sent from Roadway to OMAT | Package received | [5 empty] | Roadway Design Engineer Group Manager |  |  |  |  | N | Roadway Design Engineer | 346 | Item | employeecenter/SAM/Lists/SAM
SUBMIT Pavement Evaluation | 21729 | OMAT | Pavement;#14 | Finish Milestone | Conduct Pavement Evaluation | Review Pavement Evaluation | 12.6.2 | Pavement Evaluation | 0d | Zero day duration activity to document the sending of the Pavement Evaluation for review | When 21722 (CONDUCT Pavement Evaluation) is used | When 21722 (CONDUCT Pavement Evaluation) is not used | Day the Pavement Evaluation is submitted | Day pavement evaluation is received from consultant. |  | Rated on 21722 (CONDUCT Pavement Evaluation), not this activity. | PDP 6.3.4 | [7 empty] | N |  | 347 | Item | employeecenter/SAM/Lists/SAM
Submit Pavement Type selection | 21777 | OMAT | Pavement;#14 | Start Milestone | Submit Pavement Design TO OMAT for Approval, PM submits Pavement Design to OMAT for approval, Conduct Pavement Type Selection Report | Review Pavement Type Selection, PM Request PFPR, PM Reviews PFPR Package | 12.6.10 | Pavement Type Selection | 0d | This report that uses project information and calculations to decide what pavement type a project should use. | for new location projects or projects where road must be completely reconstructed | for projects constructed within the limits of existing roadway. | The start date should be when the request is received to perform the pavement type selection. | The end date represents the Pavement type selection being generated and sent to PM |  | Rated on 21772 (Prepare Pavement type selection report), not this activity. | [8 empty] | N |  | 348 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE prepare Pavement type selection report | 21772 | OMAT | Pavement;#14 | Task Dependent |  |  |  | Pavement Type Selection | 60d | Pavement Type Selection (PTS): Life Cycle Cost Analysis and other factors used to determine the final pavement type - asphalt or concrete used for new location and/or areas where existing pavement is not suitable for overlay. | for new location projects or projects where road must be completely redone (mill and inlay) | for projects constructed within the limits of existing roadway. | Pavement Type Selection (PTS):The start date should be when the request is received to perform the pavement type selection. | PTS: When the report is either issued by OMAT when performed internally or approved by OMAT if done by a consultant. Roadway Design sometimes requests PTS. |  | PTS: Generally 3 months. Need review time of about 30-45 days for approval of consultant reports. Usually reports to back to consultant at least once so either resubmittal activity code or on average the review duration should be doubled to 60 days to cover the back and forth to consultants.; The longer the project the more time it would generally take to do the field work and testing. We generally take a sample per lane mile so as the number of lanes and distance of the project increases so does our field work and testing. This activity is needed for PFPR. The PTS can start at the same time when a PES would start for projects that are on new location where a PTS is warranted. Sometimes a PTS would not start until after the PES is completed when it is discovered in the PES that the pavement cannot be retained and full depth reconstruction is warranted. | [7 empty] | We are rated on baseline schedule. | Y |  | 349 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Preliminary Roadway Plans Complete | 21799 | ROADWAY DESIGN | Roadway;#22;#Preliminary Plans;#40 | Finish Milestone | Conduct Avoidance and Minimization Measures Meeting (A3M), Conduct Constructability Review (with steps), Conduct QA of Preliminary Geometry, Conduct Utility Field Meeting, Develop Erosion Control Plans, Develop Preliminary Cross Sections, Develop Preliminary Horizontal Alignment, Develop Preliminary Pavement Design, Develop Preliminary Signing & Marking Plans, Develop Preliminary Typical Sections, Develop Preliminary Vertical Alignment, Develop Roadway Drainage Design, Develop Staging Plans, Develop Wall Envelopes, Develop/Update Construction Cost Estimate, First Submission Utilities Plan to PM, Local/Consultant Preliminary Bridge Plans Accepted/Approved, PM Reviews Preliminary Plans, Pavement Design Preparation, Review and Approval, Place ROW and Easement Requirements, Plot Existing Utility Locations, Preliminary Roadway Plans (consultant design), Preliminary Roadway Plans LOE (in house design), QA Review of Preliminary Roadway Plans (with steps), Receive Environmental Resource Bounda | Final Construction Plans, PFPR Request (OES), PM Request PFPR, PM Submit L & D Report, Preliminary Plans Complete, ROW Plans Preparation, Start Final Roadway Plans | 12.2 | Preliminary Roadway Plans | 0d | · Preliminary Roadway Plans Complete-21799 This is a completion milestone for the development of preliminary plans. | This activity is needed for all in house design projects. | When design is consulted out. | [11 empty] | This is a performance metric activity within our office that is measured based on baseline finish date. | Y | Roadway Design Engineer | 350 | Item | employeecenter/SAM/Lists/SAM
Preliminary Bridge Design Summary | 22000 | BRIDGE | Bridge;#7;#Preliminary Plans;#40 | WBS Summary |  |  | 12.3 | Preliminary Bridge Design | 120d | Summary of preliminary bridge design activities. | Bridge replacement, widening or reconfiguration within the limits of project. | Bridge replacement, widening or reconfiguration within the limits of project. | Completion of preliminary bridge plans Must be completed before activity 21717 – Submit preliminary bridge plans to PM for PFPR Activity 80700 (BFI Report Summary) can’t start until preliminary bridge plans are complete. | Completion of preliminary bridge plans. Must be completed before activity 21717 – Submit preliminary bridge plans to PM for PFPR. Activity 80700 (BFI Report Summary) can’t start until preliminary bridge plans are complete. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. |  |  |  | n/a |  |  |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 351 | Item | employeecenter/SAM/Lists/SAM
Conduct Pavement Type Selection Report | 21732 | OMAT | Pavement;#14 | Task Dependent | Submit Preliminary Plans to GDOT Offices (consultant design), Review Pavement Design, Conduct Pavement Evaluation, Preliminary Roadway Plans (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Submit Pavement Type Selection | 12.6.10 | Pavement Type Selection | 45d | This is when we generate the Pavement Type Selection Report. We generate quantities based on different pavement types, prepare analysis and ranking of alternatives for recommendation on the design to be used in the plans. | See PDP 6.4.2 and new Pavement Type Selection Manual on ROADS Mostly only for project with new alignment or full depth reconstruction | See PDP 6.4.2 Not needed when retaining pavement for overlay or if full depth is less than 1 mile. | This activity requires Pavement Designs to be approved 81600 and 81629 | The end date represents the Pavement Evaluation Report being approved by OMAT if done by a consultant and sent to PM. |  | PTS reports should all generally take about the same amount of time for most projects. The PTS report is used to determine alternate bid for pavements or if HMA or JPCP is the out right choice. This should be done before FFPR | PDP 6.3.4 | [7 empty] | N |  | 352 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL ACTIVITY - NOT IN GENESIS TEMPLATE Submit Pavement Type Selection Report for Approval | 21742 | ROADWAY DESIGN | Pavement;#14;#Roadway;#22 | Task Dependent | Request/Receive Pavement Evaluation, Request/Receive Pavement Type Selection Report | Develop Preliminary Pavement Design, Preliminary Roadway Plans Complete, QA Review of Preliminary Roadway Plans (with steps) | 12.2.1 | Pavement Design | 0d | Zero day duration activity to document the sending of the Pavement Type Selection Report to OMAT for review | When Roadway Design Office is doing the pavement design. | When Roadway Design Office is not doing the pavement design. | [7 empty] | Roadway Design Engineer Group Manager |  |  |  |  | Y | Roadway Design Engineer | 353 | Item | employeecenter/SAM/Lists/SAM
PM submits Pavement Design to OMAT for approval | 21749 | OMAT | PM;#18;#Pavement;#14 | Finish Milestone | Start Preliminary Roadway Plans, Preliminary Roadway Plans (consultant design) | Review Pavement Design, Submit Pavement Type Selection | 12.6.4 | Pavement Design (Local/Consultant) | 0d | Zero day duration activity to document the sending of the pavement design package to OMAT for review | When 81600 is used and project is consultant design | When 81600 is not used or if design is done in-house. | Date the package is sent by PM | Package received | Required for PFPR, is in the PFPR Checklist | [9 empty] | N |  | 354 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion) | 22387 | BRIDGE | Bridge;#7 | Start Milestone | Bridge Hydraulic Study and Layout Development (over stream), Preliminary Bridge Layout Development (non-stream), Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion), Request Preliminary Bridge Layout | Local/Consultant Preliminary Bridge Plans Accepted/Approved | 12.3.1 | Local/Consultant Preliminary Bridge Plan Review | 0d | 2nd review of consultant preliminary bridge plans (non-steam or over stream) for review. | Bridge replacement, widening or reconfiguration within the limits of project when consultants are developing bridge plans. | No bridge replacement, widening or reconfiguration within the limits of project. | No bridge replacement, widening or reconfiguration within the limits of project. | 10 days prior to completion of preliminary bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 355 | Item | employeecenter/SAM/Lists/SAM
Review Pavement Type Selection | 21782 | OMAT | Pavement;#14 | Task Dependent | Submit Pavement Type selection | Start Final Roadway Plans, Final Construction Plans | 12.6.10 | Pavement Type Selection | 20d | Pavement Type Selection is reviewed by OMAT | When 21732 (Conduct PTS ) is used | When 21732 (Conduct PTS ) is not used | Day PTS review starts | Day PTS review ends | [10 empty] | N |  | 356 | Item | employeecenter/SAM/Lists/SAM
Local/Consultant Preliminary Bridge Plans Accepted/Approved | 22400 | BRIDGE | Bridge;#7 | Finish Milestone | Bridge Hydraulic Study and Layout Development (over stream), Preliminary Bridge Layout Development (non-stream), Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion), Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion) | Final Bridge Plans Preparation, Foundation Recommendation Letter (Bridge 1), Loads Letter (Bridge 1), PM Reviews PFPR Package, Preliminary Plans Complete, Request BFI | 12.3.1 | Local/Consultant Preliminary Bridge Plan Review | 0d | Approval of consultant preliminary bridge plans. | Bridge replacement, widening or reconfiguration within the limits of project. | Bridge replacement, widening or reconfiguration within the limits of project. | Completion of preliminary bridge plans. | Completion of preliminary bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [7 empty] | Graded – completion of preliminary bridge plans before finish date. | N |  | 357 | Item | employeecenter/SAM/Lists/SAM
Develop Preliminary Pavement Design | 21752 | ROADWAY DESIGN | Pavement;#14;#Roadway;#22 | Task Dependent |  | QA Review of Preliminary Roadway Plans (with steps), Submit Pavement Design to OMAT for Approval | 12.6.6 | Pavement Design (Roadway Design) | 5d | Roadway developes pavement design | When 81600 is used and project is in-house Design | When 81600 is not used or if design is done by consultant. | day pavement design starts | day pavement design finishes |  | 21752 is a leading indicator for preliminary design. |  |  |  | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 358 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion) | 22377 | BRIDGE | Bridge;#7 | Start Milestone | Bridge Hydraulic Study and Layout Development (over stream), Preliminary Bridge Layout Development (non-stream), Request Preliminary Bridge Layout | Local/Consultant Preliminary Bridge Plans Accepted/Approved, Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion) | 12.3.1 | Local/Consultant Preliminary Bridge Plan Review | 0d | 1st review of consultant preliminary bridge plans (non-steam or over stream) for review. | Bridge replacement, widening or reconfiguration within the limits of project when consultants are developing bridge plans. | Bridge replacement, widening or reconfiguration within the limits of project when consultants are developing bridge plans. | 40 days prior to completion of preliminary bridge plans. PM. | 40 days prior to completion of preliminary bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 359 | Item | employeecenter/SAM/Lists/SAM
Request Preliminary Bridge Layout | 22100 | PROGRAM DELIVERY | Bridge;#7;#PM;#18 | Task Dependent | Database Complete, Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Bridge Hydraulic Study and Layout Development (over stream), Preliminary Bridge Layout Development (non-stream), Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion), Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion) | 12.3 | Preliminary Bridge Design | 0d | [10 empty] | n/a |  |  |  |  | N |  | 360 | Item | employeecenter/SAM/Lists/SAM
Preliminary Bridge Layout Development (non-stream) | 22200 | BRIDGE | Bridge;#7 | Task Dependent | Database Complete, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), Request Preliminary Bridge Layout | Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion), Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion), Local/Consultant Preliminary Bridge Plans Accepted/Approved, Request BFI, Submit Preliminary Plans to PM for PFPR | 12.3 | Preliminary Bridge Design | 120d | Development of preliminary bridge plans that don’t require hydraulics study. | Bridge replacement, widening or reconfiguration within the limits of project. | No bridge replacement, widening or reconfiguration within the limits of project. | 21397 – Submit Preliminary Plans to GDOT Office (with steps) – Road Design/PM | Completion of preliminary bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. |  |  |  | Bridge Design Engineer |  |  |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 361 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Develop Fiber Allocation for ITS | 22510 | TRAFFIC OPS | ITS;#27 | Task Dependent | Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | Develop Network Electronics for ITS | 12.5 | ITS Development | 35d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 362 | Item | employeecenter/SAM/Lists/SAM
Submit Preliminary Plans to GDOT Offices (consultant design) | 23697 | ROADWAY DESIGN | Roadway;#22 | Start Milestone | Conduct Avoidance and Minimization Measures Meeting (A3M), Preliminary Roadway Plans (consultant design) | Receive Preliminary Plans to Begin Technical Studies, Bridge Hydraulic Study and Layout Development (over stream), Develop Preliminary Signing & Marking Plans, Prepare Final EA/FONSI (with steps), Receive Layout for UST/HW Phase II, Conduct Pavement Type Selection Report, Prepare Draft EA (with steps), Preliminary Plans Complete, SUE Coordination (delete if no SUE) (Pilot testing this activity), Request Preliminary Bridge Layout, Receive Local/Consultant Final EA/FONSI, Conduct Section 106 Consultation - History (with steps), Preliminary Bridge Layout Development (non-stream), QA Review of Preliminary Roadway Plans (with steps), Draft Environmental Impact Statement (EIS) Development, Conduct Pavement Evaluation, Conduct Noise Analysis (with steps), Request/Receive Preliminary Lighting Plans, Conduct Agency Consultation for Ecology (with steps), Prepare CE | 12.1 | Local and Consultant Design Activities for Preliminary Plans | 0d | [15 empty] | N |  | 363 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Develop Network Electronics for ITS | 22520 | TRAFFIC OPS | ITS;#27 | Task Dependent | Develop Fiber Allocation for ITS | Develop Implementation Plan for ITS | 12.5 | ITS Development | 35d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 364 | Item | employeecenter/SAM/Lists/SAM
Bridge Hydraulic Study and Layout Development (over stream) | 22300 | BRIDGE | Bridge;#7 | Task Dependent | Database Complete, Request Preliminary Bridge Layout, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | Local/Consultant Preliminary Bridge Plans Accepted/Approved, Receive Local/Consultant Preliminary Bridge Plans for 1st Review (40 days prior to completion), Receive Local/Consultant Preliminary Bridge Plans for 2nd/Final Review (10 days prior to completion), Request BFI, Submit Preliminary Plans to PM for PFPR, PM Reviews PFPR Package | 12.3 | Preliminary Bridge Design | 120d | Development of preliminary bridge plans that requires hydraulics study. | Bridge replacement, widening or reconfiguration within the limits of project. | No bridge replacement, widening or reconfiguration within the limits of project. | 21397 – Submit Preliminary Plans to GDOT Office (with steps) – Road Design/PM | Completion of preliminary bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. |  |  |  | Bridge Hydraulics Engineer |  |  |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 365 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Develop Implementation Plan for ITS | 22530 | TRAFFIC OPS | ITS;#27 | Task Dependent | Develop Network Electronics for ITS |  | 12.5 | ITS Development | 120d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 366 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Highway System Admin Summary | 23500 | TRANSPORTATION DATA | General;#26 | [5 empty] | 10d | HISTORICAL ACTIVITY ( NOT IN GENESIS TEMPLATE, but may be present in older project schedules; Highway System Admin Summary (23500), Highway System Internal Coordination Process (23510), & Highway System External Coordination Process (23520) - These activities should be combined into one - not in current Master Schedule ; These activities cover internal and external activities related to developing the State Highway System Revision document which includes the Order of the Commissioner document which is signed by the GDOT commissioner, the GDOT treasurer, and the locals and the Authorizing Resolution document which is signed by the locals.; The internal coordination includes initial research, meetings with districts, project managers, and district engineers, and getting internal signatures for documents. The external coordination includes getting signatures as needed from locals. | This activity is needed for all projects that involve a state route realignment, relocation, or bypass. The activity should happen after the project’s environmental documents have been approved OTD needs to receive the cover sheet of the Preliminary Roadway Plans from the PM to complete their work. | This activity is not needed for any projects that do not include a state route realignment, relocation, or bypass. | These activities start when a PM notifies Bertha Bryant in OTD that a state route reassignment is needed or makes the request through Windy Bicker in OFM. The request should be made after the environmental document is approved. | The end date represents having a signed State Highway System Revision document. |  | Previously, there was a problem because the locals and the GDOT PM were going forward with purchasing ROW with State funds, federal funds, or GRTA bonds before they had the state highway revisions in place.& OTD needs to know immediately after the environmental document is approved for the projects so that OTD will have time to do the background work and complete the State Highway System Revision document before ROW acquisition starts. HB154 in 2015 eliminated the requirement of changing the local road identification to a SR and then changing it back when the project is completed. Another reason it is important to give OTD notice as soon as possible because sometimes it takes an extended time to get the signed documents back from the locals. When that happens, OTD would contact the PM to talk directly to the locals to get the signed documents back. State Highway System Revision document includes the Order of the Commissioner document and the Authorizing Resolution document. It is important that this activity happen because OTD must do a study to determine which road sections to remove from state route status in order to maintain Georgia’s total state route mileage (currently ~ 18,000 miles). If a project adds 6 miles to the state route system, a study is done to eliminate at least 4-5 miles from the state route system within the same county so that the total SR mileage remains about the same size. They consider many parameters to decide which routes to take off of the state route system including usage and traffic volumes. Part of the documentation is an agreement for the local government to take over the maintenance of the road segment that are chosen to revert back to local control. In the past, when PMs contacted Windy Bicker in OFM for state route revisions, an automatic email notification would come to Bertha Bryant in OTD that had the PI#, the PM, and the project accounting number advising highway system revisions are needed for this project. If the project crosses a county/county boundary or a county/city boundary, OTD would have to contact the PM to find out which local governments are involved and should be contacted to get all the needed information and signatures. |  | These three activities should be combined into one activity. | [6 empty] | Y |  | 367 | Item | employeecenter/SAM/Lists/SAM
PM Reviews PFPR Package | 24500 | PROGRAM DELIVERY | PM;#18;#PFPR;#23 | Task Dependent | Local/Consultant Preliminary Bridge Plans Accepted/Approved, Preliminary Roadway Plans (consultant design), QA Review of Preliminary Roadway Plans (with steps), Receive and Review PCSR, Request/Receive Constructability Review, Request/Receive Preliminary Lighting Plans, Request/Receive Utilities First Submission/SUE Coordination, Submit Preliminary Plans to PM for PFPR, Transmit Approved Pavement Design to PM for FFPR, Transmit Pavement Evaluation to PM for PFPR, Bridge Hydraulic Study and Layout Development (over stream), Conduct Pavement Type Selection | Preliminary Plans Complete, ROW Plans Preparation | 12 | Preliminary Plans | 5d | [10 empty] | n/a |  |  |  |  | N |  | 368 | Item | employeecenter/SAM/Lists/SAM
Preliminary Plans Complete | 25000 | ROADWAY DESIGN | Roadway;#22;#Preliminary Plans;#40 | Finish Milestone | PM Reviews PFPR Package, Conduct Avoidance and Minimization Measures Meeting (A3M), Request/Receive Utilities First Submission, Receive Environmental Resource Boundaries (consultant design), Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to PM for PFPR, Request/Receive Constructability Review, Local/Consultant Preliminary Bridge Plans Accepted/Approved, Request/Receive Preliminary Lighting Plans | Final Construction Plans, PFPR Request (OES), PM Request PFPR, PM Submit L & D Report, ROW Plans Preparation, Start Final Roadway Plans | 12.1 | Preliminary Plans | 0d | [15 empty] | N |  | 369 | Item | employeecenter/SAM/Lists/SAM
Prepare MS4 Design and PCSR; Submit to ODPS | 27242 | ROADWAY DESIGN | Roadway;#22;#MS4;#43 | Task Dependent | Develop Roadway Drainage Design, Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | Develop Staging Plans, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS | 7-1-01 | MS4 Design Activities (Roadway Design) | 10d | [15 empty] | N |  | 370 | Item | employeecenter/SAM/Lists/SAM
Receive and Review PCSR | 27272 | DESIGN POLICY & SUPPORT | MS4;#43 | Task Dependent | PM Submits PCSR to ODPS, Preliminary Roadway Plans (consultant design), Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS, Start Preliminary Roadway Plans | ODPS Submits PCSR to EPD, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, PFPR Inspection, PM Request PFPR, PM Reviews PFPR Package | 7-1-03 | MS4 ODPS Activities | 20d | [12 empty] | As Late As Possible |  |  | N |  | 371 | Item | employeecenter/SAM/Lists/SAM
Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS | 27262 | ROADWAY DESIGN | MS4;#43;#Roadway;#22 | Task Dependent | Develop Roadway Drainage Design, Preliminary Roadway Plans (consultant design), Prepare MS4 Design and PCSR; Submit to ODPS, Start Preliminary Roadway Plans | PCSR Revisions Post-PFPR (if needed); Submit to ODPS, Receive and Review PCSR | 7-1-01 | MS4 Design Activities (Roadway Design) | 10d | [15 empty] | N |  | 372 | Item | employeecenter/SAM/Lists/SAM
ODPS Submits PCSR to EPD | 27289 | DESIGN POLICY & SUPPORT | MS4;#43 | Finish Milestone | PCSR Revisions Post-PFPR (if needed); Submit to ODPS, PM Distributes PFPR Responses, Receive and Review PCSR | Final Construction Plans Complete, PM Request FFPR | 7-1-03 | MS4 ODPS Activities | 0d | [15 empty] | N |  | 373 | Item | employeecenter/SAM/Lists/SAM
PCSR Revisions Post-PFPR (if needed); Submit to ODPS | 27282 | ROADWAY DESIGN | MS4;#43;#Roadway;#22 | Task Dependent | PM Distributes PFPR Responses, Prepare MS4 Design and PCSR; Submit to ODPS, Prepare Stormwater BMP Infiltration Report (if needed); submit to ODPS, Receive and Review PCSR | Final Construction Plans Complete, Final Roadway Plans Complete, ODPS Submits PCSR to EPD, PM Request FFPR | 7-1-01 | MS4 Design Activities (Roadway Design) | 40d | [15 empty] | N |  | 374 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE UST and HW Summary | 27800 | OMAT | UST;#12 | WBS Summary |  |  | 9 | UST and Hazardous Waste | 1,219d | ;This activity involve two (2) phases: The Planning and Programming Engineers (DPPE) may perform Phase I assessments when the work has been assigned to the Office of Roadway Design or District Design, otherwise a Consultant Prequalified in Area Class6.05 should perform the work. OMAT may perform Phase II assessments when the project has been assigned to the Office of Roadway Design or District Design, otherwise a Consultant Prequalified in Area Class 6.05 should perform the work. An Environmental Site Assessment, Phase II is required when the results of a ESA Phase I reveal Recognized Environmental Conditions (RECs).& ; HISTORICAL: NOT IN GENESIS TEMPLATE; This activity is the process of assessing the UST(Underground Storage Tank) and Hazardous Waste status of a project site.; The PM contacts the District planning and programming engineer to ask for the district to do a site evaluation ; The District planning and programming engineer would do a site evaluation and present the results of that assessment to OMR (Office of Materials and Research).; OMR does the Phase I and Phase II assessments of the project site and delivers a UST letter to the PM to signify the completion of the UST evaluation | This activity is needed for all projects with new ROW to be acquired. Or project without new ROW involving ditching, utility work, installation offoundations, storm sewer, or other intrusive construction activities. | This activity is not needed for any projects without ROW. | when the project concept has been defined | when OMAT provides a UST letter to the PM to signify the completion of the UST evaluation. |  | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 375 | Item | employeecenter/SAM/Lists/SAM
PM Submits PCSR to ODPS | 27267 | PROGRAM DELIVERY | MS4;#43;#PM;#18 | Start Milestone | Preliminary Roadway Plans (consultant design) | Receive and Review PCSR | 7-1-02 | MS4 Design Activities (local/consultant design) | 0d | [12 empty] | As Late As Possible |  |  | N |  | 376 | Item | employeecenter/SAM/Lists/SAM
UST/HW Site Assessment Phase I Summary | 27821 | OMAT | UST;#12 | WBS Summary |  |  | 9.3 | UST/HW Site Assessment Phase I | 100d | This in house activity is the process of assessing the UST(Underground Storage Tank) and Hazardous Waste status of a project site.; The PM contacts the District planning and programming engineer to ask for the district to do a site evaluation.; The District planning and programming engineer (DPPE) would do a site evaluation and present the results of that assessment to OMR (Office of Materials and Research).; The DPPE does the Phase I; assessments of the project site and delivers a UST/HW Phase I report to the PM and OMAT. | This activity is needed for all projects with new ROW to be aquired. Or project without new ROW involving ditching, utility work, installation of foundations, storm sewer, or other intrusive construction activities. | This activity is not needed for any projects without ROW. | when the project concept has been defined | when OMAT provides a UST letter to the PM to signify the completion of the UST evaluation. |  | District Office | [8 empty] | N |  | 377 | Item | employeecenter/SAM/Lists/SAM
Receive Layout for UST/HW Phase II | 27847 | OMAT | UST;#12 | Start Milestone | Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps), UST/HW Phase I Report Preparation, Review Consultant UST/HW Phase I Report | Review Consultant UST/HW Phase II Report, UST/HW Phase II Report Preparation | 9.4 | UST/HW Site Assessment Phase II (if needed) | 0d | Supporting documentation OMAT received from PM or DDPE along with Phase I report. Preliminary ROW plans are preferred. | This activity is needed for all projects with ROW that OMAT deems in need of UST/HW Phase II assessment. | This activity is not needed for all projects that OMAT deems complete with UST/HW Phase I assessment. | Supporting documentation OMAT received from PM or DDPE along with Phase I report.& Preliminary ROW plans are preferred. | Supporting documentation OMAT received from PM or DDPE along with Phase I report. Preliminary ROW plans are preferred. | [10 empty] | N |  | 378 | Item | employeecenter/SAM/Lists/SAM
Receive Layout for UST/HW Phase I | 27827 | OMAT | UST;#12 | Start Milestone | Create & Submit Environmental Study Area Layout, Define Project Concept, Develop Revised Concept Report, Define Project Concept (scoping or pre-concept) | UST/HW Phase I Report Preparation, Review Consultant UST/HW Phase I Report | 9.3 | UST/HW Site Assessment Phase I | 0d | When the project concept report is defined, GDOT or consultant road design sends the project concept to the PM. The PM sends that information to the district planning and programming engineer to request an initial; project site evaluation. | This activity is needed for all projects with new ROW to be acquired. Or project without new ROW involving ditching, utility work, installation offoundations, storm sewer, or other intrusive construction activities. | This activity is not needed for any projects without ROW. | when the project concept has been defined and the PM sends a request to the district planning and programming engineer to get UST/HW analysis for a project. | when the project concept has been defined and the PM sends a request to the district planning and programming engineer to get UST/HW Phase I report for a project. |  | District Office | [8 empty] | N |  | 379 | Item | employeecenter/SAM/Lists/SAM
UST/HW Site Assessment Phase II Summary | 27841 | OMAT | UST;#12 | WBS Summary |  |  | 9.4 | UST/HW Site Assessment Phase II (if needed) | 180d | This the phase II report is needed after a Phase I ESA report was completed by the DDPE which reveals presence of REC along the project corridor and after carrying out a field investigation. Note: the 180d (working days) planned duration is from the time OMAT received the Phase I from the DPPE to PM receiving the final Phase II report | This activity is needed for all projects with ROW that OMAT deems in need of UST/HW Phase II assessment. | This activity is not needed for all projects that OMAT deems complete with UST/HW Phase I assessment. | Supporting documentation OMAT received from PM or DDPE along with Phase I report. Preliminary ROW plans are preferred. | when OMAT provides a UST letter to the PM to signify the completion of the UST evaluation. | [10 empty] | N |  | 380 | Item | employeecenter/SAM/Lists/SAM
UST/HW Phase I Report Preparation | 27832 | OMAT | UST;#12 | Task Dependent | Receive Layout for UST/HW Phase I | Develop Final EIS, Develop, Approve & Publish Notice of Decision (NOD), Prepare CE, Prepare Environmental Effects Report (EER), Prepare Final EA/FONSI (with steps), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Receive Layout for UST/HW Phase II, Review and Approve Environmental Effects Report (EER), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Review Consultant UST/HW Phase I Report | 9.3 | UST/HW Site Assessment Phase I | 60d | (In house) The district program and planning engineer delivers the initial project site evaluation (Phase 1 report) that the district performed to OMAT and requests UST/HW Phase II analysis if warranted. Note: The DPPE establishes the duration. | This activity is needed for all projects with new ROW to be aquired. Or project without new ROW involving ditching, utility work, installation of foundations, storm sewer, or other intrusive construction activities. | This activity is not needed for any projects without ROW. | when the district program and planning engineer delivers the initial project site evaluation to OMAT and requests UST/HW analysis | when OMAT completes the first UST/HW evaluation of the project site, prepares a report with the initial UST/HW analysis and findings, and sends it to the project PM. |  | (District Office) | [8 empty] | N |  | 381 | Item | employeecenter/SAM/Lists/SAM
Review Consultant UST/HW Phase II Report | 27854 | OMAT | UST;#12 | Task Dependent | Receive Layout for UST/HW Phase II, UST/HW Phase II Report Preparation | G.O. ROW Certification, ROW Negotiations and Acquisition Work | 9.4 | UST/HW Site Assessment Phase II (if needed) | 40d | OMAT reviews consultant UST/HW Phase I Report: The electronic files along with all supporting documents of the report are sent to Geotechnical Bureau/Environmental Branch in OMAT by the PM through <a href="mailto:Geotechnical_Reports@dot.ga.gov">Geotechnical_Reports@dot.ga.gov</a> consultant. The report is reviewed and once approved it is sent to the GDOT PM. | This activity is needed for all projects with ROW that OMAT deems in need of UST/HW Phase II assessment. | This activity is not needed for all projects that OMAT deems complete with UST/HW Phase I assessment. | when the PM delivers the initial project site evaluation and UST/HW Phase 1 report to OMAT and requests review of their report. | when OMAT provides a phase II ESA report to the PM to signify the completion of the consultant UST evaluation and approval. | [10 empty] | N |  | 382 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Schedule Development and PTIP Summary | 31111 | PROGRAM CONTROL | General;#26;#PTIP;#44 | WBS Summary |  |  | 0.5 | Schedule Development and PTIP | 178d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 383 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Request Initial Schedule | 31127 | PROGRAM DELIVERY | General;#26;#PTIP;#44 | Start Milestone | PM Review PTIP Responses | OPC Initial Schedule Development, Project Justification (request and receive) | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 384 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PTIP Responses Received by PM | 31149 | ROADWAY DESIGN | PM;#18;#Roadway;#22;#PTIP;#44 | Finish Milestone | PTIP Meeting | PM Review PTIP Responses | 0.5.5 | PTIP | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y | Roadway Design Engineer | 385 | Item | employeecenter/SAM/Lists/SAM
Review Consultant UST/HW Phase I Report | 27834 | OMAT | UST;#12 | Task Dependent | Receive Layout for UST/HW Phase I, UST/HW Phase I Report Preparation | Receive Layout for UST/HW Phase II, Environmental Approval Complete (If state funds: Env. Activities Complete) | 9.3 | UST/HW Site Assessment Phase I | 40d | OMAT reviews consultant UST/HW Phase I Report: The electronic files along with all supporting documents of the report are sent to Geotechnical Bureau/Environmental Branch in OMAT by the PM through Geotechnical_Reports@dot.ga.gov. The report is reviewed and once approved, it is sent to the GDOT PM. | This activity is needed for all projects with new ROW to be acquired. Or project without new ROW involving ditching, utility work, installation of foundations, storm sewer, or other intrusive construction activities. | This activity is not needed for any projects without ROW or for in house design projects. | when the consultant delivers the initial project site evaluation and UST/HW Phase 1 report to OMAT and requests review of their report. | when OMAT approves the Phase 1 UST/HW report that affirms or dismisses the need for UST/HW Phase II from a consultant and sends it to the GDOT PM. | [10 empty] | N |  | 386 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PTIP Meeting | 31139 | ROADWAY DESIGN | Roadway;#22;#Meeting;#4;#PTIP;#44 | Finish Milestone | PM Request PTIP | PTIP Responses Received by PM | 0.5.5 | PTIP | 0d | PTIP Meeting; HISTORICAL: NOT IN GENESIS TEMPLATE | This activity is needed for all design projects. | This activity is needed for all design projects. |  |  |  | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y | Roadway Design Engineer | 387 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Review PTIP Responses | 31152 | PROGRAM DELIVERY | PM;#18;#PTIP;#44 | Task Dependent | PTIP Responses Received by PM | Data Acquisition for Concept (with steps), PM Request Initial Schedule, Procurement Requisition Form Submitted by PM | 0.5.5 | PTIP | 5d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y | Roadway Design Engineer | 388 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE OPC Initial Schedule Development | 31132 | PROGRAM CONTROL | General;#26;#PM;#18 | Task Dependent | PM Request Initial Schedule | PM Request Schedule Revisions (1st), PM Submit Schedule Concurrence and Request for SRC Review, Procurement Requisition Form Submitted by PM | 0.5.11 | Schedule Development | 10d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 389 | Item | employeecenter/SAM/Lists/SAM
UST/HW Phase II Report Preparation | 27852 | OMAT | UST;#12 | Task Dependent | Receive Layout for UST/HW Phase II | G.O. ROW Certification, ROW Negotiations and Acquisition Work, Review Consultant UST/HW Phase II Report | 9.4 | UST/HW Site Assessment Phase II (if needed) | 180d | This the phase II report is needed after a Phase I ESA report was completed by the DDPE which reveals presence of REC along the project corridor and after carrying out a field investigation. Note: the 180d (working days) planned duration is from the time OMAT received the Phase I from the DPPE to PM receiving the the final Phase II report | This activity is needed for all projects with ROW that OMAT deems in need of UST/HW Phase II assessment. | This activity is not needed for all projects that OMAT deems complete with UST/HW Phase I assessment. | OMAT received the Phase I report from the DPPE and the PM confirms funds availability for field work and lab testing. | when OMAT provides a phase II ESA report to the PM to signify the completion of the UST evaluation. | [10 empty] | N |  | 390 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Request PTIP | 31137 | PROGRAM DELIVERY | PM;#18;#PTIP;#44 | Start Milestone |  | PTIP Meeting | 0.5.5 | PTIP | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 391 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Submit and Receive Feedback from SMEs | 31164 | PROGRAM DELIVERY | PM;#18 | Task Dependent | OPC Revise Schedule (1st Revision) | PM Request Schedule Revisions (2nd or latest request), PM Submit Schedule Concurrence and Request for SRC Review | 0.5.11 | Schedule Development | 15d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 392 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE OPC Revise Schedule (1st Revision) | 31162 | PROGRAM CONTROL | General;#26 | Task Dependent | PM Request Schedule Revisions (1st) | PM Submit Schedule Concurrence and Request for SRC Review, PM Submit and Receive Feedback from SMEs | 0.5.11 | Schedule Development | 10d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 393 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Request Schedule Revisions (2nd or latest request) | 31167 | PROGRAM DELIVERY | PM;#18 | Start Milestone | PM Submit and Receive Feedback from SMEs | OPC Revise Schedule (2nd or latest revision) | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 394 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Request Schedule Revisions (1st) | 31157 | PROGRAM DELIVERY | PM;#18 | Start Milestone | OPC Initial Schedule Development | OPC Revise Schedule (1st Revision) | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 395 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE OPC Revise Schedule (2nd or latest revision) | 31172 | PROGRAM CONTROL | General;#26 | Task Dependent | PM Request Schedule Revisions (2nd or latest request) | PM Review Schedule (2nd or latest revision) | 0.5.11 | Schedule Development | 10d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 396 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Review Schedule (2nd or latest revision) | 31174 | PROGRAM DELIVERY | PM;#18 | Task Dependent | OPC Revise Schedule (2nd or latest revision) | PM Submit Schedule Concurrence and Request for SRC Review | 0.5.11 | Schedule Development | 5d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 397 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE PM Submit Schedule Concurrence and Request for SRC Review | 31187 | PROGRAM DELIVERY | PM;#18 | Start Milestone | OPC Initial Schedule Development, OPC Revise Schedule (1st Revision), PM Review Schedule (2nd or latest revision), PM Submit and Receive Feedback from SMEs | OPC Schedule Review Committee | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 398 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE OPC Schedule Review Committee | 31189 | PROGRAM CONTROL | General;#26;#Meeting;#4 | Finish Milestone | PM Submit Schedule Concurrence and Request for SRC Review | OPC Schedule Approved by the Chief Engineer | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 399 | Item | employeecenter/SAM/Lists/SAM
Consultant Kick-Off Meeting | 33132 | PROGRAM DELIVERY | Meeting;#4;#PM;#18 | Task Dependent | Notice to Proceed (NTP) for Consultant Contract | PAR Checkpoint 1a - Introduce Project to Agencies, Define Project Concept | 2.1 | Procurement for Concept (if needed) | 10d | [15 empty] | N |  | 400 | Item | employeecenter/SAM/Lists/SAM
Consultant Acquisition (request through notification) | 33122 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Task Dependent | Procurement Requisition Form Submitted by PM | Notice to Proceed (NTP) for Consultant Contract | 2.1 | Procurement for Concept (if needed) | 120d | [15 empty] | N |  | 401 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE OPC Schedule Approved by the Chief Engineer | 31199 | CHIEF ENGINEER | General;#26;#Meeting;#4 | Finish Milestone | OPC Schedule Review Committee | Data Acquisition for Concept (with steps), PE Funding Authorization | 0.5.11 | Schedule Development | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 402 | Item | employeecenter/SAM/Lists/SAM
Procurement Requisition Form Submitted by PM | 33217 | PROGRAM DELIVERY | PM;#18;#Preliminary Plans;#40;#Procurement;#38 | Start Milestone | Prepare Procurement Requisition Form | Consultant Acquisition (request through notification) | 2.2 | Procurement for Preliminary Design (if needed) | 0d | [15 empty] | N |  | 403 | Item | employeecenter/SAM/Lists/SAM
Notice to Proceed (NTP) for Consultant Contract | 33129 | PROGRAM DELIVERY | PM;#18;#Concept;#20;#NTP;#3;#Consultant;#51;#Procurement;#38 | Finish Milestone | Consultant Acquisition (request through notification) | Consultant Kick-Off Meeting | 2.1 | Procurement for Concept (if needed) | 0d | [15 empty] | N |  | 404 | Item | employeecenter/SAM/Lists/SAM
Consultant Kick-Off Meeting | 33232 | PROGRAM DELIVERY | PM;#18;#Meeting;#4;#Consultant;#51;#Procurement;#38 | Task Dependent | Notice to Proceed (NTP) for Consultant Contract | Preliminary Roadway Plans (consultant design) | 2.2 | Procurement for Preliminary Design (if needed) | 10d | [15 empty] | N |  | 405 | Item | employeecenter/SAM/Lists/SAM
Consultant Acquisition (request through notification) | 33222 | PROGRAM DELIVERY | PM;#18;#Consultant;#51;#Procurement;#38 | Task Dependent | Procurement Requisition Form Submitted by PM | Notice to Proceed (NTP) for Consultant Contract | 2.2 | Procurement for Preliminary Design (if needed) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 406 | Item | employeecenter/SAM/Lists/SAM
Procurement Requisition Form Submitted by PM | 33117 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Start Milestone | Prepare Procurement Requisition Form | Consultant Acquisition (request through notification) | 2.1 | Procurement for Concept (if needed) | 0d | [15 empty] | N |  | 407 | Item | employeecenter/SAM/Lists/SAM
Notice to Proceed (NTP) for Consultant Contract | 33229 | PROGRAM DELIVERY | NTP;#3;#Consultant;#51;#Procurement;#38 | Finish Milestone | Consultant Acquisition (request through notification) | Develop Revised Concept Report | 2.2 | Procurement for Preliminary Design (if needed) | 0d | [15 empty] | N |  | 408 | Item | employeecenter/SAM/Lists/SAM
PM Request PFPR | 39500 | PROGRAM DELIVERY | PM;#18;#PFPR;#23;#ROW;#21 | Start Milestone | Conduct Ecology Survey (with steps), Conduct Ecology Survey for 2nd Seasonal Species, Conduct Ecology Survey for 3rd Seasonal Species, Conduct Ecology Survey for 3rd Seasonal Species, Conduct Ecology Survey for 4th Seasonal Species, Conduct Ecology Survey for Seasonal Species, Conduct History Survey (with steps), Environmental Resource Identification Complete, FHWA Approval of Draft EIS, FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), Preliminary Plans Complete, Preliminary Roadway Plans (consultant design), Preliminary Roadway Plans Complete, Prepare Environmental Effects Report (EER), Receive Environmental Study Area Layout / Start Environmental Studies, Receive and Review PCSR, Review Local/Consultant Soil Survey, Review and Approve Environmental Effects Report (EER) | PFPR Request (OES), ROW Plans Final Approval, ROW Plans Preparation | 12.4 | PFPR | 0d | [15 empty] | N |  | 409 | Item | employeecenter/SAM/Lists/SAM
Notice to Proceed (NTP) for Consultant Contract | 33329 | PROGRAM DELIVERY | NTP;#3;#PM;#18;#Procurement;#38 | Finish Milestone | Consultant Acquisition (request through notification) | Develop Revised Concept Report | 2.3 | Procurement for Final Design (if needed) | 0d | [15 empty] | N |  | 410 | Item | employeecenter/SAM/Lists/SAM
Consultant Acquisition (request through notification) | 33322 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Task Dependent | Procurement Requisition Form Submitted by PM | Notice to Proceed (NTP) for Consultant Contract | 2.3 | Procurement for Final Design (if needed) | 120d | [10 empty] | n/a |  |  |  |  | N |  | 411 | Item | employeecenter/SAM/Lists/SAM
PM Submits PFPR Responses to OES | 40450 | PROGRAM DELIVERY | PM;#18;#PFPR;#23 | Task Dependent | PFPR Report Approval and Distribution | Verify PFPR Responses | 12.4 | PFPR | 20d | PM has 20 days to review and send any responses to approved FFPR report. | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | when PM gets final PFPR report, PM has 20 work days to send any comments to be addressed by OES | 20 days after PM received final FFPR report. | [5 empty] | n/a |  |  |  |  | N |  | 412 | Item | employeecenter/SAM/Lists/SAM
PFPR Report Preparation | 40300 | ENGINEERING SERVICES | PFPR;#23 | Task Dependent | PFPR Inspection | PFPR Report Approval and Distribution | 12.4 | PFPR | 10d | PFPR Report Preparation - Comments from PFPR meeting are compiled and PFPR report produced | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | Next working date after the PFPR Inspection. Note: If the report goes out the same date of the inspection, then the date of the inspection should be placed here | The date you distribute the report or send it over to FHWA for approval on applicable PoDI projects. | [5 empty] | n/a |  |  |  |  | N |  | 413 | Item | employeecenter/SAM/Lists/SAM
PFPR Report Approval and Distribution | 40400 | ENGINEERING SERVICES | PFPR;#23 | Task Dependent | PFPR Report Preparation | PM Submits PFPR Responses to OES, Verify PFPR Responses | 12.4 | PFPR | 0d | PFPR Report Approval and Distribution - completion of PFPR report review activity | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | The date the report is sent over to FHWA on applicable PoDI projects; on all other projects, this will be the date you distributed the report. | The date the report is received from FHWA on applicable PoDI projects and is distributed; on all other projects, this will be the date the report is distributed. | [5 empty] | n/a |  |  |  |  | N |  | 414 | Item | employeecenter/SAM/Lists/SAM
PFPR Request (OES) | 40100 | ENGINEERING SERVICES | PFPR;#23;#PM;#18 | Task Dependent | FHWA Approval of Draft EIS, FHWA Review of Draft EA & Approval to Advance to Public Hearing (with steps), PM Request PFPR, Preliminary Plans Complete, Preliminary Roadway Plans Complete, , Receive Environmental Study Area Layout / Start Environmental Studies | PFPR Inspection | 12.4 | PFPR | 20d | PFPR Request - date when complete PFPR QA/QC request accepted by OES from PM | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | Date when complete PFPR request is submitted by PM | Date that scheduling letter or Waiver letter is sent out for the PFPR or the date that the letter is sent to the District for them to schedule and hold. | [5 empty] | n/a |  |  |  |  | N |  | 415 | Item | employeecenter/SAM/Lists/SAM
Procurement Requisition Form Submitted by PM | 33317 | PROGRAM DELIVERY | PM;#18;#Procurement;#38 | Start Milestone | Prepare Procurement Requisition Form | Consultant Acquisition (request through notification) | 2.3 | Procurement for Final Design (if needed) | 0d | [15 empty] | N |  | 416 | Item | employeecenter/SAM/Lists/SAM
PFPR Summary | 40000 | ENGINEERING SERVICES | PFPR;#23 | WBS Summary |  |  | 12.4 | PFPR | 56d | Preliminary Field Plan Review - from when OES receives a complete PFPR request from PM for QA/QC review of a complete set of project plans at different milestones to the PM receiving approval on all responses to the final PFPR report | This activity is needed for all projects except some bridge maintenance projects and any other maintenance projects and should be held a minimum of 16 weeks prior to ROW Authorization | This activity is not needed for maintenance projects except for some bridge maintenance projects. | This date automatically comes up from beginning date of activity 40100 | This date automatically comes up from end date of activity 40400 | [5 empty] | n/a |  |  |  |  | N |  | 417 | Item | employeecenter/SAM/Lists/SAM
PFPR Inspection | 40200 | ENGINEERING SERVICES | PFPR;#23;#Meeting;#4 | Task Dependent | Concept Approval to PFPR Inspection, PFPR Request (OES), Receive and Review PCSR | Implementation of ROW Footprint Comments (with steps), PFPR Inspection to ROW authorization, PFPR Report Preparation, ROW Plans Preparation | 12.4 | PFPR | 1d | PFPR Inspection - attending PFPR meeting and site visit inspection or preparing and sending waiver letter for PFPR | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | Date of PFPR | Same date unless the PFPR is a two day inspection. NOTE: If we waive the PFPR, put the date you sent out the Waiver Letter here. | [5 empty] | n/a |  |  |  |  | N |  | 418 | Item | employeecenter/SAM/Lists/SAM
Consultant Kick-Off Meeting | 33332 | PROGRAM DELIVERY | Meeting;#4;#PM;#18;#Consultant;#51 | Task Dependent | Notice to Proceed (NTP) for Consultant Contract | Final Construction Plans | 2.3 | Procurement for Final Design (if needed) | 10d | [15 empty] | N |  | 419 | Item | employeecenter/SAM/Lists/SAM
Implementation of ROW Footprint Comments (with steps) | 41313 | ROADWAY DESIGN | Roadway;#22;#ROW;#21;#Preliminary Plans;#40 | Task Dependent | PFPR Inspection, ROW Plans Preparation | PM Submit L & D Report, Final Construction Plans, Complete/Submit Environmental Change Form, Start Final Roadway Plans, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team) | 12.2 | Preliminary Roadway Plans | 20d | Implementation of ROW footprint comments (with steps)-41313; This activity consists of addressing PFPR comments that would require adjustments to the preliminary right of way before completing final right of way plans. | This activity is needed for all in house design projects. | When design is consulted out. | PFPR has been held and inspection report distributed. | [5 empty] | 2 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 420 | Item | employeecenter/SAM/Lists/SAM
ROW Plans Summary | 50000 | PROGRAM DELIVERY | PM;#18;#ROW;#21 | WBS Summary |  |  | 18 | ROW Plans | 405d | Process from PM request to receipt of approved final ROW Plans? | The activity is needed when a project has a right of way phase. | This activity is not needed when a project does not have a right of way phase or it has been determined that right of way is not required. | when PM requests that Road Design prepares the project ROW plans be prepared by Roadway Design? | Final ROW plans have been completed, submitted and approved by ROW, and submitted to PM. | [5 empty] | n/a |  |  |  |  | N |  | 421 | Item | employeecenter/SAM/Lists/SAM
PM Distributes PFPR Responses | 40550 | PROGRAM DELIVERY | PM;#18;#PFPR;#23 | Finish Milestone | Verify PFPR Responses, Conduct Utility Field Meeting | Complete/Submit Environmental Change Form, Develop Final EIS, Develop, Approve & Publish Notice of Decision (NOD), FHWA Review and Approval of the CE (If 4F: advance to legal review), Final Construction Plans, Implementation of ROW Footprint Comments (with steps), ODPS Submits PCSR to EPD, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, PM Request Interim FPR, PM Request Supplemental FFPR, PM Submit L & D Report, Prepare Final EA/FONSI (with steps), Prepare GEPA Type A Letter, Prepare GEPA Type B Letter, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Review and Approve GEPA Type A Letter, Review and Approve GEPA Type B Letter, Start Final Roadway Plans, Submit 1st Submission RR Package to PM, Submit CE to FHWA, Submit Final EA/FONSI to FHWA, Submit Final Plans to Utilities for Impacted RR, Submit Preliminary Plans to Utilities for Impacted Railroads | 12.4 | PFPR | 0d | [15 empty] | N |  | 422 | Item | employeecenter/SAM/Lists/SAM
Verify PFPR Responses | 40500 | ENGINEERING SERVICES | PFPR;#23 | Task Dependent | PFPR Report Approval and Distribution, PM Submits PFPR Responses to OES | Final Construction Plans, PM Distributes PFPR Responses, PM Submit L & D Report, ROW Plans Preparation, Request/Receive Utilities Second Submission, Start Final Roadway Plans, Submit Final Plans to Utilities for Impacted RR | 12.4 | PFPR | 5d | Verify PFPR Responses - Final PFPR report is approved and distributed. | This activity is needed for all projects including some bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except some bridge maintenance projects. | Date the PM submits responses to OES for acceptance. | Date that PM is notified that the responses are acceptable. | [5 empty] | n/a |  |  |  | These activities are and should be evaluated on whether or not the allowable time frames are met. | N |  | 423 | Item | employeecenter/SAM/Lists/SAM
Submit Right of Way Plans | 50300 | PROGRAM DELIVERY | PM;#18;#ROW;#21 | Task Dependent | ROW Plans Preparation | ROW Plans Final Approval | 18 | ROW Plans | 0d | Roadway Design Submits Right of Way Plans to ROW for review | The activity is needed when a project has a right of way phase. | This activity is not needed when a project does not have a right of way phase or it has been determined that right of way is not required. | When Road Design submits the project ROW plans to ROW Office for review and approval? | When Road Design submits the project ROW plans to ROW Office for review and approval? | [5 empty] | n/a |  |  |  |  | N |  | 424 | Item | employeecenter/SAM/Lists/SAM
ROW Plans Preparation | 50100 | ROADWAY DESIGN | Roadway;#22;#ROW;#21 | Task Dependent | Preliminary Plans Complete, PM Reviews PFPR Package, Utility and ROW Coordination Meeting, Verify PFPR Responses, PM Request PFPR, PFPR Inspection | Implementation of ROW Footprint Comments (with steps), PM Submit L & D Report, Submit Right of Way Plans | 18 | ROW Plans | 15d | ROW Plans Preparation- 50100 This activity consists of completing final right of way plans. | The activity is needed when a project has a right of way phase. | This activity is not needed when a project does not have a right of way phase or it has been determined that right of way is not required. | PFPR has been held and inspection report distributed. | Final ROW plans have been completed, submitted and approved by ROW, and submitted to PM. |  | Yes, the duration will vary based on the length of project and number of parcels impacted. |  |  |  | Roadway Design Engineer |  |  |  | Outside of office: This is a performance metric activity within our office that is measured based on baseline finish date. Internal to office: This is a performance metric activity that is measured based on baseline finish date for outside of office evaluation. | N | Roadway Design Engineer | 425 | Item | employeecenter/SAM/Lists/SAM
ROW Plans Final Approval | 50400 | RIGHT OF WAY | ROW;#21 | Task Dependent | PM Request PFPR, Environmental Certification for ROW Authorization Complete, Submit Right of Way Plans, FHWA Approval of Draft EIS, L & D Approval, Environmental Approval Complete (if state funds: Env. Activities Complete) | ROW Authorization | 18 | ROW Plans | 40d | ROW Plans Submission, plan review and ROW Plan approval | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | ROW Plans Submission | Plan corrections are completed, environmental cleared (if applicable), Plans approved |  | General Note: 1. Projects with parcels which are owned by one of the major railroad companies (CSX or NS) |  |  |  | n/a |  |  |  |  | N |  | 426 | Item | employeecenter/SAM/Lists/SAM
L & D Approval | 60100 | DESIGN POLICY & SUPPORT | General;#26 | Task Dependent | Develop, Approve & Publish Notice of Decision (NOD), Environmental Approval Complete (if state funds: Env. Activities Complete), PM Submit L & D Report | L & D Approval Advertisement, ROW Authorization, ROW Plans Final Approval | 17 | Location and Design | 12d | L & D Approval: Activity consists of review of L&D report for correctness & compliance with state code, and submission to Director of Engineering and Chief Engineer for management approval. For NEPA projects, the date of L&D Approval is added upon confirmation of approval of the environmental document (GEPA L&D approval is not tied to the environmental document). Approved L&D Reports are placed on ProjectWise and ArchiveStore. Upon L&D approval for GDOT let projects, the dated L&D advertisement is sent to the appropriate District Planning & Programming Engineer(s) for advertisement in accordance with state code. For local let projects, the local gov’t sponsor is responsible for the advertisement (dated ad sent to PM to coordinate advertisement). Activity 60100 begins upon receipt of L&D Report for approval, and ends when Date of L&D Approval is determined. Note: after activity is complete, proof of the advertisement should be sent back to my team. Upon receipt of proof of advertisement completion, tear sheets or other provided proof is placed on ProjectWise and the ArchiveStore in the folder where the approved L&D report is stored. | required by state code for all projects where eminent domain may be used to acquire property rights | not required for projects where property rights will not be acquired through condemnation/eminent domain. | Start date is when L&D report is submitted by PM for review & approval; End date is when date of location and design approval is placed on report by DP&S after Chief Engineer approves report. Preceded by activity 60050 | End date is when date of location and design approval is placed on report by DP&S after Chief Engineer approves report | [5 empty] | n/a |  |  |  |  | N |  | 427 | Item | employeecenter/SAM/Lists/SAM
PM Submit L & D Report | 60050 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Implementation of ROW Footprint Comments (with steps), Develop, Approve & Publish Notice of Decision (NOD), Preliminary Plans Complete, Verify PFPR Responses, PM Distributes PFPR Responses, ROW Plans Preparation, Management Concept Approval Complete | L & D Approval | 17 | Location and Design | 1d | [10 empty] | n/a |  |  |  |  | N |  | 428 | Item | employeecenter/SAM/Lists/SAM
Location and Design Summary | 60000 | PROGRAM DELIVERY | PM;#18 | WBS Summary |  |  | 17 | Location and Design | 352d | [10 empty] | n/a |  |  |  |  | N |  | 429 | Item | employeecenter/SAM/Lists/SAM
L & D Approval Advertisement | 60500 | PROGRAM DELIVERY | General;#26 | Task Dependent | L & D Approval | ROW Negotiations and Acquisition Work | 17 | Location and Design | 60d | [10 empty] | n/a |  |  |  |  | N |  | 430 | Item | employeecenter/SAM/Lists/SAM
ROW Acquisition Summary | 70000 | RIGHT OF WAY | ROW;#21 | WBS Summary |  |  | 19 | ROW Acquisition (if needed) | 181d |  | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | ROW authorized | District Certification |  | General Note: 2. Projects with parcels owned by DNR or other federally owned parcels. |  |  |  | n/a |  |  |  |  | N |  | 431 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Appraisal and Review | 71000 | RIGHT OF WAY | ROW;#21 | Task Dependent | ROW Authorization | Stake ROW | 19 | ROW Acquisition | 70d | (DISTRICTS) The first appraisal completed on the project is the start date and the last appraisal received on the project is the end date. This date is entered by the Acquisition team in the respective district. | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | First Appraisal on the project start date | last appraisal is received on the project |  | General Note: 4. The attached shows the additional time needed for acquisition for complex parcels, relocation parcels and for projects with a larger number of parcels. |  |  |  | n/a |  |  |  |  | Y |  | 432 | Item | employeecenter/SAM/Lists/SAM
ROW Authorization | 70400 | PROGRAMMING | ROW;#21 | Finish Milestone | ROW Plans Final Approval, Environmental Approval Complete (if state funds: Env. Activities Complete), Environmental Certification for ROW Authorization Complete, FHWA Approval of Environmental Reevaluation, PFPR Inspection to ROW Authorization, L & D Approval | Row Auth to Let, Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, ROW Negotiations and Acquisition Work | 19 | ROW Acquisition (if needed) | 0d | When the Office of Financial Management completes the ROW Authorization documentation. | It is needed by all projects that need ROW purchased | when there is no ROW on a project | When the Office of Financial Management receives the 1625 from ROW | When the Office of Financial Management completes the ROW Authorization documentation. |  | *Process generally takes from 1 day to 3 months to complete. The time can be extended if FHWA has a question on STIP, TIP, funding, etc.If a project is state funded, it has authorized PE funding when the 1625 system documentation is official. * If a project is PODI (has full FHWA oversight), it will skip Engineering Services review. *Documents listing steps for authorizations are available in ProjectWise in the SAM Programming folder | [8 empty] | N |  | 433 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE ROW Real Property Agreement | 70500 | RIGHT OF WAY | ROW;#21 | Task Dependent | ROW Authorization | ROW Notice to Proceed | 19.1 | LOC ROW Acquisition | 45d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 434 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE ROW Estimate for Authorization | 70200 | RIGHT OF WAY | ROW;#21 | Task Dependent | ROW Plans Final Approval | ROW Authorization | 19 | ROW Acquisition | 20d | HISTORICAL: NOT IN GENESIS TEMPLATE Receipt and final review and approval of the ROW Detailed Cost Estimate | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | ROW assigned to District for cost estimate | Receipt of detailed cost estimate |  | General Note: 3. Projects with a large number of complex parcels including the above mentioned parcels, commercial urban parcels, complex relocation parcels and other sensitive type areas (cemetery, church, tribal) |  |  |  | n/a |  |  |  |  | Y |  | 435 | Item | employeecenter/SAM/Lists/SAM
Environmental Certification for ROW Authorization Complete | 70300 | ENVIRONMENTAL SERVICES | Environmental;#5;#ROW;#21 | Task Dependent | Update Ecology Studies, Complete Environmental Reevaluation (with steps), Develop, Approve & Publish Notice of Decision (NOD), FHWA Approval of Environmental Reevaluation, Update Noise Assessments Update History Studies, Receive Revised Plans & Change Form (if changes made as a result of PFPR, circulate to Env. Team), Update Air Quality Analysis, Submit Environmental Reevaluation to FHWA, Update History Studies, Update Noise Assessments, Update Archaeology Studies, Environmental Approval Complete (if state funds: Env. Activities Complete) | ROW Authorization, ROW Plans Final Approval | 16.13 | Environmental Certification for ROW Authorization | 5d | Environmental Certification for ROW Authorization Complete Environmental Certification for ROW Authorization *NEPA P6 Team Member Activity also includes review of plans to certify that ROW amounts are accurate |  | 70300 (Env cert ROW) not needed when project is Local ROW because we do not have an action to certify. | When the project is ready to be certified for ROW; when the NEPA team member receives a Project Change Request to Access Potential Impacts (PCRAPI) form from PM or Design | When the project has been certified for ROW; when the PSCRAPI form has been sent to the SME's. | [5 empty] | n/a |  |  |  |  | N | n/a | 436 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Stake ROW | 72000 | DISTRICT OFFICE | ROW;#21 | Task Dependent | Appraisal and Review | ROW Negotiations | 19 | ROW Acquisition | 30d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 437 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE ROW Notice to Proceed | 70550 | RIGHT OF WAY | ROW;#21 | Start Milestone | L & D Approval Advertisement, ROW Real Property Agreement | G.O. ROW Certification, ROW Negotiations | 19.1 | LOC ROW Acquisition | 0d | [6 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 438 | Item | employeecenter/SAM/Lists/SAM
ROW Negotiations and Acquisition Work | 73000 | RIGHT OF WAY | ROW;#21 | Task Dependent | Develop, Approve & Publish Notice of Decision (NOD), L & D Approval Advertisement, ROW Notice to Proceed, Review Consultant UST/HW Phase II Report, Stake ROW, UST/HW Phase II Report Preparation | Complete, Environmental Certification for Let Complete, G.O. ROW Certification | 19 | ROW Acquisition (if needed) | 181d | (DISTRICTS) The onset of negotiations through District Certification completes this activity. | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | ROW authorized | Last parcel has been closed or condemned or District Certification | [5 empty] | n/a |  |  |  |  | N |  | 439 | Item | employeecenter/SAM/Lists/SAM
Request Soil Survey/Ex Pvmt Eval | 80200 | PROGRAM DELIVERY | PM;#18;#Soil Survey;#52 | Start Milestone | Start Preliminary Roadway Plans, Conduct QA of Preliminary Geometry, Preliminary Roadway Plans (consultant design), Define Project Concept | Soil Survey Report Preparation, Procurement for Soil Survey | 11 | Soil Survey | 0d | [15 empty] | N |  | 440 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant Soil Survey | 80650 | OMAT | Soil Survey;#52 | Task Dependent | Soil Survey Report Preparation | PM Request FFPR, PM Request PFPR | 11 | Soil Survey | 40d | This activiy includes a review by OMAT engineers of a complete soil survey investigation done by outside consultants. | This activity is needed for all projects except Maintenance, Traffic Ops, Safety, or Enhancement projects. It is done for projects where an outside consultant has been contracted by procurement to do the done the soil survey investigation. | This activity is not needed for Maintenance (resurfacing, landscaping, lighting), Traffic Ops (traffic signals, ATMS, intersection improvements), Safety, or Enhancement projects. | when OMAT receives a complete soil survey review request including letter, 2 copies of project plans, a property owners list, and a complete consultant soil survey investigation report from a PM | The activity is complete when the PM receives an approved soil survey investigation report. |  | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. |  |  |  | n/a |  |  |  | Evaluation is pass/fail depending on whether PM receives the final soil survey report within the 40 day duration. | N |  | 441 | Item | employeecenter/SAM/Lists/SAM
Soil Survey Report Preparation | 80600 | OMAT | Soil Survey;#52 | Task Dependent | Request Soil Survey/Ex Pvmt Eval, Procurement for Soil Survey | PM Request FFPR, Review Local/Consultant Soil Survey | 11 | Soil Survey | 60d | The activity includes assigning the soil survey request to an OMAT engineer to do a cost estimate after receiving a complete soil survey request from a PM. If the cost estimate is $25k, the project is assigned to an in house consultant according to the project location. If the cost estimate is $25k, the project is sent to procurement to get a consultant contract for the soil survey investigation report. OMAT engineers review all consultant soil survey investigations. | This activity is needed for all projects except Maintenance, Traffic Ops, Safety, or Enhancement projects. It is done for projects where the soil survey investigation will be done by OMAT engineers in house or where the in house consultant contract is used to assign the soil survey investigation and the completed soil survey investigation is reviewed by OMAT engineers. | This activity is not needed for Maintenance (resurfacing, landscaping, lighting), Traffic Ops (traffic signals, ATMS, intersection improvements), Safety, or Enhancement projects. | when OMAT receives a complete soil survey request including letter, 2 copies of project plans, and a property owners list) from a PM | The activity is complete when the PM receives an approved soil survey investigation report. |  | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. There are some Drilling Only contracts where consultants collect samples and deliver the samples to OMAT and OMAT engineers do the complete soil survey investigation. |  |  |  | n/a |  |  |  | Evaluation is pass/fail depending on whether PM receives the final soil survey report within the 180 day duration. | N |  | 442 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Review Consultant HMP Foundation Report | 80682 | OMAT | General;#26 | Task Dependent | HMP Foundation Investigation Preparation | Request/Receive Final Lighting Plans | 15 | High Mast Poles | 40d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 443 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE HMP Summary | 80655 | OMAT | General;#26 | WBS Summary |  |  | 15 | High Mast Poles | 278d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 444 | Item | employeecenter/SAM/Lists/SAM
BFI Report Summary | 80700 | PROGRAM DELIVERY | Bridge;#7;#BFI;#53 | WBS Summary |  |  | 14 | BFI Report | 185d | Process from PM request to receipt of approved BFI report? | activity needeed for all bridge projects | This activity is only needed for bridge projects. | when OMAT receives a complete BFI request including letter, 2 copies of BFI project plans, and a property owners list) from a PM | The activity is complete when the PM receives an approved BFI investigation report. | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. |  |  |  |  | n/a |  |  |  | Evaluation is pass/fail depending on whether PM receives the final soil survey report within the 180 day duration. | N |  | 445 | Item | employeecenter/SAM/Lists/SAM
Request BFI | 80800 | PROGRAM DELIVERY | Bridge;#7;#BFI;#53 | Start Milestone | Develop Wall Envelopes, Local/Consultant Preliminary Bridge Plans Accepted/Approved, Preliminary Bridge Layout Development (non-stream), Bridge Hydraulic Study and Layout Development (over stream) | BFI Report Preparation, Foundation Recommendation Letter (Bridge 1), Foundation Recommendation Letter (Bridge 2), Foundation Recommendation Letter (Bridge 3), Foundation Recommendation Letter (Bridge 4), Foundation Recommendation Letter (Bridge 5), Foundation Recommendation Letter (Bridge 6), Loads Letter (Bridge 1), Loads Letter (Bridge 2), Loads Letter (Bridge 3), Loads Letter (Bridge 4), Loads Letter (Bridge 5), Loads Letter (Bridge 6), Procurement for BFI | 14 | BFI Report | 0d | Process from PM request to receipt of approved BFI report? | activity needeed for all bridge projects | This activity is only needed for bridge projects. | when OMAT receives a complete BFI request including letter, 2 copies of BFI project plans, and a property owners list) from a PM | The activity is complete when the PM receives an approved BFI investigation report. | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. | [9 empty] | N |  | 446 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE HMP Foundation Investigation Preparation | 80680 | OMAT | General;#26 | Task Dependent | Request Foundation Investigation for High Mast Poles | Request/Receive Final Lighting Plans, Review Consultant HMP Foundation Report | 15 | High Mast Poles | 275d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 447 | Item | employeecenter/SAM/Lists/SAM
Soil Survey Summary | 80100 | PROGRAM DELIVERY | Soil Survey;#52 | WBS Summary |  |  | 11 | Soil Survey | 180d | This activity includes receiving soil survey request, producing or reviewing soil survey, and sending PM the soil survey report. | This activity is needed for all projects except Maintenance, Traffic Ops, Safety, or Enhancement projects. It is done for projects where the soil survey investigation will be done by OMAT engineers in house or where the in house consultant contract is used to assign the soil survey investigation and the completed soil survey investigation is reviewed by OMAT engineers. | [8 empty] | n/a |  |  |  |  | N |  | 448 | Item | employeecenter/SAM/Lists/SAM
BFI Report Preparation | 81200 | OMAT | Bridge;#7;#BFI;#53 | Task Dependent | Procurement for BFI, Foundation Recommendation Letter (Bridge 1), Loads Letter (Bridge 1), Request BFI | Develop Final Construction Cost Estimate (with steps), Final Bridge Plans Preparation, Request/Receive Bridge Constructability Review (over stream), Review Local/Consultant BFI | 14 | BFI Report | 120d | The activity includes assigning the Bridge Foundation Investigation project to an OMAT engineer upon receiving a complete BFI request from a PM. An OMAT engineer will do all of the work required to complete the BFI report | This activity is only needed for bridge projects. | This activity is only needed for bridge projects. | when OMAT receives a complete BFI request including letter, 2 copies of BFI project plans, and a property owners list) from a PM | The activity is complete when the PM receives an approved BFI investigation report. | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. |  |  |  |  | n/a |  |  |  | Evaluation is pass/fail depending on whether PM receives the final soil survey report within the 180 day duration. | N |  | 449 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Request Foundation Investigation for High Mast Poles | 80660 | OMAT | General;#26 | Task Dependent | Preliminary Roadway Plans (consultant design), Request/Receive Preliminary Lighting Plans, Start Preliminary Roadway Plans, Submit Preliminary Plans to GDOT Offices (consultant design), Submit Preliminary Plans to GDOT Offices (with steps) | HMP Foundation Investigation Preparation | 15 | High Mast Poles | 3d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 450 | Item | employeecenter/SAM/Lists/SAM
Final Roadway Plans LOE (in house design) | 81311 | ROADWAY DESIGN | Roadway;#22 | Level Of Effort | Start Final Roadway Plans | Submit FFPR Plans to PM for FFPR | 20.2 | Final Roadway Plans | 160d | [10 empty] | n/a |  |  |  |  | N |  | 451 | Item | employeecenter/SAM/Lists/SAM
Complete/Submit Environmental Change Form | 81312 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Environmental Approval Complete, Final Construction Plans, Implementation of ROW Footprint Comments (with steps), PM Distributes PFPR Responses, Start Final Roadway Plans | Receive Plans & Change Form (if needed); Circulate to Environmental Team | 20.9 | Final Design Phase | 10d | [10 empty] | Roadway Design Engineer |  | As Late As Possible |  |  | N |  | 452 | Item | employeecenter/SAM/Lists/SAM
Final Design Phase Summary | 81300 | ROADWAY DESIGN | Roadway;#22 | WBS Summary |  |  | 20.9 | Final Design Phase | 597d | [10 empty] | Project Manager |  |  |  |  | N |  | 453 | Item | employeecenter/SAM/Lists/SAM
Develop Final Typical Sections | 81322 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Start Final Roadway Plans | Develop Final Drainage Design, QA Review of Final Roadway Plans (with steps), Submit Second Submission Utility Plans to PM, Develop Final Horizontal Alignment, Develop Final Staging Plans | 20.2 | Final Roadway Plans | 10d | Develop Final Typical Sections | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 454 | Item | employeecenter/SAM/Lists/SAM
Review Local/Consultant BFI | 81250 | OMAT | BFI;#53;#Bridge;#7 | Task Dependent | BFI Report Preparation | Develop Final Construction Cost Estimate (with steps), Final Bridge Plans Preparation, Request/Receive Bridge Constructability Review (over stream) | 14 | BFI Report | 40d | This activiy includes a review by OMAT engineers of a complete soil survey investigation done by outside consultants. | This activity is only needed for bridge projects. | This activity is only needed for bridge projects. | when OMAT receives a complete soil survey review request including letter, 2 copies of project plans, a property owners list, and a complete consultant soil survey investigation report from a PM | The activity is complete when the PM receives an approved soil survey investigation report. | Projects in areas where the soils are known to have hazards need the soil survey at PFPR per PDP. Clay soils, coastal sandy soils, and solid rock may cause changes in the project design or location. The soil survey must be done before PFPR so that design or ROW alternatives can be evaluated. |  |  |  |  | n/a |  |  |  | Evaluation is pass/fail depending on whether PM receives the final soil survey report within the 40 day duration. | N |  | 455 | Item | employeecenter/SAM/Lists/SAM
Start Final Roadway Plans | 81317 | ROADWAY DESIGN | Roadway;#22 | Start Milestone | Environmental Approval Complete (if state funds: Env. Activities Complete), Implementation of ROW Footprint Comments (with steps), PM Distributes PFPR Responses, Preliminary Plans Complete, Submit 1st Submission RR Package to PM, Verify PFPR Responses, Conduct Utility Field Meeting, Review Pavement Type Selection | Final Bridge Plans Preparation, Submit Plans to Environmental for Permit Applications, Wall Plans Preparation, Request/Receive Final Lighting Plans, Complete/Submit Environmental Change Form, Develop Final Cross Sections (with steps), Final Roadway Plans LOE (in house design), Develop Final Vertical Alignment, QA Review of Final Roadway Plans (with steps), Develop Final Typical Sections, Develop Final Signing & Marking Plans, Develop Final Horizontal Alignment, Develop Final Signalization Plans | 20.2 | Final Roadway Plans | 0d | 81317,81322,81332,81342,81352,81372,81382,81522,81532,81562,81592,81713-Final Design Activities - Start Final Roadway Plans. These are activities required to complete final design plans. | This activity is needed for all in house design projects. | When design is consulted out. | PFPR has been held and inspection report distributed. |  |  | yes- the project type, length and complexity will impact the duration of the activities. | [8 empty] | N | Roadway Design Engineer | 456 | Item | employeecenter/SAM/Lists/SAM
Develop Final Horizontal Alignment | 81332 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Typical Sections, Start Final Roadway Plans | Develop Final Drainage Design, Develop Final Erosion Control Plans, Develop Final Signing & Marking Plans, Develop Final Staging Cross Sections, Develop Final Staging Plans, Develop Final Vertical Alignment, QA Review of Final Roadway Plans (with steps), Submit Second Submission Utility Plans to PM | 20.2 | Final Roadway Plans | 5d | Develop Final Horizontal Alignment | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 457 | Item | employeecenter/SAM/Lists/SAM
Develop Final Cross Sections (with steps) | 81352 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Vertical Alignment, Start Final Roadway Plans | Develop Final Drainage Design, Develop Final Erosion Control Plans, Develop Final Staging Cross Sections, Develop Final Staging Plans, QA Review of Final Roadway Plans (with steps), Request/Receive Utilities Second Submission, Submit Second Submission Utility Plans to PM | 20.2 | Final Roadway Plans | 10d | Develop Final Cross Sections (with steps) | This activity is needed for all in house design projects. | When design is consulted out. | [6 empty] | 1 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 458 | Item | employeecenter/SAM/Lists/SAM
Develop Final Drainage Design | 81382 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Cross Sections (with steps), Develop Final Horizontal Alignment, Develop Final Typical Sections, Develop Final Vertical Alignment | Develop Final Construction Cost Estimate (with steps), Develop Final Erosion Control Plans, Develop Final Staging Plans, QA Review of Final Roadway Plans (with steps), Submit Plans to Environmental for Permit Applications | 20.2 | Final Roadway Plans | 10d | Develop Final Drainage Design | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 459 | Item | employeecenter/SAM/Lists/SAM
Develop Final Vertical Alignment | 81342 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Horizontal Alignment, Start Final Roadway Plans | Develop Final Cross Sections (with steps), Develop Final Drainage Design, Develop Final Erosion Control Plans, Develop Final Staging Cross Sections, Develop Final Staging Plans, QA Review of Final Roadway Plans (with steps), Submit Second Submission Utility Plans to PM | 20.2 | Final Roadway Plans | 5d | Develop Final Vertical Alignment | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 460 | Item | employeecenter/SAM/Lists/SAM
Submit Plans to Environmental for Permit Applications | 81397 | ROADWAY DESIGN | Roadway;#22 | Start Milestone | Develop Final Drainage Design, Develop Final Erosion Control Plans, Develop Final Staging Cross Sections, Final Construction Plans, Start Final Roadway Plans | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Let Contract, OES Receives and Reviews Plans for Application, Prepare Buffer Variance (with steps), Submit Corrected FFPR Plans, Submit Final Plans for CST Bidding | 20 | Final Design Phase | 0d | Submit Plans to Environmental for Permit Applications | This activity is needed for all in house design projects. | When design is consulted out. |  |  |  | 81397 is a leading indicator for final design. | [5 empty] | As Late As Possible |  |  | N | Roadway Design Engineer | 461 | Item | employeecenter/SAM/Lists/SAM
Final Construction Plans | 81400 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Environmental Approval Complete (if state funds: Env. Activities Complete) , Implementation of ROW Footprint Comments (with steps), PM Distributes PFPR Responses, Preliminary Plans Complete, Preliminary Roadway Plans Complete, Review Pavement Type Selection, Consultant Kick-off Meeting, Conduct Utility Field Meeting | PM Reviews FFPR Package, Request/Receive Final Lighting Plans, Request/Receive Utilities Second Submission, Utility Agreements Preparation and Certification, Final Bridge Plans Preparation, Submit Plans to Environmental for Permit Applications, Final Construction Plans Complete, Complete/Submit Environmental Change Form, Wall Plans Preparation | 20.1 | Local and Consultant Design Activities for Final Plans | 100d | Final Construction Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 462 | Item | employeecenter/SAM/Lists/SAM
Develop Final Staging Cross Sections | 81532 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Cross Sections (with steps), Develop Final Horizontal Alignment, Develop Final Staging Plans, Develop Final Vertical Alignment | Develop Final Erosion Control Plans, Develop Special Provisions, QA Review of Final Roadway Plans (with steps), Submit Plans to Environmental for Permit Applications | 20.2 | Final Roadway Plans | 10d | Develop Final Staging Cross Sections | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 463 | Item | employeecenter/SAM/Lists/SAM
Develop Final Staging Plans | 81522 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Cross Sections (with steps), Develop Final Drainage Design, Develop Final Horizontal Alignment, Develop Final Typical Sections, Develop Final Vertical Alignment | Develop Final Staging Cross Sections, QA Review of Final Roadway Plans (with steps) | 20.2 | Final Roadway Plans | 10d | Develop Final Staging Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 464 | Item | employeecenter/SAM/Lists/SAM
Submit Second Submission Utility Plans to PM | 81517 | ROADWAY DESIGN | Roadway;#22;#PM;#18;#Utilities;#15 | Start Milestone | Develop Final Cross Sections (with steps), Develop Final Horizontal Alignment, Develop Final Signalization Plans, Develop Final Typical Sections, Develop Final Vertical Alignment, Request/Receive Final Lighting Plans | QA Review of Final Roadway Plans (with steps), Receive Utility Relocations and Plot Utilities, Request/Receive Utilities Second Submission | 20.2 | Final Roadway Plans | 0d | Submit Second Submission Utility Plans to PM | This activity is needed for all in house design projects. | When design is consulted out. |  |  |  | 81517 is a leading indicator for final design. | [8 empty] | N | Roadway Design Engineer | 465 | Item | employeecenter/SAM/Lists/SAM
Develop Final Signing & Marking Plans | 81372 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Horizontal Alignment, Start Final Roadway Plans | Develop Final Construction Cost Estimate (with steps), QA Review of Final Roadway Plans (with steps) | 20.2 | Final Roadway Plans | 10d | Develop Final Signing & Marking Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 466 | Item | employeecenter/SAM/Lists/SAM
Develop Final Construction Cost Estimate (with steps) | 81592 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Wall Plans Preparation, Develop Special Provisions, Receive Utility Relocations and Plot Utilities, Develop Final Drainage Design, Develop Final Erosion Control Plans, Final Bridge Plans Preparation, Review Local/Consultant BFI, Local/Consultant Final Bridge Plans Accepted/Approved, Develop Final Signing & Marking Plans, Request/Receive Final Lighting Plans, Develop Final Signalization Plans, BFI Report Preparation | QA Review of Final Roadway Plans (with steps) | 20.2 | Final Roadway Plans | 15d | Develop Final Construction Cost Estimate (with steps) | This activity is needed for all in house design projects. | When design is consulted out. | [6 empty] | 2 | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 467 | Item | employeecenter/SAM/Lists/SAM
Transmit approved pavement design to PM for FFPR | 81629 | OMAT | Pavement;#14;#PM;#18;#FFPR;#17 | Finish Milestone | Review Pavement Design | QA Review of Final Roadway Plans (with steps), PM Reviews PFPR Package | 12.6.8 | Pavement Design Review | 0d | Zero day duration activity to document the sending of the approved pavement design package to the PM. All work done in project wise. Notification is just an e-mail with link to approved package. | When 81600 is used | When 81600 is not used | Day Pavement Design is transmitted | Day Pavement Design is transmitted | Required for PFPR, is in the PFPR Checklist | [8 empty] | We are rated on baseline schedule | N |  | 468 | Item | employeecenter/SAM/Lists/SAM
Develop Final Erosion Control Plans | 81562 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Drainage Design, Develop Final Cross Sections (with steps), Develop Final Horizontal Alignment, Develop Final Staging Cross Sections, Develop Final Vertical Alignment | Develop Special Provisions, QA Review of Final Roadway Plans (with steps), Submit Plans to Environmental for Permit Applications, Develop Final Construction Cost Estimate (with steps) | 20.2 | Final Roadway Plans | 30d | Develop Final Erosion Control Plans | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 469 | Item | employeecenter/SAM/Lists/SAM
Receive Utility Relocations and Plot Utilities | 81792 | ROADWAY DESIGN | Roadway;#22;#Utilities;#15 | Task Dependent | Request/Receive Utilities Second Submission, Submit Second Submission Utility Plans to PM | Develop Final Construction Cost Estimate (with steps), QA Review of Final Roadway Plans (with steps) | 20.2 | Final Roadway Plans | 5d | Receive Utility Relocations and Plot Utilities | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 470 | Item | employeecenter/SAM/Lists/SAM
Submit Final Signalization Plans | 81717 | ROADWAY DESIGN | Roadway;#22 | Finish Milestone | QA Review of Final Roadway Plans (with steps), Final Roadway Plans LOE (in house design), Request/Receive Utilities Second Submission, Final Bridge Plans Preparation | PM Reviews FFPR Package, Final Construction Plans Complete | 20.2 | Final Roadway Plans | 0d | [15 empty] | N |  | 471 | Item | employeecenter/SAM/Lists/SAM
QA Review of Final Roadway Plans (with steps) | 81713 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Construction Cost Estimate (with steps), Develop Final Horizontal Alignment, Develop Final Cross Sections (with steps), Request/Receive Utilities Second Submission, Develop Final Vertical Alignment, Transmit Approved Pavement Design to PM for FFPR, Develop Final Staging Cross Sections, Start Final Roadway Plans, Receive Utility Relocations and Plot Utilities, Submit Second Submission Utility Plans to PM, Develop Final Drainage Design, Develop Final Signalization Plans, Develop Special Provisions, Develop Final Signing & Marking Plans, Develop Final Staging Plans, Develop Final Typical Sections, Develop Final Erosion Control Plans | Final Construction Plans Complete, Submit FFPR Plans to PM for FFPR, PM Reviews FFPR Package | 20.2 | Final Roadway Plans | 20d | QA Review of Final Roadway Plans (with steps) | This activity is needed for all in house design projects. | When design is consulted out. | [6 empty] | 4 | Roadway Design Quality Assurance |  |  |  |  | N | Roadway Design Engineer | 472 | Item | employeecenter/SAM/Lists/SAM
Develop Special Provisions | 81782 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Develop Final Erosion Control Plans, Develop Final Staging Cross Sections, Final Bridge Plans Preparation, Local/Consultant Final Bridge Plans Accepted/Approved, Request/Receive Final Lighting Plans, Wall Plans Preparation | Develop Final Construction Cost Estimate (with steps), QA Review of Final Roadway Plans (with steps) | 20.2 | Final Roadway Plans | 5d | Develop Special Provisions | This activity is needed for all in house design projects. | When design is consulted out. | [7 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 473 | Item | employeecenter/SAM/Lists/SAM
Review Pavement Design | 81600 | OMAT | Pavement;#14 | Task Dependent | Start Preliminary Roadway Plans, Submit Pavement Design to OMAT for Approval, Preliminary Roadway Plans (consultant design), PM submits Pavement Design for approval | Conduct Pavement Type Selection Report, Transmit Approved Pavement Design to PM for FFPR | 12.6.8 | Local and Consultant Design Activities for Preliminary Plans | 40d | This is the review of the Pavement Design Package. See PDP 6.4.2 Pavement Design, Pavement Design Review, and/or Pavement Design Approval: Pavement design work or review of the pavement designs for a project, and approval by the State Pavement Design Engineer. | This activity is needed for all in house design projects. Needed for all projects with full depth pavement. Some projects can use the minor pavement project guidelines but the designer always has the option to do their own pavement design per PDP 6.4.2 | Some program types may not need pavement designs. That clarification is being worked on. See PDP Chapter 10.2.6 for some clarification on local projects that do not require. | Traffic must be approved in order to complete your pavement designs. These activities are requested by PMs by email to the State Pavement Design Engineer that includes links to the appropriate files in ProjectWise, Pavement Design: The start date should be when OMAT receives the pavement design package for review and approval by the State Pavement Design Engineer. | Pavement Design: These activities are complete when the pavement design package is approved and signed by the State Pavement Engineer. OMAT, Road Design, and consultants do pavement design for GDOT projects. Road Design and consultants submit their pavement designs to OMAT for approval. OMAT sends an email to the PM with a signed letter pdf to notify them that the Pavement Design package documents have been approved and saved into ProjectWise. | Required for PFPR, is in the PFPR Checklist | No significant time difference to complete Pavement Design for project types. Pavement Design. Should be approved generally in 30 days. Internal roadway projects are reviewed by the COG group in Roadway before going to OMAT, see the PW process detailed earlier. All consultant design projects go straight to OMAT. Usually revisions are needed so min 30 days max 60 days for activity. All of these activities are detailed in the PDP pavement design and approval process flowchart. (insert link to Pavement Design Manual) <a href="http://www.dot.ga.gov/PartnerSmart/DesignSoftware/ProjectWise/Pavement%20Design%20Submission%20and%20Approval%20Process.pdf">http://www.dot.ga.gov/PartnerSmart/DesignSoftware/ProjectWise/Pavement%20Design%20Submission%20and%20Approval%20Process.pdf</a> | PES: See PDP 6.3.4 PTS: See PDP 6.4.2 |  |  | n/a |  |  |  | We are evaluated based on the baseline finish date for our scorecard for all these activities. Our office is not interested in duration and have stuck with the baseline date for evaluation. We have been tasked once these activities are fixed to preemptively search for projects that could be falling behind baseline and inform the project manager of the deficiency. | N |  | 474 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Utilities Second Submission | 82000 | PROGRAM DELIVERY | PM;#18;#Utilities;#15 | Task Dependent | Develop Final Cross Sections (with steps), Final Construction Plans, PM Distributes PFPR Responses, Submit Second Submission Utility Plans to PM, Verify PFPR Responses | QA Review of Final Roadway Plans (with steps), Receive Utility Relocations and Plot Utilities, Utility Agreements Preparation and Certification, Submit FFPR Plans to PM for FFPR, Final Construction Plans Complete, PM Reviews FFPR Package | 20.9 | Final Design Phase | 60d | Request/Receive Utilities Second Submission | [9 empty] | n/a |  | As Late As Possible |  |  | N |  | 475 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Final Roadway Plans Complete | 81799 | ROADWAY DESIGN | Roadway;#22 | Finish Milestone | Final Bridge Plans Preparation, Final Construction Plans, Final Roadway Plans LOE (in house design), Local/Consultant Final Bridge Plans Accepted/Approved, ODPS Submits PCSR to EPD, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, PM Reviews Final Plans, QA Review of Final Roadway Plans (with steps), Request/Receive Final Lighting Plans, Request/Receive Utilities Second Submission, Submit Preliminary Plans to Utilities for Impacted Railroads, Wall Plans Preparation | Bid Documents Review, CST AUTH Requested, FFPR Request (OES), Final Construction Plans Complete, G.O. ROW Certification, PM Request FFPR, Transportation Enhancement Agreement Approval, Utility Agreements Preparation and Certification | 20.2 | Final Roadway Plans | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE Final Roadway Plans Complete -81779 This is the completion of final FFPR plans. | This activity is needed for all in house design projects. | When design is consulted out. |  |  |  | no-this is a milestone activity with 0 duration | [7 empty] | This activity is measured within our office based on meeting the baseline finish date. | Y | Roadway Design Engineer | 476 | Item | employeecenter/SAM/Lists/SAM
Submit Final Plans to Utilities for Impacted RR | 82020 | PROGRAM DELIVERY | PM;#18;#Railroad;#42;#Utilities;#15 | Task Dependent | PM Distributes PFPR Responses, PM Request FFPR, Submit Preliminary Plans to Utilities for Impacted Railroads, Verify PFPR Responses | Railroad Agreements Preparation and Certification | 20.2 | Railroad Activities | 60d | Submit Final plans to utilities RR Safety team who will review and forward to the impacted RR for RR signal design When FFPR is requested, using the Railroad Submission Checklist found on the Utilities website, the PM and Design team put together the Final Railroad Submission Package. This Final Railroad Submission Package is then sent to the Office of Utilities, who will review for completeness and then send it on to the appropriate railroad company for their review/approval. The PM is to submit the package to the Utilities office attention Railroad Liaison, currently Jill Franks, and Railroad Specialist, currently Marcela Coll. If the railroad has comments on the Final Railroad Submission Package then the PM and Design team review the railroad comments and revise their plans to address the comment(s). The PM and Design team also need to respond to the railroad’s comments in a written format explaining how they address the comment(s) or explain why they were unable to fulfill the railroad’s request. The Revised final plans along with the written responses are then put together for the REVISED Final Railroad Submission Package, following the Railroad Submission Checklist found on the Utilities website and sent to the Office of Utilities, who will review for completeness and then send it on to the appropriate railroad company for their review/approval. This process is repeated until the Railroad has approved the Final plans.. | For the RR safety team: This activity is needed when there are RR active warning device equipment impacted by the project or recommended to be installed by the RR crossing Engineer This activity is needed for every project that required Railroad Coordination, which is determined by the Utilities Office. | When there are no RR active warning devices included in the project. This activity is not needed when the Office of Utilities deems railroad impacts do not exist. If activity 82020 does not apply then activity 21500 and 95250 will not apply either. | Start date is the date Utilities receives the plans The start date represent the date the Final Railroad Submission Package is submitted to the Office of Utilities by the PM. | Should be the same as the Start date The end date represents the day the Railroad sends the Final plans approval email/letter to the office of Utilities |  | If a project has any length of railroad track design, the duration of the activity should be lengthen from 60 days to 85 days. Final Railroad Submission Package is to be sent to the Office of Utilities no later than 28 weeks prior to the project let date. At this point the railroad parcel is “Locked down.”; “Final Lockdown Plans” are plans to which there can be no changes to the plans that will affect the railroad property, unless requested by the railroad. Any other revisions resulting from the FFPR that will impact the letting schedule will require pre-approval from the Director of Engineering. The railroads are very particular on the design of their railroad tracks and it generally takes two full years to get the railroad to approve the track design, especially with Norfolk Southern. After the railroad approved the plans then the ROW office can close on any railroad parcels to purchase the Permanent Easement Construction Agreement with the Railroad: |  |  |  | n/a |  |  |  | We are tracking metrics to see if we are either sending comments back to the PM/Designer or sending out the Railroad Submission Package within 7 calendar days and the railroad is reviewing the submission package within the deadline we give them which can range from 30-60 calendar days. We should be evaluated using the current method explained above. | N |  | 477 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Bridge Constructability Review (over stream) | 82332 | PROGRAM DELIVERY | PM;#18;#Bridge;#7 | Task Dependent | BFI Report Preparation, Review Local/Consultant BFI | PM Request FFPR, PM Reviews FFPR Package, Final Bridge Plans Preparation | 20.3.3 | Final Design Phase | 20d | [6 empty] | Has to be signed by the RR by FHWA Certification date | [8 empty] | N |  | 478 | Item | employeecenter/SAM/Lists/SAM
Develop Final Signalization Plans | 81772 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Start Final Roadway Plans | Develop Final Construction Cost Estimate (with steps), QA Review of Final Roadway Plans (with steps), Submit Second Submission Utility Plans to PM | 20.2 | Final Roadway Plans | 5d | Final Signalization Plans -81772 : This activity consists of developing signal plans. | This activity is needed for all in house design projects. | When design is consulted out. |  |  |  | This activity is measured within our office based on meeting the baseline finish date. |  | This activity should be changed to “Request Signal Plans from Traffic Ops” and moved under Preliminary Design Activities with activity 21372 as a predecessor. Roadway Design no longer has expertise to complete signal plans and no longer does this work. |  | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 479 | Item | employeecenter/SAM/Lists/SAM
Final Bridge Design Summary | 82300 | BRIDGE | Bridge;#7 | WBS Summary |  |  | 20.3.3 | Final Bridge Design | 120d | Summary of final bridge design activities. | After completion of PFPR. | Bridge replacement, widening or reconfiguration within the limits of project. | After completion of PFPR. | Completion of final bridge plans. End date is 50 days after completion of BFI. Must be completed before activity 81717 – Submit final bridge plans to PM for FFPR. |  | Railroad will provide CEI Force Account Estimate (FAE) |  |  |  | n/a |  |  |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 480 | Item | employeecenter/SAM/Lists/SAM
Final Bridge Plans Preparation | 82400 | BRIDGE | Bridge;#7 | Task Dependent | Local/Consultant Preliminary Bridge Plans Accepted/Approved, Local/Consultant Final Bridge Plans Accepted/Approved, Start Final Roadway Plans, Review Local/Consultant BFI, Final Construction Plans, Loads Letter (Bridge 1), Environmental Approval Complete (if state funds: Env. Activities Complete), Foundation Recommendation Letter (Bridge 1), BFI Report Preparation, Develop Wall Envelopes, Request/Receive Bridge Constructability Review (over stream) | PM Reviews FFPR Package, Develop Special Provisions, Submit FFPR Plans to PM for FFPR, Develop Final Construction Cost Estimate (with steps), Final Construction Plans Complete | 20.3.3 | Final Bridge Design | 120d | Development of final bridge plans. | After completion of PFPR. | Bridge replacement, widening or reconfiguration within the limits of project. | After completion of PFPR. | Completion of final bridge plans. End date is 50 days after completion of BFI. Must be completed before activity 81717 – Submit final bridge plans to PM for FFPR. Must be completed before activity – Submit plans to environmental for permit application (lock down plans). |  | Engineering Services will include TProWeb construction agreement amount in the project constr. authorization budget |  |  |  | Bridge Design Engineer |  |  |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 481 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 2) | 82422 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Foundation Recommendation Letter (Bridge 1) | 20.3.1.2 | Bridge 2 (optional) | 0d | Letter received from the Lab that recommends the type of foundation of the 2nd bridge of a project. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | Railroad takes 1 month to sign Construction Agreement | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 482 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 1) | 82421 | BRIDGE | Bridge;#7 | Finish Milestone | Foundation Recommendation Letter (Bridge 2), Foundation Recommendation Letter (Bridge 3), Foundation Recommendation Letter (Bridge 4), Foundation Recommendation Letter (Bridge 5), Foundation Recommendation Letter (Bridge 6), Local/Consultant Preliminary Bridge Plans Accepted/Approved, Request BFI | BFI Report Preparation, Final Bridge Plans Preparation, Loads Letter (Bridge 1), Local/Consultant Final Bridge Plans Accepted/Approved | 20.3.1.1 | Bridge 1 | 0d | Letter received from the Lab that recommends the type of foundation of the 1st bridge of a project. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | Ranges from $20K to $300K (or $3-4 Million if underpass project; Construction Agreement with the Railroad: | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 483 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 3) | 82423 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Foundation Recommendation Letter (Bridge 1) | 20.3.1.3 | Bridge 3 (optional) | 0d | Letter received from the Lab that recommends the type of foundation of the 3rd bridge of a project. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | Need RR Approval of Final plans 3 months before letting | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 484 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 4) | 82424 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Foundation Recommendation Letter (Bridge 1) | 20.3.1.4 | Bridge 4 (optional) | 0d | Letter received from the Lab that recommends the type of foundation of the 4th bridge of a project. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | After RR Approval – ROW office can finalize Easement Documents and purchase the Easement | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 485 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 5) | 82425 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Foundation Recommendation Letter (Bridge 1) | 20.3.1.5 | Bridge 5 (optional) | 0d | Letter received from the Lab that recommends the type of foundation of the 5th bridge. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 486 | Item | employeecenter/SAM/Lists/SAM
Foundation Recommendation Letter (Bridge 6) | 82426 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Foundation Recommendation Letter (Bridge 1) | 20.3.1.6 | Bridge 6 (optional) | 0d | Letter received from the Lab that recommends the type of foundation of the 6th bridge. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 80 days before completion of BFI. |  |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 487 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 2) | 82442 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Loads Letter (Bridge 1) | 20.3.1.2 | Bridge 2 (optional) | 0d | Letter sent to the Lab that contains the loads required on the Bridge 2 foundation. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 488 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 3) | 82443 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Loads Letter (Bridge 1) | 20.3.1.3 | Bridge 3 (optional) | 0d | Letter sent to the Lab that contains the loads required on the Bridge 3 foundation. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 489 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 1) | 82441 | BRIDGE | Bridge;#7 | Finish Milestone | Foundation Recommendation Letter (Bridge 1), Loads Letter (Bridge 2), Loads Letter (Bridge 3), Loads Letter (Bridge 4), Loads Letter (Bridge 5), Loads Letter (Bridge 6), Local/Consultant Preliminary Bridge Plans Accepted/Approved, Request BFI | BFI Report Preparation, Final Bridge Plans Preparation, Local/Consultant Final Bridge Plans Accepted/Approved | 20.3.1.1 | Bridge 1 | 0d | Letter sent to the Lab that contains the loads required on the Bridge 1 foundation. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 490 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 4) | 82444 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Loads Letter (Bridge 1) | 20.3.1.4 | Bridge 4 (optional) | 0d | Letter sent to the Lab that contains the loads required on the Bridge 4 foundation. | In-house design ONLY Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 491 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 5) | 82445 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Loads Letter (Bridge 1) | 20.3.1.5 | Bridge 5 (optional) | 0d | Letter sent to the Lab that contains the loads required on the Bridge 5 foundation. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 492 | Item | employeecenter/SAM/Lists/SAM
Loads Letter (Bridge 6) | 82446 | BRIDGE | Bridge;#7 | Finish Milestone | Request BFI | Loads Letter (Bridge 1) | 20.3.1.6 | Bridge 6 (optional) | 0d | Letter sent to the Lab that contains the loads required on the Bridge 6 foundation. | In-house design ONLY. Bridge replacement, widening or reconfiguration within the limits of project. | Consultant Design or no bridge replacement, widening or reconfiguration within the limits of project. | 60 days before completion of BFI. | 60 days before completion of BFI. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 493 | Item | employeecenter/SAM/Lists/SAM
Local/Consultant Final Bridge Plans Accepted/Approved | 82499 | BRIDGE | Bridge;#7 | Finish Milestone | Receive Local/Consultant Final Bridge Plans for 1st Review (40 days prior to completion), Receive Local/Consultant Final Bridge Plans for 2nd/Final Review (10 days prior to completion), Foundation Recommendation Letter (Bridge 1), Loads Letter (Bridge 1) | Develop Special Provisions, Final Bridge Plans Preparation, Final Construction Plans Complete, PM Reviews FFPR Package, Develop Final Construction Cost Estimate (with steps) | 20.3.2 | Local/Consultant Final Bridge Plan Review | 0d | Approval of consultant final bridge plans. | Bridge replacement, widening or reconfiguration within the limits of project. | No bridge replacement, widening or reconfiguration within the limits of project. | Completion of final bridge plans. | Completion of final bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [7 empty] | Graded – completion of preliminary bridge plans before finish date. | N |  | 494 | Item | employeecenter/SAM/Lists/SAM
Wall Plans Preparation | 82500 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | Final Construction Plans, Start Final Roadway Plans, Start Preliminary Roadway Plans | Develop Final Construction Cost Estimate (with steps), Develop Special Provisions, Final Construction Plans Complete, Final Roadway Plans Complete, PM Reviews FFPR Package | 20 | Final Design Phase | 40d | [10 empty] | Bridge Design Engineer |  |  |  |  | N |  | 495 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Final Bridge Plans for 2nd/Final Review (10 days prior to completion) | 82487 | BRIDGE | Bridge;#7 | Start Milestone | Receive Local/Consultant Final Bridge Plans for 1st Review (40 days prior to completion) | Local/Consultant Final Bridge Plans Accepted/Approved | 20.3.2 | Local/Consultant Final Bridge Plan Review | 0d | 2nd review of final preliminary bridge plans (non-steam or over stream) for review. | Bridge replacement, widening or reconfiguration within the limits of project when consultants are developing bridge plans. | No bridge replacement, widening or reconfiguration within the limits of project. | 40 days prior to completion of final bridge plans. PM. | 40 days prior to completion of final bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 496 | Item | employeecenter/SAM/Lists/SAM
Final Construction Plans Complete | 87000 | ROADWAY DESIGN | Roadway;#22 | Finish Milestone | Submit FFPR Plans to PM for FFPR, QA Review of Final Roadway Plans (with steps), Local/Consultant Final Bridge Plans Accepted/Approved, Wall Plans Preparation, PM Reviews FFPR Package, Submit Preliminary Plans to Utilities for Impacted Railroads, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, ODPS Submits PCSR to EPD, Final Bridge Plans Preparation, Final Construction Plans, Request/Receive Utilities Second Submission, Request/Receive Final Lighting Plans | PM Request FFPR, G.O. ROW Certification, FFPR Request (OES) | 20.9 | Local and Consultant Design Activities for Final Plans AND IN HOUSE | 0d | [15 empty] | N |  | 497 | Item | employeecenter/SAM/Lists/SAM
PM Reviews Final Plans | 86500 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Request/Receive Bridge Constructability Review (over stream), Final Bridge Plans Preparation, Final Construction Plans, Wall Plans Preparation, Local/Consultant Final Bridge Plans Accepted/Approved, Request /Receive Final Lighting Plans, QA Review of Final Roadway Plans (with steps), Submit FFPR Plans to PM for FFPR, Request/Receive Utilities Second Submission | Final Construction Plans Complete | 20.9 | Final Design Phase | 5d | [10 empty] | n/a |  |  |  |  | N |  | 498 | Item | employeecenter/SAM/Lists/SAM
Receive Local/Consultant Final Bridge Plans for 1st Review (40 days prior to completion) | 82477 | BRIDGE | Bridge;#7 | Start Milestone |  | Local/Consultant Final Bridge Plans Accepted/Approved, Receive Local/Consultant Final Bridge Plans for 2nd/Final Review (10 days prior to completion) | 20.3.2 | Local/Consultant Final Bridge Plan Review | 0d | 1st review of consultant final bridge plans (non-steam or over stream) for review. | Bridge replacement, widening or reconfiguration within the limits of project when consultants are developing bridge plans. | No bridge replacement, widening or reconfiguration within the limits of project. | 40 days prior to completion of final bridge plans. PM. | 40 days prior to completion of final bridge plans. |  | Length of bridge, type of bridge, complexity of bridge, complexity of hydraulics study, FEMA involvement, Coast Guard involvement, railroad involvement, complexity of geometry, environmental ESA, species, historic properties, historic bridges, utilities, constructability, etc. all make a difference in the time to complete. | [5 empty] | As Late As Possible |  | Graded – completion of preliminary bridge plans before finish date. | N |  | 499 | Item | employeecenter/SAM/Lists/SAM
OES Receives and Reviews Plans for Application | 88222 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Environmental Approval Complete (if state funds: Env. Activities Complete), Submit Plans to Environmental for Permit Applications | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Environmental Certification for Let Complete, Prepare Buffer Variance (with steps), Update Ecology Studies | 16.14 | Permits | 10d | [6 empty] | 88222= should be connected to 18814 (update ecology); the name of activity 88222 should include a reference to “lockdown plans” for the permit; because that is what the activity is used for. Maybe add 88222, 88233, 88253 altogether and make more steps. But if there is no permit, those activities should not be added together. |  |  |  | Ecologist |  | As Late As Possible |  |  | N | Ecologist | 500 | Item | employeecenter/SAM/Lists/SAM
Request/Receive Final Lighting Plans | 82700 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Final Construction Plans, Request/Receive Preliminary Lighting Plans, Start Final Roadway Plans | Develop Special Provisions, PM Reviews FFPR Package, Develop Final Construction Cost Estimate (with steps), Final Construction Plans Complete, Submit Second Submission Utility Plans to PM | 20.9 | Final Design Phase | 20d | [10 empty] | n/a |  |  |  |  | N |  | 501 | Item | employeecenter/SAM/Lists/SAM
404 Individual Permit - JPN Activities (only add if individual 404 permit) | 88234 | ENVIRONMENTAL SERVICES | Environmental;#5;#Permits;#56 | Task Dependent | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit | Construction Authorization, Environmental Certification for Let Complete, Issue NTP 3, Let Contract, Prepare Buffer Variance (with steps) | 16.14.1 | 404 Permit | 40d | 404 Individual Permit - JPN Activities (only if IP required) Permits (65 or 100 days Total) *Ecology P6 Team Member Activity | only if IP required | if IP not required | when the JPN (Joint Public Notice) is published | when the public comment period has ended and all public comments have been addressed |  | 88234 & 88253 can be done concurrently |  |  |  | n/a |  | As Late As Possible |  |  | N | n/a | 502 | Item | employeecenter/SAM/Lists/SAM
404 and Buffer Variance (BV) Permits LOE | 88231 | ENVIRONMENTAL SERVICES | Environmental;#5;#Permits;#56 | Level Of Effort | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Prepare Buffer Variance (with steps) | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Prepare Buffer Variance (with steps) | 16.14 | Permits | 115d | [10 empty] | n/a |  |  |  |  | N | n/a | 503 | Item | employeecenter/SAM/Lists/SAM
PM Submits Interim FPR Responses to ES | 89145 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Interim FPR Report Approval and Distribution | Verify Interim FPR Responses (ES) | 2.11 | Interim FPR | 10d | [10 empty] | n/a |  |  |  |  | N |  | 504 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Request (ES) | 89110 | ENGINEERING SERVICES | General;#26 | Task Dependent | PM Request Interim FPR | Interim FPR Inspection | 2.11 | Interim FPR | 20d | Interim FPR Request - date when complete Interim FPR QA/QC request accepted by ES from PM | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Interim FPR. | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | Date when complete Interim FPR request is submitted by PM | Date that scheduling letter or Waiver letter is sent out for the Interim FPR or the date that the letter is sent to the District for them to schedule and hold. | [5 empty] | n/a |  |  |  |  | N |  | 505 | Item | employeecenter/SAM/Lists/SAM
PM Request Interim FPR | 89105 | PROGRAM DELIVERY | PM;#18 | Start Milestone | PM Distributes PFPR Responses | Interim FPR Request (ES) | 2.11 | Interim FPR | 0d |  |  | Interim FPRs are needed if there is < 30 months between management ROW date and management LET date. | [12 empty] | N |  | 506 | Item | employeecenter/SAM/Lists/SAM
Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit | 88233 | ENVIRONMENTAL SERVICES | Permits;#56 | Task Dependent | Environmental Approval Complete (if state funds: Env. Activities Complete), ROW Authorization, Receive Environmental Study Area Layout / Start Environmental Studies, Submit Plans to Environmental for Permit Applications, 404 and Buffer Variance (BV) Permits LOE, Environmental Approval Complete, OES Receives and Reviews Plans for Application | 404 and Buffer Variance (BV) Permits LOE, Let Contract, Construction Authorization, Environmental Certification for Let Complete, Prepare Buffer Variance (with steps), 404 Individual Permit – JPN Activities (only add if individual 404 permit) | 16.14.1 | 404 Permit | 65d | Complete 404 Permit (with steps Applicable tasks (7 Steps • 404 Permit Application Preparation• 404 Permit Application GDOT Review• 404 Permit Submission• 404 Permit Review by Resource Agency• USACE Public Notice (PCN or JPN)• USACE Prepares and Issues 404 Permit• Purchase of 404 Mitigation Credits NWP/RP(Nationwide) = 65 days IP(individual permit) = 100 days Permits (65 or 100 days Total) *Ecology P6 Team Member Activity | Ecology team member would know if permits needed and what type of permit is needed from activities 13463 and 13467 and by evaluation of the plans | a. 88233= Permits not always needed (ex: maintenance projects or projects with no impacts to waters). | when the preparation of the 404 Permit application is begun | when the ecology team member has the 404 Permit authorization and mitigation credits have been purchased b. 88233- Complete permit= The steps listed with this activity aren’t indicative of the true work/deliverables. When we click finish we usually have not totally met all steps listed under this activity. We do not wait until mitigation has been completed before clicking complete on this activity. We click complete when the permit verification is received by the USACE. We are unaware of when mitigation has been purchased. |  |  |  |  | 7 | Ecologist |  | As Late As Possible |  |  | N | Ecologist | 507 | Item | employeecenter/SAM/Lists/SAM
Prepare Buffer Variance (with steps) | 88253 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | 404 Individual Permit - JPN Activities (only add if individual 404 permit), 404 and Buffer Variance (BV) Permits LOE, Environmental Approval Complete (if state funds: Env. Activities Complete), OES Receives and Reviews Plans for Application, Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Submit Plans to Environmental for Permit Applications | 404 and Buffer Variance (BV) Permits LOE, Let Contract, Environmental Certification for Let Complete, Construction Authorization | 16.14.2 | Vegetative Buffer Variance (BV) | 85d | Prepare Buffer Variance (with steps) Applicable tasks (4 Steps) • Prepare BV Application• GDOT Review of BV Application• Submit BV Application to EPD• BV Public Notice Permits (65 or 100 days Total) *Ecology P6 Team Member Activity |  | b. 88253= BV not always needed (ex: when no impacts to stream buffers). | when OES begins preparing the BV Application. | when you have received the BV and mitigation credits have been purchased. |  | 88234 & 88253 can be done concurrently |  |  | 4 | Ecologist |  | As Late As Possible |  |  | N | Ecologist | 508 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Inspection | 89120 | ENGINEERING SERVICES | General;#26 | Task Dependent | Interim FPR Request (ES) | Interim FPR Report Preparation | 2.11 | Interim FPR | 1d | Interim FPR Inspection - attending Interim FPR meeting and site visit inspection or preparing and sending waiver letter for Interim FPR | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Interim FPR. | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | Date of Interim FPR. Note: If we waive the Interim FPR, put the date you sent out the Waiver Letter here. | Same date as the Interim FPR. | [5 empty] | n/a |  |  |  |  | N |  | 509 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Report Preparation | 89130 | ENGINEERING SERVICES | General;#26 | Task Dependent | Interim FPR Inspection | Interim FPR Report Approval and Distribution | 2.11 | Interim FPR | 10d | Interim FPR Report Preparation - Comments from Interim FPR meeting are compiled and Interim FPR report produced | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Interim F | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | Next working date after the Interim FPR Inspection. Note: If the report goes out the same date of the inspection, then the date of the inspection should be placed here. | The date you distribute the report or send it over to FHWA for approval on applicable PoDI projects. | [5 empty] | n/a |  |  |  |  | N |  | 510 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Report Approval and Distribution | 89140 | ENGINEERING SERVICES | General;#26 | Task Dependent | Interim FPR Report Preparation | PM Submits Interim FPR Responses to ES, Verify Interim FPR Responses (ES) | 2.11 | Interim FPR | 0d | Interim FPR Report Approval and Distribution - Interim FPR report is approved and distributed. It is sent to FHWA for signatures if it is a PoDI project. | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Interim FPR. | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | The date the report is sent over to FHWA on applicable PoDI projects. On all other projects, this will be the date the report is distributed. | The date the report is received from FHWA on applicable PoDI projects and is distributed. On all other projects, this will be the date the report is distributed. | [5 empty] | n/a |  |  |  |  | N |  | 511 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Summary | 89100 | ENGINEERING SERVICES | General;#26 | WBS Summary |  |  | 2.11 | Interim FPR | 46d | Interim Field Plan Review - from when ES receives a complete Interim FPR request from PM for QA/QC review of a complete set of project plans at different milestones to the PM receiving approval on all responses to the Interim FPR report | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. The interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Final FPR. | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | This date automatically comes up from beginning date of activity 89110 | This date automatically comes up from end date of activity 89150. | [5 empty] | n/a |  |  |  |  | N |  | 512 | Item | employeecenter/SAM/Lists/SAM
Supplemental FFPR Summary | 89200 | ENGINEERING SERVICES | General;#26 | WBS Summary |  |  | 2.13 | Supplemental FFPR | 41d | Supplemental Final Field Plan Review - from when ES receives a complete Supplemental FFPR request from PM for QA/QC review of a complete set of project plans at different milestones to the PM receiving approval on all responses to the final Supplemental FFPR report | This activity is needed when plans are of poor quality, need major revisions,or when a project's scope changes.&nbsp; The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc. Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | This date automatically comes up from beginning date of activity 89210 | This date automatically comes up from end date of activity 89250 | [5 empty] | n/a |  |  |  |  | N |  | 513 | Item | employeecenter/SAM/Lists/SAM
PM Distributes Interim FPR Responses | 89155 | PROGRAM DELIVERY | PM;#18;#General;#26 | Finish Milestone | Verify Interim FPR Responses (ES) | G.O. ROW Certification, Implementation of FFPR Comments, PM Request FFPR, PM Request Supplemental FFPR, Submit Corrected FFPR Plans, Submit Final Plans for CST Bidding | 2.11 | Interim FPR | 0d | [15 empty] | N |  | 514 | Item | employeecenter/SAM/Lists/SAM
Verify Interim FPR Responses (ES) | 89150 | ENGINEERING SERVICES | General;#26 | Task Dependent | Interim FPR Report Approval and Distribution, PM Submits Interim FPR Responses to ES | PM Distributes Interim FPR Responses | 2.11 | Interim FPR | 5d | Verify Interim FPR Responses - Final Interim FPR report is approved and distributed. | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date. Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to FFPR. | Interim FPRs are not needed if there is < 30 months between management ROW date and management LET date. | Date the PM submits responses to ES for acceptance. | Date that PM is notified that the responses are acceptable. | [5 empty] | n/a |  |  |  | These activities are and should be evaluated on whether or not the allowable time frames are met. | N |  | 515 | Item | employeecenter/SAM/Lists/SAM
PM Request Supplemental FFPR | 89205 | PROGRAM DELIVERY | PM;#18;#General;#26 | Start Milestone | PM Distributes FFPR Responses, PM Distributes Interim FPR Responses, PM Distributes PFPR Responses | Supplemental FFPR Request (ES) | 2.13 | Supplemental FFPR | 0d | FFPR Request - date when complete FFPR QA/QC request accepted by ES from PM | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | [12 empty] | N |  | 516 | Item | employeecenter/SAM/Lists/SAM
Supplemental FFPR Request (ES) | 89210 | ENGINEERING SERVICES | General;#26 | Task Dependent | PM Request Supplemental FFPR | Supplemental FFPR Inspection | 2.13 | Supplemental FFPR | 20d | Supplemental FFPR Request - date when complete Supplemental FFPR QA/QC request accepted by ES from PM | This activity is needed when plans are of poor quality, need major revisions or when a project's scope changes. The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc. Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | Date when complete Supplemental FFPR request is submitted by PM | Date that scheduling letter or Waiver letter is sent out for the Supplemental FFPR or the date that the letter is sent to the District for them to schedule and hold. | [5 empty] | n/a |  |  |  |  | N |  | 517 | Item | employeecenter/SAM/Lists/SAM
Supplemental FFPR Inspection | 89220 | ENGINEERING SERVICES | General;#26 | Task Dependent | Supplemental FFPR Request (ES) | Supplemental FFPR Report Preparation | 2.13 | Supplemental FFPR | 1d | Supplemental FFPR Inspection - attending Supplemental FFPR meeting and site visit inspection or preparing and sending waiver letter for Supplemental FFPR | This activity is needed when plans are of poor quality, need major revisions or when a project's scope changes. The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | Date of Supplemental FFPR. | Same date unless the Supplemental FFPR is a two day inspection. | [5 empty] | n/a |  |  |  |  | N |  | 518 | Item | employeecenter/SAM/Lists/SAM
Supplemental FFPR Report Preparation | 89230 | ENGINEERING SERVICES | General;#26 | Task Dependent | Supplemental FFPR Inspection | Supplemental FFPR Report Approval and Distribution | 2.13 | Supplemental FFPR | 10d | Supplemental FFPR Report Preparation - Comments from Supplemental FFPR meeting are compiled and Supplemental FFPR report produced | This activity is needed when plans are of poor quality, need major revisions or when a project's scope changes. The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc. Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | Next working date after the Supplemental FFPR Inspection. Note: If the report goes out the same date of the inspection, then the date of the inspection should be placed here. | The date you distribute the report or send it over to Supplemental FHWA for approval on applicable PoDI projects. | [5 empty] | n/a |  |  |  |  | N |  | 519 | Item | employeecenter/SAM/Lists/SAM
Supplemental FFPR Report Approval and Distribution | 89240 | ENGINEERING SERVICES | General;#26 | Task Dependent | Supplemental FFPR Report Preparation | PM Submits Supplemental FFPR Responses to OES, Verify Supplemental FFPR Responses (ES) | 2.13 | Supplemental FFPR | 0d | Supplemental FFPR Report Approval and Distribution - Supplemental FFPR report is approved and distributed. It is sent to FHWA for signatures if it is a PoDI project. | This activity is needed when plans are of poor quality, need major revisions or when a project's scope changes. The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc. Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | The date the report is sent over to Supplemental FHWA on applicable PoDI projects On all other projects, this will be the date you distributed the report. | The date the report is received from Supplemental FHWA on applicable PoDI projects and is distributed. On all other projects, this will be the date you distributed the report. | [5 empty] | n/a |  |  |  |  | N |  | 520 | Item | employeecenter/SAM/Lists/SAM
PM Submits Supplemental FFPR Responses to ES | 89245 | PROGRAM DELIVERY | PM;#18;#General;#26 | Task Dependent | Supplemental FFPR Report Approval and Distribution | Verify Supplemental FFPR Responses (ES) | 2.13 | Supplemental FFPR | 10d | [10 empty] | n/a |  |  |  |  | N |  | 521 | Item | employeecenter/SAM/Lists/SAM
Verify Supplemental FFPR Responses (ES) | 89250 | ENGINEERING SERVICES | General;#26 | Task Dependent | PM Submits Supplemental FFPR Responses to OES, Supplemental FFPR Report Approval and Distribution | PM Distributes Supplemental FFPR Responses | 2.13 | Supplemental FFPR | 5d | Verify Supplemental FFPR Responses - Final Supplemental FFPR report is approved and distributed. | This activity is needed when plans are of poor quality, need major revisions or when a project's scope changes. The need is determined on a project by project basis. However, Supplemental FFPR's are required, per the PDP, if the Management LET date is more than 2 years after FFPR. | Supplemental FFPR's are not needed if plans are of good quality, no major revisions have occurred, no major scope changes, etc Supplemental FFPRs are not required if the Management LET date is less than two years from the FFPR. | Date the PM submits responses to ES for acceptance. | Date that PM is notified that the responses are acceptable. | [5 empty] | n/a |  |  |  | These activities are and should be evaluated on whether or not the allowable time frames are met. | N |  | 522 | Item | employeecenter/SAM/Lists/SAM
PM Distributes Supplemental FFPR Responses | 89255 | PROGRAM DELIVERY | PM;#18;#General;#26 | Finish Milestone | Verify Supplemental FFPR Responses (ES) | G.O. ROW Certification, Implementation of FFPR Comments, Submit Corrected FFPR Plans, Submit Final Plans for CST Bidding | 2.13 | Supplemental FFPR | 0d | [15 empty] | N |  | 523 | Item | employeecenter/SAM/Lists/SAM
PM Request FFPR | 89500 | PROGRAM DELIVERY | PM;#18;#General;#26 | Start Milestone | Environmental Approval Complete (if state funds: Env. Activities Complete), Request/Receive Bridge Constructability Review (over stream), Final Construction Plans Complete, PM Distributes Interim FPR Responses, PM Distributes 2nd Interim FPR Responses, PCSR Revisions Post-PFPR (if needed); Submit to ODPS, ODPS Submits PCSR to EPD, PM Posts Corrected PFPR Plans, Submit Preliminary Plans to Utilities for Impacted Railroads, Soil Survey Report Preparation, Review Local/Consultant Soil Survey | FFPR Request (ES), Receive Plans & Change Form (if needed); Circulate to Environmental Team, Submit Final Plans to Utilities for Impacted RR | 20.4 | FFPR | 0d | [15 empty] | N |  | 524 | Item | employeecenter/SAM/Lists/SAM
FFPR Summary | 90000 | ENGINEERING SERVICES | General;#26 | WBS Summary |  |  | 20.4 | FFPR | 46d |  | This activity is needed for all projects and should be held a minimum of 24 weeks prior to CST Authorization. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | This date automatically comes up from beginning date of activity 90100 | This date automatically comes up from end date of activity 90400 | [5 empty] | n/a |  |  |  |  | N |  | 525 | Item | employeecenter/SAM/Lists/SAM
FFPR Inspection | 90200 | ENGINEERING SERVICES | General;#26 | Task Dependent | FFPR Request (OES) | FFPR Report Preparation, Let Contract, FFPR Inspection to Let Contract | 20.4 | FFPR | 1d | FFPR Inspection - attending FFPR meeting and site visit inspection or preparing and sending waiver letter for FFPR | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | Date of FFPR. Note: If we waive the FFPR, put the date you sent out the Waiver Letter here. | Same date unless the FFPR is a two day inspection. NOTE: If we waive the FFPR, put the date you sent out the Waiver Letter here. | [5 empty] | n/a |  |  |  |  | N |  | 526 | Item | employeecenter/SAM/Lists/SAM
Maintenance Project Final Plans Review by ES | 90110 | ENGINEERING SERVICES | General;#26 | Task Dependent | Environmental Approval Complete (if state funds: Env. Activities Complete) | Construction Authorization | 20.5 | Maintenance Activities | 2d | Maintenance Plan QA/QC Review Request submitted by PM and OES completes Inspection and Approval | This activity is needed for all maintenance projects except bridge maintenance projects. | This activity is not needed for projects other than maintenance projects. | Date when OES accepts a Maintentence QA/QC package from the PM | Date when Maintentence QA/QC is completed by OES | [5 empty] | n/a |  |  |  |  | N |  | 527 | Item | employeecenter/SAM/Lists/SAM
FFPR Request (ES) | 90100 | ENGINEERING SERVICES | General;#26 | Task Dependent | Final Construction Plans Complete, PM Request FFPR | FFPR Inspection | 20.4 | FFPR | 20d | FFPR Request - date when complete FFPR QA/QC request accepted by OES from PM | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | Date when complete FFPR request is submitted by PM | Date that scheduling letter or Waiver letter is sent out for the FFPR or the date that the letter is sent to the District for them to schedule and hold. | [5 empty] | n/a |  |  |  |  | N |  | 528 | Item | employeecenter/SAM/Lists/SAM
FFPR Report Preparation | 90300 | ENGINEERING SERVICES | General;#26 | Task Dependent | FFPR Inspection | FFPR Report Approval and Distribution | 20.4 | FFPR | 10d | FFPR Report Preparation - Comments from FFPR meeting are compiled and FFPR report produced | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | Next working date after the FFPR Inspection. Note: If the report goes out the same date of the inspection, then the date of the inspection should be placed here. | The date you distribute the report or send it over to FHWA for approval on applicable PoDI projects. | [5 empty] | n/a |  |  |  |  | N |  | 529 | Item | employeecenter/SAM/Lists/SAM
Verify FFPR Responses (ES) | 90400 | ENGINEERING SERVICES | General;#26 | Task Dependent | FFPR Report Approval and Distribution, PM Submits FFPR Responses to OES | Implementation of FFPR Comments, PM Distributes FFPR Responses, Submit Corrected FFPR Plans, Submit Final Plans for CST Bidding | 20.4 | FFPR | 5d | Verify FFPR Responses - Final FFPR report is approved and distributed. | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | Date the PM submits responses to ES for acceptance. | Date that PM is notified that the responses are acceptable. | [5 empty] | n/a |  |  |  |  | N |  | 530 | Item | employeecenter/SAM/Lists/SAM
PM Distributes FFPR Responses | 90450 | PROGRAM DELIVERY | PM;#18;#General;#26 | Finish Milestone | Verify FFPR Responses (ES) | G.O. ROW Certification, Implementation of FFPR Comments, PM Request Supplemental FFPR, Submit Corrected FFPR Plans, Submit Final Plans for CST Bidding | 20.4 | FFPR | 0d | completion of FFPR report activity |  |  | last date of activity 90400 | last date of activity 90400 | [10 empty] | N |  | 531 | Item | employeecenter/SAM/Lists/SAM
Final Submittals Summary | 95000 | ROADWAY DESIGN | Roadway;#22 | WBS Summary |  |  | 21 | Final Submittals | 90d | [10 empty] | Project Manager |  |  |  |  | N |  | 532 | Item | employeecenter/SAM/Lists/SAM
Submit Final Plans | 95100 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | G.O. ROW Certification, Environmental Certification for Let Complete, PM Distributes FFPR Responses, Verify FFPR Responses (ES), Submit Plans to Environmental for Permit Applications, Implementation of FFPR Comments, Submit Corrected FFPR Plans, PM Distributes Supplemental FFPR Responses, PM Distributes Interim FPR Responses, Utility Agreements Preparation and Certification | Construction Authorization, Let Contract, Project Advertisement | 21 | Final Submittals | 0d | [10 empty] | n/a |  |  |  |  | N |  | 533 | Item | employeecenter/SAM/Lists/SAM
FFPR Report Approval and Distribution | 90350 | ENGINEERING SERVICES | General;#26 | Task Dependent | FFPR Report Preparation | PM Submits FFPR Responses to OES, Verify FFPR Responses (ES) | 20.4 | FFPR | 0d | FFPR Report Approval and Distribution - FFPR report is approved and distributed. It is sent to FHWA for signatures if it is a PoDI project. | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | The date the report is sent over to FHWA on applicable PoDI projects. On all other projects, this will be the date you distributed the report. | The date the report is received from FHWA on applicable PoDI projects and is distributed.On all other projects, this will be the date you distributed the report. | [5 empty] | n/a |  |  |  | These activities are and should be evaluated on whether or not the allowable time frames are met. | N |  | 534 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Receive Utility Certification Package from Locals | 95271 | PROGRAM DELIVERY | PM;#18;#Utilities;#15 | Start Milestone | Request/Receive Utilities First Submission/SUE Coordination, Request/Receive Utilities Second Submission | Utility Agreements Preparation and Certification | 21.2 | LOC Final Submittals | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE Receive Utility Certification Package from Locals | [11 empty] | As Late As Possible |  |  | Y |  | 535 | Item | employeecenter/SAM/Lists/SAM
District Submits Recommendation and Certification Package | 95259 | DISTRICT OFFICE | General;#26 | Finish Milestone | Local Gov Submits Certification Package (local sponsored projects only) | Utility Agreements Preparation and Certification | 21.05 | Utility Certification | 0d | [12 empty] | As Late As Possible |  |  | N |  | 536 | Item | employeecenter/SAM/Lists/SAM
Submit Corrected FFPR Plans | 90500 | PROGRAM DELIVERY | PM;#18 | Finish Milestone | PM Distributes FFPR Responses, PM Distributes Interim FPR Responses, PM Distributes Supplemental FFPR Responses, Submit Plans to Environmental for Permit Applications, Verify FFPR Responses (ES) | Environmental Certification for Let Complete, Let Contract, Submit Final Plans for CST Bidding, Utility Agreements Preparation and Certification | 24 | Final Submittals | 0d | [12 empty] | As Late As Possible |  |  | N |  | 537 | Item | employeecenter/SAM/Lists/SAM
Local Gov Submits Certification Package (local sponsored projects only) | 95249 | PROGRAM DELIVERY | PM;#18 | Finish Milestone |  | District Submits Recommendation and Certification Package, Utility Agreements Preparation and Certification | 21.05 | Utility Certification | 0d | [12 empty] | As Late As Possible |  |  | N |  | 538 | Item | employeecenter/SAM/Lists/SAM
Utility Agreements Preparation and Certification | 95300 | UTILITIES | Utilities;#15 | Task Dependent | Request/Receive Utilities Second Submission, Submit Corrected FFPR Plans, Final Construction Plans, Railroad Agreements Preparation and Certification, Local Gov Submits Certification Package (local sponsored projects only), District Submits Recommendation and Certification Package | Construction Authorization, Let Contract, Submit Final Plans for CST Bidding, Utilities Notice to Proceed | 21.05 | Utility Certification | 30d | Utility Agreements Preparation and Certification | [9 empty] | n/a |  | As Late As Possible |  |  | N |  | 539 | Item | employeecenter/SAM/Lists/SAM
Implementation of FFPR Comments | 91312 | ROADWAY DESIGN | Roadway;#22 | Task Dependent | PM Distributes FFPR Responses, PM Distributes Interim FPR Responses, PM Distributes Supplemental FFPR Responses, Verify FFPR Responses (ES) | Submit Final Plans for CST Bidding | 20.2 | Final Roadway Plans | 40d | Implementation of FFPR Comments -91312 This activity consists of updating final plans to address all comments in the FFPR inspection report and prepare plans for submission for letting. | This activity is needed for all in house design projects. | When design is consulted out. | FFPR inspection has been held and FFPR report has been distributed. | Plans are complete and coversheets have been signed. | [5 empty] | Roadway Design Engineer |  |  |  |  | N | Roadway Design Engineer | 540 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Locals Submit Package for Authorization | 95440 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Submit Final Plans | Construction Authorization, Develop Bid Documents | 21.2 | LOC Final Submittals | 1d | HISTORICAL: NOT IN GENESIS TEMPLATE ; package that locals send to Engineering Services with final plans included | [9 empty] | n/a |  |  |  |  | Y |  | 541 | Item | employeecenter/SAM/Lists/SAM
PM Submits FFPR Responses to ES | 90375 | PROGRAM DELIVERY | PM;#18 | Task Dependent | FFPR Report Approval and Distribution | Verify FFPR Responses (ES) | 20.4 | FFPR | 10d | PM has 10 days to review and send any responses to approved FFPR report. | This activity is needed for all projects including bridge maintenance projects but not other maintenance projects. | This activity is not needed for maintenance projects except bridge maintenance projects. Other maintenance projects are checked using a shorter process - activity 90110. | when PM gets final FFPR report, PM has 10 work days to send any comments to be addressed by OES | 10 days after PM received final FFPR report. | [5 empty] | n/a |  |  |  |  | N |  | 542 | Item | employeecenter/SAM/Lists/SAM
Environmental Certification for Let Complete | 95200 | ENVIRONMENTAL SERVICES | Environmental;#5 | Task Dependent | Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, 404 Individual Permit - JPN Activities (only add if individual 404 permit), Environmental Approval Complete (if state funds: Env. Activities Complete), Receive Plans & Change Form (if needed); Circulate to Environmental Team, FHWA Approval of Environmental Reevaluation, Complete Environmental Reevaluation for CST Authorization (with steps), Submit Corrected FFPR Plans, Develop, Approve & Publish Notice of Decision (NOD), OES Receives and Reviews Plans for Application, ROW Negotiations and Acquisition Work, Update Noise Assessments and Public Outreach (with steps), Update Ecology Studies, Update Archaeology Studies, Update Air Quality Analysis, Update History Studies, Prepare Buffer Variance (with steps) | Construction Authorization, Let Contract, Submit Final Plans for CST Bidding | 16.15 | Environmental Certification for CST Authorization | 10d | Environmental Certification for Let Complete Environmental Revaluation and Certification for Let (80-90 days) *NEPA P6 Team Member Activity |  |  | when the document is prepared to be Certified for Let. | when the Certification for Let has been completed. | [5 empty] | NEPA Analyst |  | As Late As Possible |  |  | N | NEPA Analyst | 543 | Item | employeecenter/SAM/Lists/SAM
Railroad Agreements Preparation and Certification | 95250 | UTILITIES | Utilities;#15 | Task Dependent | Submit Final Plans to Utilities for Impacted RR | Let Contract, Utility Agreements Preparation and Certification | 20.2 | Railroad Activities | 30d | RR safety will prepare and route and agreement to the RR for any active warning device equipment work that is reimbursable. This process can take up to 10 months. We can only begin this process once the RR and design team have completed their work in the area of concern as it relates to the warning devices and the RR has provided and estimate for the work and the PM has confirmed that there are funds to cover he work. Once the railroad has approved the final design plans, this activity is for the Utilities Office to write up the Railroad Construction Agreement and the Special Provision for Protection of Railway Interest. It also includes time for the railroad company to sign the Railroad Construction Agreement. We need the railroad to sign the Railroad Construction Agreement before the Office of Utilities can certify the project for the letting. | For the RR safety team This activity is needed when there are RR active warning device equipment impacted by the project or recommended to be installed by the RR crossing Engineer This activity is needed for every project that required Railroad Coordination. | When there is no active warning device work included in the project. This activity is not needed when the Office of Utilities deems railroad impacts do not exist. If activity 95250 does not apply then activity 21500 and 82020 will not apply either. | Start date is the date Utilities receives Force account estimate from the RR. The start date would be when our office starts the preparation of Railroad Construction Agreement, which happened after the railroad has approved the final design plans. | Should be the date we get the partially signed agreement back from the RR The end date would be the date that the Utilities Office certifies the project for letting. We must have received the executed copy of the Railroad Construction Agreement back from the railroad. |  | The number of crossings may affect the time the RR needs to return the agreements for a project. RR Estimates are only good for 1 year. The PM should be mindful when shifting the let dates. If the RR estimate expires, we can potentially end up rerouting the agreement which can add time to the project. Special circumstance #1: (5% Participation projects)If the project eliminates an existing at-grade crossing with active warning devices (bells, lights, gates) and replaces it with a bridge over the railroad tracks, the railroad is required to participate in the portion of the cost of the bridge. This is federally mandated in Title 23, Part 646.210. In these cases, this activity duration should be extended from 30 days to 45 days. It takes the railroad companies more time to approve the participation amount. .Special circumstance #2: (Three Party Agreements)When the project has a roadway bridge that will not be maintained by GDOT, or there are existing at-grade crossings that are being eliminated, a Three Party Agreement will be needed. The Railroads can require the local governments (3rd Party) to sign the Railroad Construction Agreements first, before the railroad signs it. In these three party agreements, this activity duration should be extended from 30 days to 60 days to allow time for the local government to put the Railroad Construction Agreement before their committee/counsel for their signatures. For Three Party Agreements, the local government and the railroad has to sign the agreement before the Office of Utilities can certify the project for letting. There are two Railroad Groups in the office of Utilities. One group is call the Railroad Surface Group and the other is called the Railroad Safety Group. Each group could have an agreement depending on the project.; The Railroad Safety Group would have an agreement for Warning Devices (bells, lights & gates) and the Railroad Surface Group would have agreement for any other type of impact (parallel, at-grade or bridge impacts). Both groups would have to have their agreement signed before certification can occur. Some small railroad companies, called Short lines, do not require a Railroad Construction Agreement and some minor impacts to railroad property do not require a Railroad Construction Agreement. If a Railroad Construction Agreement is not needed, then the project is ready for certification, for the Railroad portion of the Office of Utilities certification, after the Special Provision for Protection of Railway Interest is written and sent to the PM |  |  |  | n/a |  | As Late As Possible |  | We are tracking the metrics to see if the railroad is signing the Railroad Construction Agreement within 30 calendar days. We should be evaluated using the current method explained above. | N |  | 544 | Item | employeecenter/SAM/Lists/SAM
G.O. ROW Certification | 95400 | RIGHT OF WAY | ROW;#21 | Task Dependent | Final Construction Plans Complete, PM Distributes Supplemental FFPR Responses, UST/HW Phase II Report Preparation, PM Distributes Interim FPR Responses, PM Distributes FFPR Responses, ROW Negotiations and Acquisition Work, Review Consultant UST/HW Phase II Report | Construction Authorization, Submit Final Plans for CST Bidding | 21.5 | Final Submittals | 4d | The end of ROW acquisition with the receipt of a District Certification and GO certification including relocation and property management certifications. | When ROW or easement(s) are required for the construction of the project. | For projects constructed within the limits of existing ROW. | District Certification | GO review, relocation & property management certification | [5 empty] | n/a |  |  |  |  | N |  | 545 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Transportation Enhancement Agreement Approval | 95450 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Construction Authorization, Final Construction Plans Complete, Final Roadway Plans Complete | Let Contract | 21.1 | TE Final Submittals - See TE Template | 40d | [10 empty] | n/a |  |  |  |  | Y |  | 546 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE CST AUTH Requested | 95490 | PROGRAM DELIVERY | PM;#18 | Task Dependent | Environmental Approval Complete, Environmental Certification for Let Complete, Final Construction Plans Complete, Final Roadway Plans Complete, G.O. ROW Certification, Utility Agreements Preparation and Certification | Construction Authorization | 21.1 | TE Final Submittals - See TE Template | 1d | [10 empty] | n/a |  |  |  |  | Y |  | 547 | Item | employeecenter/SAM/Lists/SAM
Construction Authorization | 95500 | PROGRAMMING |  | Finish Milestone | Environmental Certification for Let Complete, Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Submit Final Plans for CST Bidding, G.O. ROW Certification, 404 Individual Permit - JPN Activities (only add if individual 404 permit), Maintenance Project Final Plans Review by OES, Prepare Buffer Variance (with steps), Utility Agreements Preparation and Certification | Let Contract, Project Advertisement | 24 | Final Submittals | 0d | When the Office of Financial Management completes the Construction Authorization documentation. | It is needed by all projects | It is needed by all projects. | When the Office of Financial Management receives the 1625 from Engineering Services or from the PM if it is a Local Let project. | When the Office of Financial Management completes the Construction Authorization documentation. |  | *Process generally takes from 1 day to 3 months to complete. The time can be extended if FHWA has a question on STIP, TIP, funding, etc. *If a project is state funded, it has authorized PE funding when the 1625 system documentation is official * If a project is PODI (has full FHWA oversight), it will skip Engineering Services review. *Documents listing steps for authorizations are available in ProjectWise in the SAM Programming folder. | [8 empty] | N |  | 548 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE NTP to Bid to Local Government | 95540 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Develop Bid Documents | Bid Evaluation Review by GDOT, Let Contract | 21.2 | LOC Final Submittals | 1d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 549 | Item | employeecenter/SAM/Lists/SAM
Utilities Notice to Proceed | 95700 | PROGRAM DELIVERY | PM;#18;#Utilities;#15 | Finish Milestone | Utility Agreements Preparation and Certification | Let Contract | 24 | Final Submittals | 0d | Utilities Notice to Proceed | [11 empty] | As Late As Possible |  |  | N |  | 550 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Develop Bid Documents | 95550 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Construction Authorization, Locals Submit Package for Authorization | Let Contract, NTP to Bid to Local Government | 21.2 | LOC Final Submittals | 40d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 551 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Bid Evaluation Review (w/DBE) | 95570 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Bid Documents Review, Let Contract, Project Advertisement | Construction Notice to Proceed | 21.1 | TE Final Submittals - See TE Template | 30d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 552 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Bid Documents Review | 95560 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Final Construction Plans, Final Construction Plans Complete, Final Roadway Plans Complete, PM Reviews Final Plans | Bid Evaluation Review (w/DBE), Let Contract, Project Advertisement | 21.1 | TE Final Submittals - See TE Template | 10d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 553 | Item | employeecenter/SAM/Lists/SAM
Project Advertisement | 95600 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Construction Authorization, Submit Final Plans for CST Bidding | Let Contract | 24 | Final Submittals | 15d | [10 empty] | n/a |  |  |  |  | N |  | 554 | Item | employeecenter/SAM/Lists/SAM
Let Contract | 95800 | CONSTRUCTION BIDDING | General;#26 | Finish Milestone | 404 Individual Permit - JPN Activities (only add if individual 404 permit), Complete 404 Permit (with steps) 65d if Nationwide 100d if Individual Permit, Environmental Certification for Let Complete, FFPR Inspection, Submit Plans to Environmental for Permit Applications, Project Advertisement, Submit Final Plans for CST Bidding, Construction Authorization, Utilities Notice to Proceed, Submit Corrected FFPR Plans, Row Auth to Let, FFPR Inspection to Let, Railroad Agreements Preparation and Certification, Utility Agreements Preparation and Certification, Prepare Buffer Variance (with steps) |  | 24 | Final Submittals | 0d | [15 empty] | N |  | 555 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE CST Agreement Execution | 95820 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Bid Evaluation Review by GDOT, Let Contract | Construction Notice to Proceed | 21.2 | LOC Final Submittals | 1d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 556 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Bid Evaluation Review by GDOT | 95810 | CONSTRUCTION BIDDING | General;#26 | Task Dependent | Let Contract, NTP to Bid to Local Government | CST Agreement Execution | 21.2 | LOC Final Submittals | 1d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 557 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Construction Notice to Proceed | 95900 | CONSTRUCTION BIDDING | General;#26 | Finish Milestone | Bid Evaluation Review (w/DBE), CST Agreement Execution, Let Contract | Construction Final Payment, Transportation Enhancement/ Project Complete | 22 | LOC and TE Project CST Activities | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 558 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Construction | 98332 | CONSTRUCTION | General;#26 | Task Dependent | Issue NTP 3 | Construction Complete | 24.232.22 | Post Let Construction | 480d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 559 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Construction Complete | 98339 | CONSTRUCTION | General;#26 | Finish Milestone | Construction, ROW Negotiations | Post Evaluation Report | 24.232.22 | Post Let Construction | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 560 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Post Evaluation Report | 98342 | CONSTRUCTION | General;#26 | Task Dependent | Construction Complete |  | 24.232.22 | Post Let Construction | 30d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE | [8 empty] | Y |  | 561 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Transportation Enhancement/ Project Complete | 99410 | CONSTRUCTION | General;#26 | Task Dependent | Construction Notice to Proceed | Transportation Enhancement/ Final Acceptance | 22.1 | TE CST Activities | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 562 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Transportation Enhancement/ Final Acceptance | 99420 | CONSTRUCTION | General;#26 | Task Dependent | Transportation Enhancement/ Project Complete |  | 22.1 | TE CST Activities | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 563 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE Construction Final Payment | 99500 | CONSTRUCTION | General;#26 | Finish Milestone | Construction Notice to Proceed |  | 22 | LOC and TE Project CST Activities | 0d | HISTORICAL ACTIVITY - NOT IN CURRENT MASTER TEMPLATE This activity involves the process on the final payment for the contractor and paperwork being sent to the Office of Accounting to start the project close out. | On all Construction projects | This activity will always be needed on construction projects. | This is a milestone date. Start and End date are the same. State Construction Office will process this activity. | This is a milestone date. Start and End date are the same. State Construction Office will process this activity. |  | HISTORICAL: NOT IN GENESIS TEMPLATE & This activity is independent of type, size and complexity. It is always a one-day task. | [8 empty] | Y |  | 564 | Item | employeecenter/SAM/Lists/SAM
HISTORICAL: NOT IN GENESIS TEMPLATE CST Activity Summary | 99000 | CONSTRUCTION | General;#26 | WBS Summary |  |  | 22 | LOC and TE Project CST Activities | 0d | HISTORICAL: NOT IN GENESIS TEMPLATE | [5 empty] | HISTORICAL: NOT IN GENESIS TEMPLATE |  |  |  | n/a |  |  |  |  | Y |  | 565 | Item | employeecenter/SAM/Lists/SAM
Develop Revised Concept Report | 04100 | ROADWAY DESIGN | Roadway;#22;#Concept;#20 | Task Dependent | PE Funding Authorization, Notice to Proceed (NTP) for Consultant Contract, Consultant Kick-Off Meeting, Notice to Proceed (NTP) for Consultant Contract | PM Submit Revised Concept Report, 2nd Concept Layout Revisions for PAR, Receive Layout for UST/HW Phase I, PM Submit Revised Concept Report | 2.1 | Revised Concept (only needed if intended to be critical path) | 30d | Develop Revised Concept Report- 04100 This activity consists of revising the approved concept report. | [14 empty] | N |  | 566 | Item | employeecenter/SAM/Lists/SAM
Prepare Procurement Requisition Form | 19212 | PROGRAM DELIVERY | Procurement;#38;#PM;#18 |  |  | Procurement Requisition Form Submitted by PM | 1.2 | Procurement for Scoping (if needed) | 60d | Prepare Procurement Requisition Form | when a project's scoping is done by a consultant | when a project's scoping is not done by a consultant | [12 empty] | N |  | 568 | Item | employeecenter/SAM/Lists/SAM
PM Posts Corrected PFPR Plans | 40559 | Program Delivery | PM;#18;#PFPR;#23 | Finish Milestone | PM Distributes PFPR Responses | PM Request FFPR | 12.4 | PFPR | 0d | PM Posts Corrected PFPR Plans | when there are corrections requested at PFPR for a project with 12 months or more ROW | when there are no corrections requested at PFPR for a project with 12 months or more ROW; will not apply to shorter projects with less than 12 months for ROW like LIBPs | after PFPR | before FFPR |  | PM will post a letter in ProjectWise documenting the corrections to PFPR plans that were requested at PFPR for review | [8 empty] | N |  | 569 | Item | employeecenter/SAM/Lists/SAM
Interim FPR Summary | 89300 | ENGINEERING SERVICES | General;#26 | WBS Summary |  |  | 2.12 | Interim FPR (2nd) | 46d | Interim Field Plan Review - when ES receives a complete SECOND Interim FPR request from PM for QA/QC review of a complete set of project plans at different milestones to the PM receiving approval on all responses to the Interim FPR report | This activity is needed for some projects when the project's Management ROW date is 30 months from the Management LET date Interim FPR should be held approximately a year or more (depends on how much time is between ROW and LET) prior to Final FPR. | Interim FPRs are not needed if there is MORE THAN 30 months between management ROW date and management LET date. | [12 empty] | N |  | 570 | Item | employeecenter/SAM/Lists/SAM
2nd Interim FPR Request (ES) | 89305 | PROGRAM DELIVERY | PM;#18 | Start Milestone | PM Distributes PFPR Responses | 2nd Interim FPR Request (ES) | 2.12 | Interim FPR (2nd) | 0d |  | A 2nd Interim FPR is needed when there is an extended time between an initial Interim FPR and the management LET date. | A 2nd Interim FPR is not needed unless there is an extended time between an initial Interim FPR and the management LET date. | [12 empty] | N |  | 571 | Item | employeecenter/SAM/Lists/SAM
2nd Interim FPR Request (ES) | 89310 | ENGINEERING SERVICES | PM;#18 | Task Dependent | PM Request 2nd Interim FPR | 2nd Interim FPR Inspection | 2.12 | Interim FPR (2nd) | 20d |  | This activity is needed when a second Interim FPR is needed prior to FFPR. | [13 empty] | N |  | 572 | Item | employeecenter/SAM/Lists/SAM
2nd Interim FPR Inspection | 89320 | ENGINEERING SERVICES | General;#26 | Task Dependent | 2nd Interim FPR Request (ES) | 2nd Interim FPR Report Preparation | 2.12 | Interim FPR (2nd) | 20d | 2nd Interim FPR Inspection - attending 2nd Interim FPR meeting and site visit inspection or preparing and sending waiver letter for 2nd Interim FPR | This activity is needed when a 2nd Interim FPR should be held prior to FFPR. | This activity is not needed when 1 Interim FPR or no IFPRs are needed in a project schedule. | [14 empty] | 573 | Item | employeecenter/SAM/Lists/SAM
2nd Interim FPR Report Approval and Distribution | 89340 | ENGINEERING SERVICES | General;#26 | Task Dependent | 2nd Interim FPR Report Preparation | PM Submits 2nd Interim FPR Responses to ES, Verify 2nd Interim FPR Responses (ES) | 2.12 | Interim FPR (2nd) | 0d | 2nd Interim FPR Report Approval and Distribution - 2nd Interim FPR report is approved and distributed. It is sent to FHWA for signatures if it is a PoDI project. | This activity is needed when a 2nd Interim FPR is needed. | This activity is not needed when a 2nd Interim FPR is not needed. | The date the 2nd IFPR report is sent over to FHWA on applicable PoDI projects. On all other projects, this will be the date the report is distributed. | The date the 2nd IFPR report is received from FHWA on applicable PoDI projects and is distributed. On all other projects, this will be the date the report is distributed. | [10 empty] | N |  | 574 | Item | employeecenter/SAM/Lists/SAM
PM Submits 2nd Interim FPR Responses to ES | 89345 | PROGRAM DELIVERY | PM;#18 | Task Dependent | 2nd Interim FPR Report Approval and Distribution | Verify 2nd Interim FPR Responses (ES) | 2.12 | Interim FPR (2nd) | 10d | [15 empty] | N |  | 575 | Item | employeecenter/SAM/Lists/SAM
Verify 2nd Interim FPR Responses (ES) | 89350 | ENGINEERING SERVICES | General;#26 | Task Dependent | 2nd Interim FPR Report Approval and Distribution, PM Submits 2nd Interim FPR Responses to ES | PM Distributes 2nd Interim FPR Responses | 2.12 | Interim FPR (2nd) | 5d | Verify 2nd Interim FPR Responses - 2nd Interim FPR report is approved and distributed. | This activity is needed for some projects when a 2nd Interim FPR is held. | This activity is only needed for a project with a 2nd Interim FPR. | Date the PM submits 2nd IFPR responses to ES for acceptance. | Date that PM is notified that the 2nd IFPR responses are acceptable. | [10 empty] | N |  | 576 | Item | employeecenter/SAM/Lists/SAM
2nd Interim FPR Report Preparation | 89330 | ENGINEERING SERVICES | General;#26 | Task Dependent | 2nd Interim FPR Inspection | 2nd Interim FPR Report Approval and Distribution | 2.12 | Interim FPR (2nd) | 10d | 2nd Interim FPR Report Preparation - Comments from 2nd Interim FPR meeting are compiled and 2nd Interim FPR report produced | This activity is needed when a project has a 2nd Interim FPR. | This activity is not needed when a project doesn't have a 2nd Interim FPR. | Next working date after the 2nd Interim FPR Inspection. Note: If the report goes out the same date of the inspection, then the date of the inspection should be placed here. | The date you distribute the report or send it over to FHWA for approval on applicable PoDI projects. | [10 empty] | N |  | 577 | Item | employeecenter/SAM/Lists/SAM
PM Distributes 2nd Interim FPR Responses | 89355 | PROGRAM DELIVERY | PM;#18 | Finish Milestone | Verify 2nd Interim FPR Responses (ES) | PM Request FFPR, Submit Corrected FFPR Plans | 2.12 | Interim FPR (2nd) | 0d | [15 empty] | N |  | 578 | Item | employeecenter/SAM/Lists/SAM
Concept Start to Preliminary Plans Start | 0Concept2Prel | PROGRAM CONTROL | Diagnostics;#57 | Level of Effort | Define Project Concept (scoping or pre-concept), Develop Draft Concept and Submit (formerly Define Project Concept), Data Acquisition for Concept (with steps), Data Acquisition for Scoping or Concept (with steps) | Preliminary Roadway Plans (consultant design), Start Preliminary Roadway Plans | 1A1 | Project Diagnostics | 1424d | total duration of activities between Concept Start to Preliminary Plans Start | when a project has concept and preliminary plans in the schedule | when a project does not have concept and/or preliminary plans in the schedule | concept start date | preliminary plans start date | [10 empty] | N |  | 579 | Item | employeecenter/SAM/Lists/SAM
Concept Approval to PFPR Inspection | 1Concept2PFPR | PROGRAM CONTROL | Diagnostics;#57 | Level of Effort | Management Concept Approval Complete | PFPR Inspection | 1A1 | Project Diagnostics | 451d | total duration between Concept Approval to PFPR Inspection | when a project has concept and a PFPR in schedule | when a project does not have concept and/or a PFPR in schedule | Concept Approval date | PFPR Inspection date | [10 empty] | N |  | 580 | Item | employeecenter/SAM/Lists/SAM
Start Technical Studies to Environmental Completion | 2Tech2EnvAPP | PROGRAM CONTROL |  | Level of Effort | Receive Preliminary Plans to Begin Technical Studies | Environmental Approval Complete (If state funds: Env. Activities Complete) | 1A1 | Project Diagnostics | 601d | total standard duration from the start of Technical Studies to Environmental Completion | when a project has Technical Studies and Environmental phases | when a project does not have Technical Studies and Environmental phases | [12 empty] | N |  | 581 | Item | employeecenter/SAM/Lists/SAM
PPFR Inspection to ROW authorization | 3PFPR2ROWAUTH | PROGRAM CONTROL | Diagnostics;#57 | Level of Effort | PFPR Inspection | ROW authorization | 1A1 | Project Diagnostics | 460d | total duration between PPFR Inspection meeting to ROW authorization | when a project has a PPFR and ROW | when a project does not have a PPFR and/or ROW | PPFR Inspection meeting date | date of ROW authorization | [10 empty] | N |  | 582 | Item | employeecenter/SAM/Lists/SAM
Row Auth to Let | 4ROW2LET | PROGRAM CONTROL | Diagnostics;#57 | Level of Effort | ROW authorization | Let Contract | 1A1 | Project Diagnostics | 240d | duration between ROW Authorization and Let date (should be around 12 months or 240d for most projects) | for projects with ROW | for projects without ROW | date of ROW authorization | Let date | [10 empty] | N |  | 583 | Item | employeecenter/SAM/Lists/SAM
FFPR Inspection to Let | 5FFPR2LET | PROGRAM CONTROL | Diagnostics;#57 | Level of Effort | FFPR Inspection | Let Contract | 1A1 | Project Diagnostics | 179d | duration between FFPR Inspection to Let date | for all projects | never | FFPR Inspection meeting date | Let date | [10 empty] | N |  | 584 | Item | employeecenter/SAM/Lists/SAM
Transmit Pavement Type Selection to PM | 21789 | OMAT | Pavement;#14 | Finish Milestone | 21782 Review Pavement Type Selection | 86500 PM Reviews FFPR Package | 12.6.10 | Pavement Type Selection | 0d | Zero day duration activity to document the sending of the approved Pavement Type Selection to PM | When 21732 (Conduct PTS ) is used | When 21732 (Conduct PTS ) is not used | Day PTS is transmitted | Day PTS is transmitted | [10 empty] | N |  | 585 | Item | employeecenter/SAM/Lists/SAM
NEPA class of Action Determination (1 Year LOE from Decision Made to Pursue EA/FONSI through 18100) | 14321 | Environmental | Environmental;#5;#NEPA;#45 | Level of Effort | 14329 Submit Draft EA | 18100 Environmental Approval Complete | 16.10.1 | EA | 370d | tracks the commitment to getting an EA approval within 1 year and starts on the same day that FHWA receives the draft EA for review | when environmental document is an EA | when environmental document is not an EA | same day that FHWA receives the draft EA for review | at EA approval | [10 empty] | N |  | 586 | Item | employeecenter/SAM/Lists/SAM
Conduct Agency Consultation Concurrence for Cultural Resources | 14342 | Environmental | Environmental;#5 | Task Dependent | 14329 Submit Draft EA |  | 16.10.1.5 | Draft EA | 20d | agency consultation for cultural resources, that begins at the decision to pursue the EA | when the environmental document is an EA | when the environmental document is not an EA | [12 empty] | N |  | 587 | Item | employeecenter/SAM/Lists/SAM